[image: image1.wmf]


StreamNet

BPA Project Number 198810804

Fourth Quarter Progress Report

Fiscal Year 2000
Table of Contents

Introduction………………………………………………………………………………..
Page 2

Objective 1.  Data Development………………………………………………………...
Page 3

   Task 1.1.  Anadromous Fish…………………………………………………….…….
Page 3

   Task 1.2.  Resident Fish and Other Aquatic Species………………………………
Page 11

   Task 1.3.  Habitat……………………………………………………………………….
Page 15

   Task 1.4.  Facilities……………………………………………………………………..
Page 17

   Task 1.5.  Habitat Restoration / Improvement Projects…………………………….
Page 20

   Task 1.6.  Sub-basin Planning………………………………………………………..
Page 22

Objective 2.  Data Management and Delivery…………………………………….…..
Page 24

Objective 3.  Library………………………………………………………………………
Page 31

Objective 4.  Services to Fish and Wildlife Program Activities………………………
Page 33



Objective 5.  Project Management / Coordination……………………………………
Page 37
Introduction
This report presents accomplishments of the StreamNet project for the Fourth Quarter of Fiscal Year 2000.  The report is organized to clearly link accomplishments by the project participants to the tasks and responsibilities detailed in the annual Statement of Work.  It is organized by task for all project participants rather than by individual project participant as in previous years.  This report is the second use of the database approach to recording and reporting accomplishments.  While it has taken some time to get the database organized, we anticipate increased flexibility and more rapid assembly of quarterly reports in the future.  Since not all tasks are addressed each quarter and the project participants often work on different tasks, some tasks do not show activity in the Fourth Quarter.

Project participants contributing to the StreamNet project were Columbia River Intertribal Fisheries Commission (CRITFC), US Fish and Wildlife Service (FWS), Idaho Department of Fish and Game (IDFG), Montana Fish, Wildlife and Parks (MFWP), Oregon Department of Fish and Wildlife (ODFW), Pacific States Marine Fisheries Commission (Region), Shoshone-Bannock Tribes (SBT), and Washington Department of Fish and Wildlife (WDFW).


  Introduction





Fiscal Year 2000 Fourth Quarter





Page 2 of 43
Objective
1
Data Development

Increase the knowledge base concerning the region’s fish and wildlife resources through the acquisition of new information that responds to emerging 

needs as well as the updating and enhancement of production and survival trends and other existing information.

Objective  1

Data Development
Task
1
Anadromous Fish

Acquire data sets related to salmon, steelhead and, where data are readily available, other anadromous fish populations from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective
1
Data Development
Task   1   Anadromous Fish
Task
1.a
Distribution, Life History (use type), and Barriers

Document the occurrence and distribution of anadromous species, related barriers to migration, and life history characteristics
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000
  IDFG
1
Develop an associated barriers database. Available, existing 
Continued to identify and code constraints as barrier types into preliminary

information on natural barriers is particularly lacking, so the 
anadromous barriers table.


barriers dataset should be expected to be incomplete.

  ODFW
1
Populate the FishBarrier table by rectifying all anadromous 
Submitted 3,184 new/updated FishBarrier records to StreamNet this 

distribution with the barriers database:
quarter. Continued efforts to populate the FishBarrier table as new 


In the Lower Columbia HUCs (below the Willamette). 
distribution and barrier information were identified.


In the Mid-Columbia HUCs (between the Willamette & John Day 


basins).


In the Upper Columbia HUCs (upstream of the John Day)

  ODFW
2
Update, maintain, and correct the 100k distribution event tables 
1.  Processed supplementary anadromous fish distribution datasets in 

for Oregon as needed and applicable.
order to facilitate comparison with the current StreamNet anadromous 

distribution data.  Many updates to the current distribution are likely to stem from these supplementary databases.  


2.  Developed methodologies for transferring 1:24,000 scale distribution 


data into event format based on 1:100,000 scale routed hydrography.


Processed documentation information to further develop information in the 


DistPres table for the Hood and Fifteenmile subbasins.


Objective
1
Task
1.a
Fiscal Year 2000 Fourth Quarter 
Page 3 of 43

ODFW
3
Update the 100k distribution event tables:  For the Willamette
Routine updates were made to the 1:100k fish distribution event records 

basin using documentation records derived from the W-DESH 2
as errors or omissions were identified.


Project; for the John Day basin; and for the NE Oregon basins


ODFW
4
Test an automated approach to populate the FishBarrier table by 
Continued to refine the process of distribution and barrier data rectification.

rectifying all anadromous distribution with the barriers database 


using the Tillamook basin


ODFW
5
Populate the FishBarrier table for the Willamette basin by
Completed during the second quarter.

rectifying all anadromous distribution with the barriers database.


ODFW
7
Develop a database to capture fish presence survey data to
Continued to enter data into the Fish Presence Survey Database which is 

help populate the DistPresence table.
designed to capture Oregon’s upper fish distribution and culvert 


information collected by ODF/ODFW surveyors.  To date, 1,337 records 


have been entered.


ODFW
8
Develop a database for capturing incidental species
Continued to make enhancements to the database structure. Currently, 28 

observations not routinely reported in agency documents.
of the 91 records in the database are for Columbia Basin streams.


ODFW
9
Locate documentation information in the Willamette (W-DESH 2 
Completed during the first quarter.

Project) in order to populate the DistPresence table.


ODFW
10
Assist in identifying appropriate references for anadromous fish 
Ongoing.

distribution data in order to populate the DistPresence table.


ODFW
11
Assist project staff with identifying appropriate references for 
Ongoing.

anadromous fish distribution.


ODFW
12
Assist in adding new barrier records to the Barriers database 
Efforts with the Barrier Database involved identifying information sources 

including providing references for any information in the 
to populate missing information for existing barrier records. Continued to 


database.
refine the data entry interface.  Participated in discussions to coordinate 


the development of a comprehensive statewide barriers database that 


includes all existing culvert information.


ODFW
13
Plot new Columbia basin barriers on maps for review by ODFW 
Efforts with the Barrier Database involved identifying information sources 

field staff and incorporate changes as needed.
to populate missing information for existing barrier records. Continued to 


refine the data entry interface.  Participated in discussions to coordinate 


the development of a comprehensive statewide barriers database that 


includes all existing culvert information.


Objective
1
Task
1.a
Fiscal Year 2000 Fourth Quarter 
Page 4 of 43

ODFW
16
Transfer all 250K Lamprey distribution data into the 100K data 
Acquired and processed Pacific Lamprey and Brook Lamprey data for the 

structure using data from ORIS.
Midcoast region. Processed ORIS 250k lamprey data.


ODFW
17
Assist as needed with tabular data collection and compilation 
Ongoing.

tasks in order to help produce anadromous salmon distribution 


coverages.


ODFW
18
Compile Columbia basin distribution coverages from other State
Ongoing.

& Federal agencies and incorporate new information into ODFW 


distribution update processes. Four updates planned.


ODFW
19
Update the Barrier database with information obtained during 
Added to and updated Oregon's Barrier Database and submitted records 

conduct of other project activities and submit updated information 
to StreamNet.  The barrier data submission included: 66 Barrier records 


to PSMFC.  Four updates anticipated.
added, 501 Barrier records updated. Conducted q/a on dam data.


Region
1
Compile distribution updates (tabular events) as they arrive.  
QA'd and compiled an update of all Oregon anadromous distribution 

Create distribution GIS coverages from these event tables, and 
events.  Created update distribution coverages from these events and 


post the shape files to the StreamNet website as downloadable 
posted these files to the StreamNet website as downloadable GIS 


GIS coverages
coverages.


Region
3
Assist StreamNet partners with acquisition, development, 
The Regional Fisheries Biologist worked with representatives from ODFW 

formatting and submission of data.
and MFWP to determine if an acceptable and widely-used definition of 


"partial barrier" can be created.  One part of this task was to survey 


biologists regarding how they used the term.  It was determined that the 


term is very widely used, but seldom explicitly defined.  Where defined, 


the definition does not necessarily match the definitions used by others.  It 


was decided that StreamNet would not attempt to define "partial barrier."  


Instead, we will provide space for this item, and another field for defining 


exactly what is meant.  At some point in the future it may be possible to 


categorize these barriers more finely.


WDFW
2
Review barriers in layer, based on SSHIAP information and 
Barriers data review has become part of the data work to support 

indicators in the Stream Catalog. Update and exchange.
subbasin assessments, and so was postponed to avoid duplication.


Objective
1
Task
1.a
Fiscal Year 2000 Fourth Quarter 
Page 5 of 43
Objective  1

Data Development
Task   1   Anadromous Fish
Task
1.b
Adult Abundance

Escapement, redd counts, trap counts, dam counts
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

FWS
2
Complete programs to transform data into StreamNet exchange 
conversion programs completed

format


FWS
3
Submit data through 1999  to StreamNet
submitted 1995-1999 data

IDFG
2
The data will then be migrated to the current version of the PNW 
Started migration and necessary clean up of all existing redd count data to

1:100,000-scale hydrography.
our new 100K LLID based   IDFG StreamNet database management 


system. This included the 1999 field season data and all other existing 


redd count data.


IDFG
3
Write new routines to convert the redd count data to the 
Not started due to delay in migrating data.

StreamNet data exchange format (2000.1) and submit to PSFMC.


ODFW
1
Update StreamNet abundance and indices data (escapement, 
Due to the departure of our abundance database staff person, and the 

redd counts, trap counts, peak/other spawning counts, etc.) for 
anticipated delays in filling the position, no future work was accomplished.


OR populations within the Columbia Basin (updated through 


1998).  Three updates planned.


ODFW
2
Compile some* of the Columbia basin abundance field data 
The new abundance database staff person was hired on Sept. 11th.  

gathered by the CREP crews into the SN abundance dataset.
Efforts this quarter focused on becoming familiar with the StreamNet DEF 


and contacting data providers to get updated information.


ODFW
3
Update existing abundance trends to the new 2000.1 exchange 
Submitted comments on the new interface including a list of errors and 

format standards as trends are updated through 1998.  Three 
their fixes to Regional StreamNet staff and comments to WDFW staff.


updates planned.


ODFW
4
Revise and enhance the Abundance data entry interface to suit 
Due to the departure of our abundance database staff person, no efforts 

project needs.
were made during this quarter.


ODFW
5
Opportunistically review all 60K series trends for Oregon and 
Due to the departure of our abundance database staff person, no efforts 

transfer to 50K series trends or delete them if they cannot be 
were made during this quarter.


validated.


ODFW
6
Review all Oregon trends with personal communication 
Due to the departure of our abundance database staff person, no efforts 

references in the Abundance database and update to hardcopy 
were made during this quarter.


reports if possible.


Objective
1
Task
1.b
Fiscal Year 2000 Fourth Quarter 
Page 6 of 43

Region
1
Assist StreamNet partners with acquisition, development, 
Met with ODFW and WDFW staff and discussed the availability of and 

formatting and submission of data.
obstacles to developing and posting run reconstruction data.  These data 


are used in regulation setting processes, but are not routinely 


disseminated.  Obstacles include incomplete base data (necessitating 


multiple assumptions) and concern over use of the estimates beyond their 


level of reliability.  More work will be needed with the biologists who 


generate these estimates before we can agree on wider dissemination.


WDFW
1
Update and exchange hatchery returns through 1998 in the 
1. Bob updated historical hatchery returns from old hatchery report books 

StreamNet data exchange format (2000.1).
found (years prior to 1965). Worked on moving data into the internal 


databases, locating proper coding, and starting to convert into exchange 


format. Modifications to the exchange format for hatchery facilities have 


slowed this work.


2. Leslie used the TrendUI tool to proof hatchery returns data from Bob 


and found the tool doesn't catch several things worth identifying 


(individual count fields not adding up to total, etc.). She generated her own


maneuvers to catch these additional items; Bob prepared a follow-up 


version of the returns table and Leslie began verifying it once more.


WDFW
2
Update and exchange natural spawner data through 1998
Fall chum, late fall chum, and fall chinook natural spawner returns data 

(CR, PS)
were updated through 1999. Data were prepared for exchange but set 


aside to complete work on hatchery returns data and LLID coding.

Objective  1

Data Development
Task   1   Anadromous Fish
Task
1.c
Juvenile Data

Sample records, abundance indices (as available)
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Prepare and submit recommended modifications of the draft 
Due to the departure of our abundance database staff person, no efforts 

Juvenile abundance portion of the DEF.
were made during this quarter.


ODFW
2
Update Oregon's 10 existing juvenile abundance records to 
New DEF has yet to be proposed or adopted. No efforts were made this 

approved DEF standards.
quarter.


Objective
1
Task
1.c
Fiscal Year 2000 Fourth Quarter 
Page 7 of 43
Objective  1

Data Development
Task   1   Anadromous Fish
Task
1.d
Harvest

In-river, terminal, and other harvest, as available
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Provide statewide 1997 tributary sport harvest from angler 
Acquired, compiled, and maintained in-season updates of catch estimates 

harvest cards.
by species in Columbia River sport and commercial fisheries.


WDFW
1
Update and exchange salmon harvest data through 1998, 
Columbia River mainstem terminal harvest was updated by stock through 

beginning with Columbia River commercial, sport and treaty 
1998 (commercial) and 1997 (sport), and data were prepared for 


harvest.
exchange.


WDFW
2
Update and exchange steelhead harvest through 1997 if feasible.
Steelhead harvest data development was delayed due to competing 

priorities.









Objective  1

Data Development
Task   1   Anadromous Fish
Task
1.e
Hatchery Production

Releases, disposition, straying
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

FWS
1
Compile hatchery release data as it becomes available, add CWT 
managed new hatchery release information

information


IDFG
2
Migrate the data to the PNW 1:100,000-scale hydrography, write 
Work started on migrating the data to our new 100K LLID based IDFG 

new routines to convert the data to the StreamNet data exchange 
StreamNet database management system.


format (2000.1), and submit to PSFMC.


ODFW
1
Develop the ability to remotely access the Portland mainframe 
Due to the departure of our database manager, no efforts were made this

hatchery data and download hatchery return data consistent with
quarter.


 the StreamNet contract.


ODFW
2
Compile 1997 egg-take data and submit to PSMFC
Due to the departure of our database manager, no efforts were made this

quarter. No DEF was adopted by StreamNet this year, therefore no data 


could be submitted.


ODFW
3
Develop an automated procedure for updating egg-take data
Due to the departure of our database manager, no efforts were made this

and to capture and incorporate historic data into the StreamNet 
quarter.


database.


Objective
1
Task
1.e
Fiscal Year 2000 Fourth Quarter 
Page 8 of 43

ODFW
4
Compile data on returns to ODFW hatchery facilities (updated for 
Due to the departure of our database manager, no efforts were made this

1997 and part of 98 returns).
quarter. The new DEF was not agreed upon and adopted by StreamNet 


this year, therefore no data was submitted this quarter.


Region
1
Assist StreamNet partners with acquisition, development, 
In past years, PSMFC entered and updated time-series data.  With staff 

formatting and submission of data.
changes, it is now necessary for the other StreamNet partners to take 


over these "trends" and assume the responsibility for updating them.  


During this quarter, regional staff assisted USFWS staff with which of 


these trends to take over, and how the process should proceed.


Region
2
Acquire data from the RMIS database.
Acquired RMIS Releases and Locations.  Partially processed data into 

StreamNet format, but prior methodology was dependent upon a river 


reach code to Pacific Salmon Commission location code translation table.  


The translation table was incomplete for many new location codes, 


and during this project quarter, StreamNet transitioned into using LLID 


codes for locations, so a new PSC code to LLID code translation table 


must be compiled in order to load these regional release records correctly.


WDFW
1
Update and exchange juvenile release data to PSMFC through 
New person in the position (July 1) was unable to "come up in speed" in 

1999.
time to exchange a new year's worth of data. We expect the exchange to 


occur by the end of December.


WDFW
2
Explore providing “unrolled” release data directly to StreamNet.
No work done (new staff in the Hatchery Data division).

Objective  1

Data Development
Task   1   Anadromous Fish
Task
1.f
Natural Production

Survival, production factors, spawner / recruit
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

Objective
1
Task
1.g
Fiscal Year 2000 Fourth Quarter 
Page 9 of 43
Objective  1

Data Development
Task   1   Anadromous Fish
Task
1.g
Age

Age/sex composition for returning adults
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

IDFG
2
Migrate the data to the PNW 1:100,000-scale hydrography, write 
Started migration of age/sex composition data to our new 100K LLID 

new routines to convert the data to the data exchange format 
based IDFG StreamNet database management system.


(2000.1), and submit to PSFMC.


ODFW
1
Compile age frequency data (updated for natural spring chinook
Completed during second quarter.

in 1997, available time series for natural steelhead in OR portion 


of Columbia basin).


WDFW
1
Provide age/sex data associated with exchanged CRB natural 
Data delayed due to competing priorities.

returns data.

Objective  1

Data Development
Task   1   Anadromous Fish
Task
1.h
Genetics

Areas where genetics data exists and the sources of these data
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

Region
1
Determine the desire/need for and availability of genetics data.
Genetics data were discussed briefly by the Steering Committee.  This 

data type appears to currently be a lower priority.




Objective  1

Data Development
Task   1   Anadromous Fish
Task
1.i
Populations

Population delineation, as determined by others

Project
Work Element
Accomplishments, Fourth Quarter, FY2000

WDFW
1
Compile and exchange Washington SaSI stock status data for 
Started but did not complete conversion of Washington SaSI stock status 

anadromous fish using newly developed 2000.1 Data Exchange 
data to draft StreamNet format; discovered a need to re-synchronize 


Format (DEF)(see Task 2.3).
StreamNet presence data with SaSI spawning areas in parts of the state


Objective  1

Data Development
Task   1   Anadromous Fish
Task
1.j
Historic Range

As available at the watershed-level.  Compilation at the reach level is an option if these data are available
Project
Work Element
Accomplishments, Fourth Quarter, FY2000

Objective
1
Task
1.j
Fiscal Year 2000 Fourth Quarter 
Page 10 of 43
Objective  1
Data Development 

Task
2
Resident Fish and Other Aquatic Species

Acquire data sets related to resident fish species, and where specifically identified other aquatic species, from the multiple agencies, tribes and 

organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective  1

Data Development
Task   2   Resident Fish and Other Aquatic Species
Task
2.a
Distribution and Life History

Document species occurrence and distribution and life history characteristics

Project
Work Element
Accomplishments, Fourth Quarter, FY2000

IDFG
1
As new information becomes available, update and maintain the 
Migrated existing reference based fish distribution data to the 100K LLIDs. 

existing IDFG StreamNet distribution dataset for resident 
Migrated Collection Permit Data to 100K LLIDs. Incorporated both into the 


salmonids and other species of concern that is attached to the 
new IDFG StreamNet database management system.


PNW 1:100,000-scale hydrography.  Include collecting permit 


records and annual reports.


MFWP
1
Convert MRIS from the River Reach Numbering system to an
Completed converting western Montana hydrography from a 

"LLID system" (temporary use of MFWP water code).
temporary "LLID" to a permanent system with LLIDs provided by 


StreamNet regional staff and USFS conversion.  Converted existing data 


in MRIS existing in "routes" based on the old RRN system; converted 


data to routes and measures.


MFWP
2
Restructure MRIS datasets and create a new edit/entry program 
Continued updating edit/entry screen to accommodate copying measures 

with tabular and spatial components for distribution data entry by 
from Arcview over to Access.  Also made other structural changes to the 


measures.
forms to facilitate data entry.


MFWP
3
Update and edit distribution data for game and native fish during 
Continued editing distribution from biologist interviews and data collected 

visits with state and federal fisheries biologists by StreamNet 
during 2nd quarter.  Entered tabular edits from distribution list handed out 


staff during February through June 2000. Collect supporting 
to biologists in the 2nd and 3rd quarter.


references and survey data to document distribution.


MFWP
4
Complete conversion of data to a routed hydrography following 
Worked with NRIS on converting FWP LLID system over to the NHD; 

access to the NHD.
NRIS received a grant to complete a NHD product for the state; name 


checking is first step in the process that they are doing.


Objective
1
Task
2.a
Fiscal Year 2000 Fourth Quarter 
Page 11 of 43


MFWP     
5  Work with regional StreamNet staff to develop a resident
Developed initial proposal for DEF for DistUse, DistPresence, 

fish data exchange format.
DistGenetics, Genetics and Resident Population Estimate tables; provided 


to StreamNet Steering Committee for review.


ODFW
1
Produce GIS coverages illustrating rainbow and redband trout 
Completed during the first quarter for the areas where we have data.

distribution where available for Columbia basin streams.


ODFW
2
Transfer Lahontan cutthroat and white sturgeon 250K resident 
Submitted Lahontan Cutthroat Trout data to StreamNet. Confirmed 

distribution data from ORIS into the 100K data structure and 
accuracy of data based on the regional stream routes.


compare with the current 100K distribution and update 


accordingly.


Region
2
Assist StreamNet partners with acquisition, development, 
QA'd and compiled an update of white sturgeon distribution events.  

formatting and submission of data.
Created updated distribution coverage from these events and posted this 


file to the StreamNet website as a downloadable GIS coverage.


WDFW
1
Update and exchange bull char distribution data at 100K
Completed basic data and map collection for bull char distribution/use 

resolution if multi-agency agreement on distribution criteria can
update. Compilation involved WDFW biologists from Regions 1, 2, 3, and 


be reached (see Task 2.3).
5 plus other knowledgeable (tribal, federal) biologists. Data entry nearly 


completed; review and verification by field biologists will follow. Conversion


to StreamNet exchange formats is scheduled for next fiscal year

Objective  1

Data Development
Task   2   Resident Fish and Other Aquatic Species
Task
2.b
Adult Abundance

Escapement, redd counts, trap counts, dam counts
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Collect stream fisheries survey data collected for population 
Continued collection of survey data from state, federal and private sector 

trends; genetics and escapement, redd counts, trap count and 
biologists.


other counts during visits to biologists.  


MFWP
2
Collect references for each survey.
Began refining the references link from the library to stream data; on larger

reports where numerous species and numerous streams are mentioned, 


difficult to insure that reference is for a particular stream/species.  Will 


look into modifying edit/entry program to accommodate for this.


Objective
1
Task
2.b
Fiscal Year 2000 Fourth Quarter 
Page 12 of 43

ODFW
1
Update existing abundance trends to the new exchange format 
The new abundance database staff person was hired on Sept. 11th.  

standards as trends are updated through 1998.  Three updates 
Efforts this quarter focused on becoming familiar with the StreamNet DEF 


planned.
and contacting data providers to get updated information.


ODFW
2
Review all Oregon trends with personal communication 
The new abundance database staff person was hired on Sept. 11th.  No 

references in the Abundance database and update to hardcopy 
effort was made on this task during this quarter.


reports if possible.


ODFW
3
Update StreamNet abundance and indices data holdings (redd 
The new abundance database staff person was hired on Sept. 11th.  

counts, trap counts, peak/other spawning counts, etc.) for OR 
Efforts this quarter focused on becoming familiar with the StreamNet DEF 


populations within the Columbia Basin (updated through 1998).  
and contacting data providers to get updated information.


Three updates planned.


ODFW
4
Opportunistically review all 60K series trends for Oregon and 
The new abundance database staff person was hired on Sept. 11th.  No 

transfer to 50K series trends or delete them if they cannot be 
effort was made on this task during this quarter.


validated.


WDFW
1
Compile, convert, and exchange portions of the Yakima Basin 
Work delayed until onset of subbasin assessments (Columbia Plateau).

juvenile and adult abundance data from Ken Ham.

Objective  1

Data Development
Task   2   Resident Fish and Other Aquatic Species
Task
2.c
Angler Use

Fishing pressure, creel census
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Add FWP 1999 angler survey data to MRIS collected by MFWP 
Completed the addition of these data to the MRIS database and updated 

mail survey.
on the Internet query program.


MFWP
2
Review available creel census data on Montana's waters and 
Checked with biologists and all creel data is for lakes and reservoirs only.

determine value and availability.


WDFW
1
Explore conversion of Angler Fish Database harvest information 
No work done (vacancy unable to be filled).

from the Columbia Basin into either "harvest" or a new "census" 


format for exchange.


Objective
1    Task
2.c
Fiscal Year 2000 Fourth Quarter 
Page 13 of 43

Objective  1

Data Development
Task   2   Resident Fish and Other Aquatic Species
Task
2.d
Hatchery Production

Hatchery production (releases and outplants) for salmonids
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

IDFG
1
IDFG resident fish stocking data currently uses an IDFG specific 
Worked on attaching stream-based catalog numbers to 100K hydro LLIDs, 

stream and lake locator (Catalog Number). IDFG SN will develop 
with from to measures. Included unmarked or misnamed bridges which 


an ArcInfo compatible event table to cross-reference the catalog 
went into a new landmarks event table.


numbers to LLIDs.


ODFW
1
Acquire 1997 trout release data  (by species, location, and 
Due to the departure of our database manager, no efforts were made this

facility) and compile into SN exchange format.
quarter.


WDFW
1
Complete conversion and exchange resident fish stocking data 
Work not yet completed.

from 1930-1981, once location coding has been standardized and


verified.


WDFW
2
Add stocking data from 1981-1999 if time permits.
Work not yet completed.

Objective  1

Data Development
Task   2   Resident Fish and Other Aquatic Species
Task
2.e
Genetics

Areas where genetics data exists and the sources of these data
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Update genetic spatial and tabular databases that contain the 
Genetics tables updated through the 4th quarter.

results of genetic analysis of populations of Montana's species of


special concern


MFWP
2
Update genetic codes in fish distribution table.
Completed.

MFWP
3
Explore the development of data exchange format with regional 
Sent the genetics DEF with the rest of the draft resident fish distribution 

SN staff
DEF.


Objective
1
Task
2.f
Fiscal Year 2000 Fourth Quarter 
Page 14 of 43
Objective  1

Data Development
Task   2   Resident Fish and Other Aquatic Species
Task
2.f
Population

Population delineation, as determined by others
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Maintain spatial delineation of bull trout populations, core and 
Updated this layer in July with new information from MFWP Native 

nodal habitat.  Enhance layer with population risk field.  
Species Coordinator.  Have not enhanced layer with population risk field.


MFWP
2
Determine westslope cutthroat trout priority areas as part 
Completed and provided hard copy maps of conservation areas to all 

Westslope Cutthroat Conservation Agreement.
biologists involved in their management.


WDFW
1
Synchronize WDFW tabular SaSI data fields and codes with those
Work in progress, awaiting finalization of bull char update and information 

 linked to the spatial presence data for bull char.
from new SaSI data manager.


WDFW
2
Compile and exchange Washington SaSI stock status data for 
Work in progress, awaiting information from new SaSI data manager.

resident fish using newly developed exchange format (see Task 


2.3).

Objective  1

Data Development
Task   2   Resident Fish and Other Aquatic Species
Task
2.g
Historic Range

As available at the watershed-level
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Explore the development of historic range coverages for all of 
Started the initial creation of historic layer by editing of existing TNC 

Montana's native species.
database.

Objective  1

Data Development
Task   2   Resident Fish and Other Aquatic Species
Task
2.h
Status

Population stability index
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Assist regional and state data managers in developing data 
Provided input to regional data managers as requested.

exchange format.


MFWP
2
If DEF adopted, submit bull trout, arctic grayling and westslope 
DEF not adopted; data not provided.

and Yellowstone cutthroat trout data.

Objective
1
Task
2.h
Fiscal Year 2000 Fourth Quarter 
Page 15 of 43
Objective  1

Data Development
Task
3
Habitat

Acquire data sets related to fish habitat from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective  1

Data Development
Task   3   Habitat
Task
3.a
Stream / Watershed Habitat

Incorporate applicable stream and watershed level habitat and stream survey data, as these become available
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Determine what type of habitat data and at what scale Montana 
Completed in 3rd quarter.  Habitat data are generally collected by the 

state and federal fisheries biologists are collecting during regional 
USFS biologists; these data will be available eventually on a nationwide 


visits.
USFS site.


MFWP
2
Determine if there is a core set of variables that we could gather 
In progress.

on each stream.


MFWP
3
Work with regional staff on data exchange format, if sufficient 
No DEF created.

interest and/or data.


MFWP
4
Explore the idea of a statewide stream survey form that would 
Ongoing.

include these core variables (if established).


WDFW
1
Transfer and exchange spatial layers of SSHIAP habitat 
Change in order of SSHIAP product work; spatial layers will not be ready 

characteristics and segmentation (based on gradient, 
until January 2001.


confinement, and substrate).

Objective  1

Data Development
Task   3   Habitat
Task
3.b
Water Quality

 Incorporate existing Clean Water Act 303(d) data and other water quality data as applicable
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Provide a link to The MT Dept. of Environmental Quality (DEQ) 
This link has been created by NRIS to the DEQ data; on-line, you can get 

from MRIS.  The Natural Resource Information System (NRIS) 
TMDL data and MRIS fisheries data.


has been contracted by DEQ to develop a web-based application 


of these data.


Objective
1
Task
3.b
Fiscal Year 2000 Fourth Quarter 
Page 16 of 43

MFWP
2
Provide MRIS data and expertise in the process of updating the 
DEQ staff utilized on-line MRIS to update their process.

303(d) (TMDL) affected water bodies for the state.  Integrate 


these data into the sub-basin planning effort if opportunity arises 


during the fiscal year.


Region
2
Develop data structure for stream nutrient data compiled by 
Developed a relational data structure for stream and lake nutrient data 

PSMFC
compiled by PSMFC.


Region
3
Georeference (assign LLIDs) to the stream nutrient data
Completed georeferencing of all stream and lake nutrient data.  Moves this 

data into a relational data format and posted to the StreamNet web site for 


download as both GIS and tabular data sets.

Objective  1

Data Development
Task   3   Habitat
Task
3.c
Miscellaneous Habitat Data



Incorporate habitat data from various sources, as appropriate

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Provide links through NRIS with GAP and other statewide
Accomplished by NRIS but not through this contract.

natural resource data.


MFWP
2
Update and incorporate MFWP water leasing and dewatered 
Completed.  Updated both these tables in MRIS and on the web.

stream list data into MRIS.


MFWP
3
Provide to StreamNet if data exchange format is developed.
No DEF.

ODFW
1
Update key stream management area designations for OR 
No changes have been made to these data layers therefore no efforts 

including FEMAT key watersheds, AFS aquatic diversity areas, 
were made this quarter.


ODFW coho source river reaches, ODSL essential salmon 


habitat and Priority Areas.


WDFW
1
Explore Cosentino's model to assess habitat suitability for
Change in order of SSHIAP product work; spatial layers will not be ready 

anadromous and resident fish by comparing predictions to
until January 2001.


actual.  Write paper on techniques and findings.


Objective
1
Task
3.c
Fiscal Year 2000 Fourth Quarter 
Page 17 of 43
Objective  1     
Data Development
Task
4
Facilities

Acquire data sets related to fishery-related facilities and structures from the multiple agencies, tribes and organizations within the Columbia Basin and 

compile and maintain them in standardized, consistent formats for the following categories:

Objective  1

Data Development
Task   4   Facilities
Task
4.a
Dams and Fish Passage Facilities

Enhance the existing StreamNet dams data set by updating relevant data from the Pacific Northwest Hydropower Database and Analysis System NWHS) and the National Inventory of Dams
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

IDFG
1
Add enhanced data from the National Inventory of Dams to the 
Worked on migration and necessary clean up of our enhanced dams data 

IDFG StreamNet information system.
(NID plus Idaho Department of Water Resources database) to the new 


IDFG StreamNet database management system.


MFWP
1
Quality check the existing StreamNet dams dataset and update 
Ongoing; duties have been transferred to Jeff Hutten and will be 

relevant data from the GNIS and the National Inventory of Dams,
completed in FY2001.


if needed.


MFWP
2
Exchange Montana's data.
Ongoing

ODFW
1
Update the dam database with information obtained during the 
Added to and updated Oregon's Barrier Database, which contains 

conduct of other project activities.  Four updates planned
information on Oregon dams.  Submitted new and updated dam records to 


StreamNet.  The data submission included: 59 Dam records added, 198 


Dam records updated, 144 DamXDamPurpose records added, 88 


DamXDamType records added.


Region
1
Convert remaining 250K Dams information in StreamNet
Georeferenced all Oregon and Washington dams, where possible, to 

database to the 100K system. Create a 100K Dams and Fish
1:100,000 scale stream-based locations (w/ LLIDs).  Returned this 


Passages facilities GIS coverage and distribute it via the
information to ODFW and WDFW for verification. 


StreamNet website.


Region
2
Assist StreamNet partners with acquisition, development, 
Assisted ODFW in determining correct locations of dams.  Assisted 

formatting and submission of data.
WDFW in comparing NID dam locations to Washington Dept of Ecology 


dam locations.


WDFW
1
Review, update, and exchange any new Washington state dams 
Provided most recent dataset from WDOE to David Graves. Assisted in 

information.
solving some data "mysteries".


Objective
1
Task
4.a
Fiscal Year 2000 Fourth Quarter 
Page 18 of 43
Objective  1

Data Development
Task   4   Facilities
Task
4.b
Hatcheries

Update and maintain a dataset on anadromous and resident hatchery facilities containing information on location, design, management and uthorization
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

FWS
1
Continue checking for submitted FWS update records, update 
periodically checked StreamNet web site for updated information

records when appropriate, submit to StreamNet


IDFG
1
IDFG StreamNet has attached the IDFG hatchery database to
Worked on migration and necessary clean up of hatchery facilities to the 

the current 1:100,000-scale PNW hydrography. The data will be 
new IDFG StreamNet database management system.


incorporated into the IDFG database and submitted to PSMFC.


IDFG
2
Supporting hatchery structures, such as weirs and traps, will be 
Started to build a database of traps and weirs tied to the 100K LLID 

added to the hatcheries database.
hydrography. Includes data from 1956-2000.


MFWP
1
Provide update of these data if changes have occurred in 
No changes.

Montana's facilities.  


ODFW
2
Update OR hatchery facilities data to the 99 version of the 
1.  Updated the Oregon Hatchery Facilities data to the 2000.2 version of 

exchange format and submit to PSMFC.
the exchange format.  Contacted hatchery staff members and updated the 


records for which information was provided.  Submitted 36 hatchery 


facility records to StreamNet this quarter.


2.  Reviewed WDFW's proposed changes to the Hatchery Facilities table 


and provided comments.


WDFW
1
Provide standard geo-spatial coordinates (Longitude-Latitude)
Work in progress.

for each facility.


WDFW
2
Compile similar coordinates for fish releases that occur away 
Work not started due to competing priorities.

from these facilities, in order to develop a spatial layer of fish 


release sites (including streams, lakes, and marine areas.


WDFW
3
Complete, convert, and exchange tabular and spatial data
1.  Worked to develop a standardized system of water body and site 

tables of Washington state hatchery facilities, including federal
identifiers for fixed entities (hatchery facilities) that is compatible with the 


and tribal stations.
100K LLID system of stream identifiers.


2.  Gil updated the spatial layer of hatchery facilities to bring it in line with 


the tabular data exchanged with StreamNet in May 2000.


3.  Leslie pursued finding specific site locations for about 70 entries in the 


hatchery facilities table.


4. Leslie accepted the role of chair of the SN data team charged with


resolving location coding questions for the hatchery facilities exchange
format. She sent an updated draft format to all tech team members that


were appointed in July at the Helena meeting. She contacted all members


to get their responses and attend the September GIS Team meeting


to work out some spatial data issues related to the hydrology layer.


Objective
1
Task
4.b
Fiscal Year 2000 Fourth Quarter 
Page 19 of 43
Objective  1

Data Development
Task   4   Facilities
Task
4.c
Diversion/screening

Develop a dates for water diversions and screening
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Review regional data exchange format.
No DEF to review.

ODFW
1
Identify fish screening data that is appropriate for the StreamNet 
No exchange format has been developed, therefore no efforts were made

site and submit test records once an exchange format has been 
this quarter.


adopted.


ODFW
2
Develop a database structure Oregon's fish screening data and 
Provided technical assistance as requested, and modified the basic 

submit a draft data exchange format to SC for adoption.
database that was developed last quarter to meet project needs.

Objective  1

Data Development
Task
5
Habitat Restoration/Improvement Projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:
Objective  1

Data Development
Task   5   Habitat Restoration/Improvement Projects
Task
5.a
Fish and Wildlife Program Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects related to the Fish and Wildlife Program
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Incorporate Fish and Wildlife Program Projects for Montana into 
Exchange with StreamNet DEF begin in fourth quarter; will complete the 

Restoration and Mitigation database and submit in data exchange 
conversion and DEF in FY2001.


format. 


ODFW
2
Provide technical assistance to GWEB and StreamNet staff as 
Provided technical assistance to OWEB staff, answering MS Access 

needed to make compilation of ODFW habitat restoration /
questions to make compilation of ODFW mitigation and restoration data 


improvement projects in the Columbia basin more efficient.
more efficient.


Objective
1
Task
5.a
Fiscal Year 2000 Fourth Quarter 
Page 20 of 43

Region
3
Assist StreamNet partners with acquisition, development, 
Regional staff worked with WDFW staff to evaluate the utility of 

formatting and submission of data.
Washington Department of Outdoor Recreation's PRISM database for 


StreamNet use.  The PRISM database is used in Washington to track 


implementation of projects on the ground, and had potential use as a 


standard database for the region.  It was discovered by WDFW staff, 


however, that PRISM has a fatal flaw in terms of StreamNet's needs, 


because it did not allow for the degree of complexity which is necessary 


for capturing fish habitat restoration projects.


WDFW
1
Compile and convert a test set of restoration project data from
1. Gil began converting key MS Access tables from the PRISM system to 

 the Interagency Commission (which oversees state salmon
Paradox and scoping the table contents, documenting his findings along 


recovery project funds) PRISM database (which monitors
the way. He also began the work of trying to fit critical fields into 


project contracts) into exchange formats for conversion (projects
StreamNet's exchange format. Leslie will review his work and perform the


since 1995).
 actual exchange.


2. Gil received additional information from the USFS (the IRDA database) 


and the Nooksack Salmon Enhancement Association (a local database) as 


a result of inquiries he sent our to several sources seeking additional 


sources of habitat restoration information.

Objective  1

Data Development
Task   5   Habitat Restoration/Improvement Projects
Task
5.b
Other Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects other than related to the Fish and Wildlife Program
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

IDFG
1
IDFG StreamNet will continue to compile information from non-
Completed entry of data from Idaho Conservation Data Center and 

FWP restoration projects into the PSMFC projects database
submitted to PSMFC. Updated structural and coding changes to the 


and interface and submit to PSMFC.
MitProjects GUI. Compiled data from BLM NEPA logs for 2000 for all 


resource areas in Idaho. Also, compiled miscellaneous BLM data. 


Established a working relationship with Boise National Forest by helping 


them develop data standards for a similar process they are starting. This 


will allow us to easily incorporate their data later on.


MFWP
1
Data will be updated for FWP Projects during FY-00; a spatial
Locations for western Montana checked and verified by MFWP biologists. 

data layer of project location will be checked by regional staff
Received all other projects during visits and inputted into Montana's 


and the possibility of adding other agency/FWP divisions will be
system.  Will exchange 2nd quarter FY2001.


explored during regional visits. 


MFWP
2
Exchange Montana data in data exchange format.
Ongoing.

ODFW
2
Provide technical assistance to GWEB and StreamNet staff as 
Provided technical assistance to OWEB staff, answering MS Access 

needed to make compilation of ODFW habitat restoration /
questions to make compilation of ODFW mitigation and restoration data 




improvement projects in the Columbia basin more efficient.
more efficient.










Objective
1
Task
5.b
Fiscal Year 2000 Fourth Quarter 
Page 21 of 43
Objective  1
Data Development
Task
6
Sub-basin Planning

Develop consistent data sets and information that are particularly suitable and useful for regional sub-basin planning and make them readily available for planners

Objective  1

Data Development
Task   6   Sub-basin Planning
Task
6.a
Provide data for Sub-basin Planning

Organize and distribute the available fish, wildlife and habitat data in a standardized format for use in Sub-basin Planning or other regional planning efforts
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

MFWP
1
Coordinate with MT CBFWA rep and provide available fish,
Coordinated with Montana CBFWA rep and competed a set of maps for 

 wildlife and habitat data in a standardized format for Sub-basin
the Flathead and Kootenai drainages for their document.  A set of maps 


Planning or other regional planning.  
was created for cutthroat genetic purity, bull trout distribution, stream 


classification information (which is based on a variety of habitat and 


species distribution on native species), barrier locations and wildlife 


habitat (included bald eagle habitat, big game seasonal distribution, lynx 


distribution, wolf pack distribution, grizzly bear management areas, 


waterfowl production areas, and state and national wildlife refuges).


ODFW
2
Participate in discussions concerning data needs to support 
Continued to consulted with ODFW staff who are preparing the Hood and 

sub-basin planning or other processes adopted by the amended 
Fifteen Mile subbasin summaries to identify ways StreamNet might be able 


Fish & Wildlife Program. Modify data plan and priorities as
to help.


needed to be responsive.


Region
2
Develop, with help from the state SN projects, an 'example' 
Enhanced an 'example' package of GIS information for subbasin planning 

package for a test sub-basin of StreamNet data suitable for use
and created a PowerPoint presentation to demonstrate this information and


in sub-basin planning.
StreamNet GIS capabilities.


WDFW
1
Participate in discussions concerning data needs to support 
1. Met with NMFS staff and Drew Parkin in Seattle to discuss NMFS data 

sub-basin planning or other processes adopted by the amended 
needs for Viable Salmon Population analysis and relationship to Basin 


Fish & Wildlife Program. Modify data plan and priorities as needed 
data needs for subbasin assessments.


to be responsive.
2. Met with Council Staff (Drew Parkin, Peter Paquet) to discuss a strategy


and possible StreamNet role in developing data to support subbasin 







assessments.

WDFW
2
Coordinate data compilation from other WDFW Units as 
Data compilation has not begun.

needed to respond to the above needs, using StreamNet 




data exchange experience.
Objective
1
Task
6.a
Fiscal Year 2000 Fourth Quarter 
Page 22 of 43

WDFW
3
Provide consultation services for WDFW wildlife and habitat
Data compilation has not begun.

data managers to assist them in meeting the above needs.

Objective  1

Data Development
Task   6   Sub-basin Planning
Task
6.b
Capture information from Sub-basin Planning

Acquire information developed during subbasin planning to update anadromous fish, resident fish, and wildlife data sets
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

CRITFC
1
In collaboration with regional staff, develop computer applications 
Subbasin planning was delayed by the Power Council until spring of 2001.

to enter and edit information developed during subbasin planning 
In collaboration with tribal staffs, we did some scoping of the new data 


as described in Tasks 1.1 through 1.5, above.
sources and the work load which may be involved in capturing new 


subbasin planning data. We developed a draft set of standard tables for 


fish population data, based on the Stock Summary Reports. These tables 


are being prototype tested by the Yakima Nation during the present 


Provincial "rolling review" process.


CRITFC
2
Train subbasin planners in use of the applications.
Discussed use of the prototype tables developed under task 1.6.b.1 with 

tribal staff and tribal contractors working on subbasin summaries under 


the rolling review process.


CRITFC
3
Modify tools as needed on experience in the Columbia Gorge 
Tools will be developed and tested under the FY01 contract.

province


MFWP
1
Collaborate with regional staff and Montana CBFWA 
No data available at this time.

representative when data become available


ODFW
1
Determine the Subbasin Planning generated data types that
Continued reviewing draft subbasin summaries to identify new data types 

are not contained in StreamNet and adjust staff work plans to
that StreamNet might consider compiling. Efforts this quarter focused on 




capture new data if appropriate

examining reference lists in the summaries for potential new data.

Objective
1
Task
6.b
Fiscal Year 2000 Fourth Quarter 
Page 23 of 43
Objective
2
Data Management and Delivery

Provide high quality data management services, with specific emphasis on the creation of regionally consistent data sets and the timely delivery of data to users in formats that meets their policy, planning, and management needs
Objective  2

Data Management and Delivery
Task
1.
Database Management

Maintain functional database programs at the state and regional levels to make consistent data sets for anadromous fish, resident fish and to a lesser extent wildlife available through the StreamNet online database system.  At both the regional and state levels, provide database management and administration necessary for accomplishing StreamNet objectives, to include: 1) maintaining regional and state-level StreamNet data sets, 2) processing exchange data into the regional database, 3) transporting data to the SQL environment, 4) enhancing StreamNet database structures and capabilities, and 5) providing programming services to project participants to allow for efficient data entry and transfer.

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Provide state-level StreamNet database management / 
1.  Continued testing, modifying, and commenting on the StreamNet 

administration / development.  Enhance StreamNet and ODFW 
Access user interface.


database structure and capabilities as possible.
2.  Continued to scope the development of a composite database which 


will be used to capture a variety of different survey information.


3.  Due  to the departure of our database manager, efforts were limited this 


quarter.


ODFW
2
Modify/update the EventMapper tools with updated event data 
Incorporated new barrier and lake coverages for OWEB and ODFW staff 

and/or background GIS layers.
members.


ODFW
3
Maintain and update state-level StreamNet data sets, database 
Submitted records and photos from Oregon's Image Database to 

structures, and interfaces.
StreamNet.  Submitted: 38 MapCat records, 2 MapCatXBarrier records, 32 


MapCatXDam records, 38 MapCatXFormat records, 4 MapCatXHatchery 


records, 38 MapCatXState records, and 38 Photos.


ODFW
4
Develop custom GIS projects and database structures that help 
Technical assistance was provided to several ODFW data collection 

improve data management transfer with ODFW field staff.
projects which will aid in greater data availability and more efficient data 


transfer to StreamNet.


ODFW
5
Develop custom database products in support of project data 
The Riparian Lands Tax Incentive Program database was completed. 

compilation efforts as described in 3.1 below.
Version 2.1 of the database structure can be made available to StreamNet 







staff upon request.

Objective
2
Task
1.
Fiscal Year 2000 Fourth Quarter 
Page 24 of 43

ODFW
6
Investigate and summarize the pros and cons of distributed vs. 
Completed during the third quarter.

centralized information systems


ODFW
7
Update existing data sets as described in Task 1 and provide
Due to the departure of our database manager and our abundance 

data to the regional StreamNet office in DEF.  Provide data as
database staff person, efforts were limited this quarter.


sub-sets are updated rather than waiting for entire data to be 


complete.


Region
2
Add data submitted to the StreamNet regional office into the SN
Loaded 356 Oregon Restoration/Improvement projects and associated




database within ~30 days of receipt from the project partners.
ownership records for ODFW.


Region
3
Assist data-providing agencies with error checking of data sets.
1.  Regional staff discovered errors with the habitat restoration data 

submitted by ODFW.  ODFW staff were informed, and they worked with 


OWEB staff to correct the problems.


2.  Regional staff discovered and documented errors in hatchery release 


data that had been entered by regional staff in previous years.  ODFW, 


which is taking over ownership of these records, was notified of the 


errors found.


Region
5
Update the database structure as new data categories are added 
The regional database tables were modified to accommodate LLID




or categories are changed.




georeferencing, and additional lookup tables were created to optimize













data queries from the web based system.  This was a major revision.


Region
8
Develop metadata for spatial data sets posted to the StreamNet 
Developed metadata for new spatial data sets posted to the StreamNet 

GIS web page.
GIS Web page and updated existing metadata when updates to the 


related spatial data sets occurred.

Objective  2

Data Management and Delivery
Task
2.
Data Plan

Update and maintain a project data plan that identifies 1) current data holdings at the regional level, 2) data items to be incorporated in the current contract period and in future years, and 3) expectations for data development and delivery from participating organizations within the current contract period

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Work jointly with other participants to modify elements of data
Reviewed the draft StreamNet Charter document.

plan or priorities based on needs arising out of sub-basin 


planning or other processes that drive Basin data needs through 


the amended Fish &Wildlife Program.


Objective
2
Task
2.
Fiscal Year 2000 Fourth Quarter 
Page 25 of 43
Objective  2

Data Management and Delivery
Task
3.
Data Exchange Standards

Establish and maintain data exchange standards that ensure consistent format and content of data that originated from the multiple agencies and data 

sources in the basin.  Included will be proposed and adopted data exchange formats, metadata and location look-up tables for specific data items as 


described under Objective 1.  At the regional level, this task will provide technical assistance regarding standard codes and exchange formats for Fish 


and Wildlife Program and ESA- related projects, and for applicable tribal data compilation activities.  At the state level, this task will provide similar technical assistance for state agency data activities applicable to StreamNet.


Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Participate in the design, development and maintenance of 
Reviewed and commented on FishBarrier and barrier issues.  Reviewed 

standard codes and data exchange formats. This will occur 
and commented on the new quarterly report format (the quarterly 


through involvement on the Steering Committee and technical 
database).   Reviewed and responded to comments by PSMFC staff 


work groups. There is no set schedule for this task, because it is 
regarding mapping the mitigation/restoration data.  Reviewed and 


highly dependent on issues facing the Steering Committee. 
commented on the FY-2001 StreamNet Statement of Work. Coordinated 


Potential new data exchange standards may include juvenile 
with regional StreamNet staff to develop a draft definition for the term 


abundance, genetics, stream habitat, stream temperature and 
"partial" blockage in relation to the FishBarrier table.


resident fish releases.


Region
1
Work with the project database managers to identify needed 
1. Coordinated creation of new StreamNet codes for species.

modifications to the Data Exchange Format (DEF) to
2. The exchange format was updated for several items which have been 


accommodate changing data needs
agreed to since the adoption of version 2000.1.  These changes will take 


effect with the next version, which will be 2001.1.

Objective  2

Data Management and Delivery
Task
4.
GIS Data System

Establish and implement procedures for coordination of StreamNet-related spatial data activities among participating organizations, to include regular 

meetings and or other communication links among participating GIS specialists. Designate and maintain metadata format for spatial data to be used by 


StreamNet participants. Prepare map products in hardcopy and/or electronic format for use in Program-related aquatic resource policy, planning, and 


management.  Provide for distribution of spatial data in GIS and tabular format and as GIS products.

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Participate in planning and coordination meetings for state-level 
Attended Oregon / Washington Hydrography Framework group meeting in 

24k hydrography layer to ensure compatibility with the PNW
Olympia.  Learned of specifics regarding direction of USFS hydro 


100k hydrography.
standards in relation to the NHD and the upcoming FGDC standard and 


the associated impacts on the Framework model development.


Attended OGIC Hydro subcommittee meeting covering 100k / 24k issues.


Objective
2
Task
4.
Fiscal Year 2000 Fourth Quarter 
Page 26 of 43


ODFW
     2  General maintenance activities associated with the GIS data 
Tested out both Arc Info / Access and Arcview / Access functionality in 

 system
relation to meeting future data development needs and also improving 


data development efficiency.


ODFW
3
Develop a lakes coverage for Oregon.
Completed during the third quarter.

ODFW
4
Participate in spatial metadata format development processes with
Participated in discussion to formulate a metadata strategy at the 

 PSMFC, WA, ID, & MT.
StreamNet GIS coordination meeting in Olympia.


Region
1
Maintain and enhance a geographic information system (GIS) 
1.  Maintained a geographic information system related to regional 

related to regional StreamNet goals and objectives.
StreamNet goals and objectives.


2.  Coordinated a StreamNet meeting of GIS staff in Olympia.


3.  Researched and wrote a report on internet mapping for the StreamNet 


steering committee.


4.  Updated the regional lakes/reservoirs GIS layer to clean up lakes 


situated on state boundaries.


5.  Developed a GIS coverage of adult returns (trend) information and 


associated metadata and posted to the StreamNet site for download in a 


GIS format.


6.  Errors were found and corrected in the GIS subbasin boundary layer.


Region
2
Prepare GIS data and map products from StreamNet data.
Prepared GIS data and map products from StreamNet data, as needed.  

Responded to all requests from the public and prepared GIS data, maps, 


and other products for 21 public requests relating to mapping or GIS.  


Requests were from a variety of sources including private citizens, 


environmental consulting firms, government agencies, educators, and 


students.


Region
3
Integrate the functioning of the GIS system with the StreamNet 
Integrated the functioning of the GIS system with the StreamNet fisheries 

fisheries and habitat database, in support of the query system.  
and habitat database.  Maintained and updated cross tables of our LLID 


Create cross tables and queriable maps used via the StreamNet 
stream locations by county, subbasin, hydrologic cataloging unit, state, 


web interface.
and region in support of the query system.  Created queriable GIS 


coverages of updated fish distribution and hydrography for the StreamNet 


web interface.  Updated downstream stream tributary information for 


1:100k streams to approximately 90% of all streams for better stream 


identification in the online system.  Added previously designed subbasin 


base maps to the online map catalog.


Region
4
Direct users to other GIS resources when requests exceed
Directed users to other GIS resources when requests exceeded 

StreamNet capability
StreamNet capability.


Objective
2
Task
4.
Fiscal Year 2000 Fourth Quarter 
Page 27 of 43
Objective  2

Data Management and Delivery
Task
5
StreamNet Internet Site

Continue to maintain and enhance the existing client-server system to provide access to StreamNet data products through the Internet.  The StreamNet 

home page will continue to be recognized as the project's primary data delivery vehicle.  Priority will be given to incorporating data developed through 


Objective 1 and providing access to reference materials secured through Objective 3.  Appropriate training on the use of the system will be provided 


through a combination of on-line help and in-person training sessions.

Objective  2

Data Management and Delivery
Task   5   StreamNet Internet Site
Task
5.a
Maintain the StreamNet Client Server system
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

Region
1
Maintain, upgrade as needed, and administer the StreamNet
We experienced a failure of one hard drive on our database server.  Since

web servers.
this was one of a three-drive RAID system, this compromises the internal 


backup features of the server.  We developed a plan to request 


replacement of this server through BPA's spending authority.


Region
2
Convert the query system from the RRN to the LLID system where
1.  Conversion of the query system from the RRN system to the LLID 

 possible.
system was completed during this quarter, with the new system going live


on the StreamNet web site on August 28, 2000.  Extensive and varied 


work went into this effort, including discussions of necessary and 


potential changes or updates to the database, devising a new system for 


tying data to geographic areas, programming, extensive testing / 


debugging, and other related activities.


2.  The user survey was implemented the same day as the new query 


system.

Objective  2

Data Management and Delivery
Task   5   StreamNet Internet Site
Task
5.b
Enhance and improve the StreamNet website

 Maintain and enhance components of the StreamNet home page and incorporate new features that complement existing components
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

CRITFC
1
Work with subbasin planners to identify modifications and new 
Subbasin planning was deferred into 2001 by the Power Council. Hence, 



uses which will make the website more useful to them

work on this task will occur in the next fiscal year.


Objective
2
Task
5.b
Fiscal Year 2000 Fourth Quarter 
Page 28 of 43

CRITFC
2
Identify changes and new features which will improve delivery of
Held periodic discussions with Power Council contractors to identify 

 Library services
literature services which will be useful to stakeholders during the NPPC 


rolling review and subbasin planning activities. It was determined that 


enhancements of Internet-based services could be provided more 


efficiently if CRITFC managed a library web site separate from but linked 


with the main StreamNet web site.


CRITFC
3
Work with regional staff to implement changes identified above.
Identified changes will be implemented in FY01.

MFWP
1
Montana will review and comment when necessary.
No requests were received

ODFW
1
Recommend and/or take part in review of new products and 
Reviewed and commented on the StreamNet test and production query 

features.  Provide feedback on content, suitability, navigability
systems.


and data currency issues.


Region
1
Develop and conduct an online survey of users to determine the 
An on-line survey was developed and deployed during the quarter.  The 

need for modifications to the site, the data or the project.
purpose of the survey was to ask StreamNet users the types of data they


come to StreamNet to find, what they wish StreamNet had that we do not,


and to obtain other various feedback.  All users of the StreamNet query 


system were exposed to the survey questionnaire before proceeding to the


query system.  Unfortunately, very few people filled out the 


questionnaire.  Because very few people took the survey, it was not 


worth the effort to do a thorough analysis of the results.  No clear trends 


were evident from the few results obtained (less than two dozen 


responses, some of which were obviously only casual users).


Region
2
Review the website for clarity, organization and ease of use.  
During the quarter, a user pointed out an error in the "species database" 

Recommend and implement changes to maximize utility for
contained in the Fish Facts portion of the StreamNet web site.  Further 


people accessing the site to obtain information
investigation revealed more errors.  The creator of the species database 


was contacted, and he provided the sources of the information.  As time 


permits, the species database will be reviewed, any necessary 


corrections will be made, and citations will be added for all information.


Region
7
Modify the query system to function with revisions to the DEF
The query system was modified to function with the revised DEF and 




brought on line. 


WDFW
1
Take part in review of new products and features. Provide 
Gil reviewed and reported comments on the new StreamNet Online Test 

feedback on content, suitability, navigability and data currency 
Query system. Leslie reviewed and commented on the GIS maps 


issues, especially issues related to providing static or dynamic 
available, and Gil also looked at the MRIS site to compare what was 


map capabilities.
available there to similar StreamNet services.


Objective
2
Task
5.b
Fiscal Year 2000 Fourth Quarter 
Page 29 of 43
Objective  2

Data Management and Delivery
Task
6.
1:100,000-scale Hydrography

Maintain the 1:100,000-scale PNW hydrography for purposes of attaching StreamNet data.  Coordinate with efforts to prepare a National Hydrographic 

Dataset (NHD). Develop a standardized method for incorporating lake hydrography and attribute information.

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Submit issues and corrections to 100K stream coverage as 
Submitted information on two streams in the "allstr" table that have 

identified during other data compilation activities.
anomalous BegFt data. Modified stream routes in the Sandy River, Goose 


Lake and Donner Und Blitzen river subbasins.


ODFW
2
Review Duane's RRN-LLID cross-reference table for errors and 
Worked to get correct LLIDs assigned to barrier, dam and hatchery 

incorporate LLIDs into Oregon's abundance records
records.


ODFW
3
Review and provide an evaluation of the NHD test CU's.
Completed during second quarter.

ODFW
4
Participate in technical and policy discussions concerning 
Reviewed the NHD model and participated in a discussion amongst 

adoption of the NHD 100K framework for the Northwest.
StreamNet GIS staff to determine the suitability / challenges of this model 


in relation to existing / future StreamNet hydrography needs.  It was 


determined that further testing was necessary which will occur in FY2001


Q1.


Region
1
Continue to maintain the regional 1:100,000-scale PNW 
Designed a hydrography web page for use by regional entities.

hydrography.


Region
2
Implement updates to the 1:100,000-scale PNW hydrography
Corrected hydrography errors in Oregon in coordination with ODFW and 

from state cooperators.
integrated the Smith R watershed (HUC 18010101- Southern Oregon) into 


the PNW Reach files.


Region
3
Update and serve a regional web version of the 1:100,000-scale 
Created an updated set of PNW hydrography in multiple formats and 

PNW hydrographic set from the StreamNet website.
posted to the StreamNet web site for download.


Objective
2
Task
6.
Fiscal Year 2000 Fourth Quarter 
Page 30 of 43
Objective  2

Data Management and Delivery
Task
7.
Data Requests

Receive and respond to requests for data, source materials, and custom products.  Response to requests will be honored within the limits of available 

resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.  Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural resource management activities.

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
As requested, consistent with other deliverables in this contract, 
A total of 12 data, 60 document, and 4 other requests were answered 

receive and respond to requests for data, source materials, and 
during this quarter. A detailed list by requester and request type can be 


custom products.
made available upon request.  Also, 2,820 data downloads were made 


from the ODFW FTP site during this quarter.


ODFW
2
As requested, provide training and instruction on the use of the 
Instruction on the use of the StreamNet web site was provided to at least 

StreamNet website data delivery system.
4 individuals via phone conversation.


Region
1
Respond within one day whenever possible to all user requests 
1.  The Regional GIS Specialist responded to 21 GIS/map related requests 

received via email, phone, or other medium.  Typical requests 
this quarter. 


received include help using the query system, complex data 
2.  The Regional Fisheries Biologist responded to 20 data/help requests 


requests not easily done with the query system, and requests 
this quarter.


for GIS coverages and maps.

Objective  3

Library / Reference Services

Provide a full service regional library for fish (and to some degree wildlife) literature (published and gray), including documentation of all data in the 

StreamNet database.

Objective  3

Library / Reference Services
Task
1.
Collection Development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document data source materials, Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies, interested parties, and other libraries.

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Provide originals/copies of all documents and reports referenced 
Submitted 189 documents associated with StreamNet data to the 

in the compilation of new StreamNet data holdings, but not
StreamNet Library during this quarter.


already housed in the StreamNet Library.


Objective
3
Task
1.
Fiscal Year 2000 Fourth Quarter 
Page 31 of 43


ODFW
    2 Update the set of historic Oregon Fish Commission and Game 
This effort is on hold till our Library tracking software is updated (see Task

Commission reports and provide to the StreamNet library as 
 3.2).


available.


ODFW
3
Update library bibliography of ODFW, Fish Commission, and
This effort is on hold until our Library tracking software is updated 

Game Commission reports with 99 ODFW publications and
(see Task 3.2).


make bibliography available to the StreamNet Library for reference.

Objective  3

Library / Reference Services
Task
2.
Provide Access to Collection

Provide user access to the materials described in Task 3.1 by providing facilities for storage of paper and electronic copies of documents, an online 

catalog of all documents in collections, and staff to answer location questions and respond to requests.

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Investigate existing approaches and recommend adoption or 
Reviewed documentation for InMagic to determine installation needs. 

develop a custom library interface and bibliography that allows 
Installed InMagic software on Library computer and imported data from the


tracking of information requests, key word searches, and easy 
existing bibliography database.  Worked on some customizations and 


comparison to the StreamNet Library holdings.
worked on importing the progress and information report lists.

Objective  3

Library / Reference Services
Task
4.
Library Services

Manage the StreamNet Library and provide library services to the StreamNet user community and the general public.
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Respond to requests for ODFW documents and other source 
Provided 324 hardcopy documents and 5 electronic documents to 87 

materials.
individual users during the quarter.

Objective  3

Library / Reference Services
Task
5.
Inter-library Coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other collections that will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000
  CRITFC  1-5  Routine coordination with customers and other libraries
Ongoing


Objective
3
Task
5.
Fiscal Year 2000 Fourth Quarter 
Page 32 of 43
Objective  4

Services to Fish and Wildlife Program Activities

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife Program projects
Objective  4

Services to Fish and Wildlife 
Task
1.
Project Tracking

Assist CBFWA, BPA, and the Council in providing Internet access to the Annual Implementation Work Plan (AIWP) database and other essential information from AIWP-related reports

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

Region
1
Update AIWP information in a timely manner as it is received,
Responsibility for the AIWP information was transferred to CBFWA last 

and make it available and queriable via the StreamNet web site.
quarter.

Objective  4

Services to Fish and Wildlife 
Task
2
Monitoring and Evaluation

Assist in the development of products that contribute to the monitoring and evaluating (M&E) of Fish and Wildlife Program effectiveness.  Specific area of involvement will include:

Objective  4

Services to Fish and Wildlife 
Task   2   Monitoring and Evaluation
Task
2.a
M&E Participation

 Participate in Program-related monitoring and evaluation work groups
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

CRITFC
1
Assist CBFWA to develop an R/M/E plan consistent with the 
Work was completed in the third quarter.

regional Framework (cost sharing)


IDFG
1
Participate in discussions concerning data needs to support 
Discussed data management needs at StreamNet Steering Committee 

processes adopted by the amended Fish & Wildlife Program
meetings.


for Monitoring and Evaluation. 


ODFW
1
Participate in discussions concerning data needs to support 
Reviewed the Fish & Wildlife Program Amendment document,  focusing on 

processes adopted by the amended Fish & Wildlife Program
data management needs and issues and submitted comments to 


for Monitoring and Evaluation.
ODFW-Portland and Regional StreamNet staff.


WDFW
1
Participate in discussions concerning data needs to support 
No specific discussions were held.

processes adopted by the amended Fish & Wildlife Program 


for Monitoring and Evaluation.


Objective
4
Task
2.a
Fiscal Year 2000 Fourth Quarter 
Page 33 of 43

Objective  4

Services to Fish and Wildlife 
Task   2   Monitoring and Evaluation
Task
2.b
Evaluation

Periodically re-evaluate the StreamNet data plan to ensure consistency with M&E needs
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

CRITFC
1
Keep Steering Committee apprised of regional R/M/E plans and 
Discussed R/M/E issues with NMFS and NWPPC staffs and contractors. 

needs
Kept SC apprised of these discussions via reports at SC meetings and via 


e-mail.

Objective  4

Services to Fish and Wildlife 
Task   2   Monitoring and Evaluation
Task
2.c
M & E Reporting

Prepare reports and data products that illustrate key M&E topics
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

CRITFC
1
Assist Steering Committee to identify useful M&E products which 
Identification of specific M&E products depends on discussions with other 

StreamNet can produce at regular intervals
entities which are expected to occur next fiscal year. See also comments 


on previous sub-components of this task.

Objective  4

Services to Fish and Wildlife 
Task
3.
Watershed Projects

Provide data and data services to Fish and Wildlife Program-sponsored watershed planning and assessment projects
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

Region
1
Receive information on watershed restoration and improvement 
Explored the existence of restoration project data tracking by BPA by 

projects and make available via the StreamNet website
meeting with BPA staff.  Found out that project tracking in BPA has not 


been supported, but that some staff have interest.  There is potential for 


some collaborative effort to develop project tracking, but more discussions


are needed to determine roles, capabilities, etc.  Would like to find means 


of linking current StreamNet efforts on restoration project data (projects 


not BPA funded) with data from BPA funded projects.  Continued 


coordination with other state and federal restoration efforts through 


meetings with interested parties and the Forest Service Regional 




Ecosystem Office (see Objective 5, Task 3, Work Component 1).

Objective
4
Task
3.
Fiscal Year 2000 Fourth Quarter 
Page 34 of 43
 Objective  4
Services to Fish and Wildlife 
Task
4.
Stock Assessment Projects

Provide technical assistance to the Upper Columbia Basin and Upper Snake River Basin resident fish stock assessment projects, including a) identification of regionally consistent data exchange standards and b) Internet access to project data and other information. Specific actions will be defined in consultation with stock assessment project managers
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000
Objective  4

Services to Fish and Wildlife 
Task
5.
Service to Other Fish and Wildlife Program Projects and Activities

In consultation with CBFWA, the Council, and BPA StreamNet will provide technical assistance and data services to select Program projects
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
No work planned this year.
Contributed hatchery release information to ODFW staff preparing the 

Hood and Fifteenmile Creek subbasin summaries.


Participated in a meeting with NWPPC staff to discuss subbasin planning 


data management needs and how StreamNet could help.


Region
1
Work with Fish and Wildlife Program projects throughout the
1.  Developed a matrix of data available in the StreamNet database by 

basin to assist with providing information needed by the projects
subbasin as a means of informing subbasin planners and projects 


and acquiring and distributing information generated by the
throughout the basin of the kinds of information available to them just by 


projects.







accessing the StreamNet web site.  Provided this to planners and to 


Power Planning Council staff.  Met with NWPPC staff to discuss data 


needs for subbasin summaries/assessments and plan approach for 


developing the needed information.  Met with NMFS NW Science Center 


staff and NWPPC data contractor to discuss TRT recovery plan data 


needs and VSP data needs.


2.  Created a preliminary list of subbasins and their geographic extents in 


order to create a coverage in the GIS.  A coverage is necessary for 


determining which water bodies are in which subbasin, which is a 


necessary step in providing data to subbasin planners.


Objective
4
Task
5.
Fiscal Year 2000 Fourth Quarter 
Page 35 of 43
Objective  4

Services to Fish and Wildlife 
Task
6.
Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas dataset, b) archive the official version as a historic record, and c) in 

consultation with the Council, respond to requests for information concerning Protected Areas

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

Region
1
Maintain the existing Protected Areas database.
This is ongoing.

Objective  4

Services to Fish and Wildlife 
Task
7
Basin Data Needs

StreamNet will provide information and assistance to regional reviews of data management projects and data management needs conducted by the 

NWPPC, ISRP, ISAB and other regional entities

Objective  4

Services to Fish and Wildlife 
Task   7   Basin Data Needs
Task
7.a
Data Management Needs

Provide an analysis of regional data management needs, challenges and capabilities to the Power Planning Council, CBFWA, and other regional data 

review processes

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

CRITFC
1
Review and contribute to the data management 'white paper'.
Staff  helped to frame the issues, contributed suggestions for content, and

reviewed the final data management white paper.


WDFW
1
Prepare an outline for a 'white paper' report describing the
Work completed during second quarter.

current state of regional data management and future options.


WDFW
2
Review and contribute to the data management 'white paper'.
Work completed during second quarter.

Objective
4
Task
7.a
Fiscal Year 2000 Fourth Quarter 
Page 36 of 43
Objective  4

Services to Fish and Wildlife 
Task   7   Basin Data Needs
Task
7.b
Data Needs Workshop

Promote organization of a regional 'data needs workshop' to establish regional data / information needs and priorities and to develop recommendations for roles and responsibilities for acquiring and providing the needed data / information
  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

CRITFC
1
Assist in planning and conducting the workshop.
Workshop was delayed into the next fiscal year.

Region
1
Organize and hold a meeting of the regional data management 
Met with the PSMFC data projects to discuss coordination.

projects to discuss current activities and capabilities, investigate 


potential duplication of effort, and develop a plan for coordinated 


activities to meet regional data and information needs.


Region
2
Call for, and if successful, participate in, a regional workshop 
Workloads precluded initiating a regional data needs workshop.  We 

designed to bring together regional, state and tribal agencies to 
decided to initiate a strategy of inviting broad participation to StreamNet 


establish data and information needs, determine data and 
Steering Committee meetings so that agency data needs can be 


information priorities, and determine a coordinated regional 
discussed and included in future work statements.


approach to developing and providing the priority data and 


information.


WDFW
1
Assist Regional staff as needed.
No assistance was requested.

Objective
5
Project Management / Coordination

Provide effective leadership that ensures the production of high quality products targeted at critical applications and the development of these products in a timely, cost-effective manner.

Objective  5

Project Management / Coordination
Task
1.
Manage Project Activities

Administer all aspects of the project at the regional and sub-contractor levels, including oversight of budget, personnel, work statement preparation and 

implementation, coordination among participating agencies, active participation in steering committee work, and project reporting

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Attend StreamNet steering committee or specific technical data 
Staff attended the July Steering Committee meeting in Helena, MT.


meetings as needed to address data issues.

Objective
5
Task
1.
Fiscal Year 2000 Fourth Quarter 
Page 37 of 43

ODFW
2
Summarize/compile individual staff quarterly reports into one 
Compiled and submitted the 2000-3 quarterly report.   Reviewed and 

document, including fiscal year highlights, and plans for the next 
commented on the new quarterly report format (the quarterly database).   


quarter.
Reviewed and responded to comments by PSMFC staff regarding 


mapping the mitigation/restoration data.  Reviewed and commented on the 


FY-2001 StreamNet Statement of Work.


ODFW
3
Coordination activities: Oversee and monitor personnel, budget, 
1.  Ongoing. Continued efforts to recruit a new database manager / 

and other project activities.
developer.


2.  Successfully recruited for and hired a new data analyst whose primary 


responsibility will be to update and maintain our abundance trends.


3.  Met with Regional and WDFW staff to discuss the role of ODFW - 


Columbia River Management staff in StreamNet. 


4.  Conducted mid-year work plan reviews with two staff members.


5.  Drafted a data status summary report and submitted it to Regional 


StreamNet staff.


ODFW
4
Prepare for and attend StreamNet steering committee meetings 
Staff attended the July Steering Committee meeting in Helena, MT.

and specific technical data meetings as needed to address data 


issues.


ODFW
5
Participate / attend appropriate conferences and submit 
Duplicate task - see activity 5.4b.1

conference agendas, proceedings, and presentations to PSMFC 


upon request


ODFW
6
Produce and provide a Statement of Work and budget proposal 
Drafted the FY-2001 Oregon StreamNet Statement of Work, staff 

for ODFW
allocation table, and an objective specific budget and submitted it to


PSMFC.


ODFW
7
Contribute to the Oregon portion of Quarterly and Annual reports 
All staff submitted required reports for this period.

by providing period highlights, plans for the next quarter, and a 


data request/response log.


ODFW
8
Develop a mid-year status report for work items contained in 
Completed in the 3rd quarter.



individual work plans.

ODFW
9
Summarize/compile individual CRM staff quarterly reports into
Completed

one document, including fiscal year highlights, and plans for the 


next quarter, and deliver to Cedric


Objective
5
Task
1.
Fiscal Year 2000 Fourth Quarter 
Page 38 of 43


Region
1
Provide oversight for the StreamNet Program
Routine project administration and oversight continued.  Worked with the 

sub-project leaders on the work plans for FY2001.


Region
2
Supervise and train StreamNet regional staff
1.  The Program Manager attended training in the ACCESS database.

2.  The Regional Fisheries Biologist explored programming languages, in 


order to determine which would be best to learn in order to assist the 


project.  It was decided Visual Basic would be most useful, and he began 


a semester-long class.   He also explored ArcView in order to better use 


that program.


Region
3
Develop program budgets and manage / monitor expenditures
The budget requested for FY2001 was reduced to the point that serious 

reductions were required from regional and cooperator projects.  This 


was due to the cumulative effects of no cost of living increase for FY2001


and four years of cost of living increases that fell below actual salary 


increases.  All budgets were adjusted to reflect the reductions, and work 


was begun on requesting reinstatement of funding to continue the project 


at full strength.


Region
5
Coordinate with data collecting agencies and organizations to 
Met with ODFW and WDFW staff regarding availability of run 

determine data availability and encourage data and information 
reconstruction data.


being made public.


Region
6
Coordinate with regional management agencies / entities and
1)  Requests to various staff in many agencies to determine data 

data using entities to determine information and data service
needs were not fully successful at identifying ongoing and future needs.  


needs to assure rapid response to reasonable requests for data
Meetings were held specifically with NMFS staff at the NW Science Center


and information.
on data needed to support various modeling efforts.  


2)  We developed a plan to invite agency representatives to participate in 


StreamNet Steering Committee meetings as a means of increasing input 


Region
7
Produce quarterly reports within 1 month after the end of each 
A new database was developed to capture quarterly accomplishments 

quarter
from all project participants.  The intent is to have the process automated 


so that report production is quick and efficient.  The system was not 


functional enough to complete the third quarter report on time, however.
on agency data needs.  This will be carried out beginning in FY2001.


Objective
5
Task
1.
Fiscal Year 2000 Fourth Quarter 
Page 39 of 43

Region
9
Manage and serve the StreamNet Steering Committee through:  
1.  Developed the agenda and chaired the Summer Steering Committee 

Organizing and conducting committee meetings at least quarterly; 
meeting on July 11-12 in Helena, MT.  All PSMFC staff attended this 


Calling additional meetings as needed to address timely issues; 
meeting.


and, Actively consulting with Steering Committee on program 
2.  At the request of the Steering Committee, regional staff began creating 


activities
a document that describes the roles and responsibilities of each of the 


regional staff.  This request was made by the Steering Committee in order 


to minimize confusion regarding who to contact for various types of 


regional coordination.


Region
11
Prepare a project proposal and Statement of Work for FY 2001
The FY2001 Work Statement was developed in an ACCESS database 

format.  The accompanying budget was developed at the Council 


approved level, and included references to the full amount needed to 


support the entire project.  Uncertainty over the actual budget amount for 


the fiscal year and the best way to depict the budget needs delayed final


submission and approval of the  work statement and budget until the first


quarter of FY2001.

Objective  5

Project Management / Coordination
Task
2.
Participate in Fish and Wildlife Program Development Activities

Organize, facilitate, and/or participate in appropriate coordination meetings with BPA, CBFWA, the Council, ESA officials, ISAB/ISRP, and/or staff and 

management of participating organizations aimed at identifying ways that StreamNet might more effectively contribute to the Fish and Wildlife Program 


(FWP). Participate in advisory groups, task forces, and other groups whose purpose is enhancing the effectiveness of the Fish and Wildlife Program and 


its data development activities.

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Participate in Fish and Wildlife Program advisory groups and 
Participated in a conference call with NMFS-Seattle staff regarding data 

applicable regional policy, planning, and management forums
needs for their upcoming Viable Salmon Population analytical procedure.


and provide a written summary of activities in quarterly progress 


reports.


Region
1
Participate in appropriate coordination meetings with BPA, 
Participated in meetings with NMFS NW Science Center staff regarding 

CBFWA, the Council, ESA officials, ISAB / ISRP, and/or staff and 
data needed for modeling and recovery planning efforts.


management of participating organizations aimed at identifying 


ways that StreamNet might most effectively contribute data / 




information and support to the FWP.

Objective
5
Task
2.
Fiscal Year 2000 Fourth Quarter 
Page 40 of 43
Objective  5

Project Management / Coordination
Task
3.
Coordinate with Other Related Activities

As needed, produce public information materials including updated versions of the project brochure, computer demonstration materials, and/or other 

appropriate materials

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

ODFW
1
Establish / maintain working relationships with major data 
1.  Participated in restoration data integration meetings with the Regional 

collection projects within and outside ODFW to promote efficient 
Ecosystem Office, BLM, USFS, and OWEB. 


and beneficial data sharing.
2.  Reviewed and commented on a draft white paper outlining restoration 


data integration efforts between REO, StreamNet, OWEB, and federal 


agencies.


Region
1
Coordinate the efforts of the StreamNet project with other data 
1.  The Regional Fisheries Biologist participated in an interagency group 

compilation projects occurring in the region.  Address issues of 
which is attempting to coordinate and consolidate habitat restoration 


data gaps, duplication of effort, data set integration, 
projects data for the region. Three meetings were attended, and a white 


georeferencing standardization, scientific rigor, management 
paper was initiated which will lay out a strategy for integrating the several


needs, etc.
independent databases now in existence.


2.  The Regional Fisheries Biologist participated in a workshop on 


volunteers using macroinvertebrates for monitoring, presented by the 


Xerces Society.  At this meeting, he gained an understanding of what data


are collected, and how they may be integrated into StreamNet in the 


future.  At the request of the Xerces staff, he also provided feedback to 


the Xerces Society staff on ways they could improve their techniques, 


and how they could more easily move their data into StreamNet format.


Objective
5
Task
3.
Fiscal Year 2000 Fourth Quarter 
Page 41 of 43
Objective  5

Project Management / Coordination
Task
4
Prepare Public Information Materials.

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities to identify means for collaborative data collection, storage, and dissemination. Collaborative data activities will target tribal fishery programs within the Columbia Basin, federal land managers’ fishery programs, state fish and wildlife agencies, and, with respect to water use and stream development, state water resource Collaboration with coast-wide and private data collection/compilation efforts will be pursued when this supports overall project goals. Areas of particular management agencies. emphasis are 1) participation in Fish and Wildlife Program monitoring and evaluation activities, and 2) exploring opportunities for integration of StreamNet data exchange formats into Fish and Wildlife Program contract terms and conditions.

Objective  5

Project Management / Coordination
Task   4   Prepare Public Information Materials.
Task
4.a
Prepare Public Information Materials

As needed, produce public information materials including updated versions of the project brochure, computer demonstration materials, and/or other 

appropriate materials

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

CRITFC
1
Produce and update a Library brochure and Access guide listing 
Brochure was updated previously.

services, hours and cost recovery fees.


MFWP
1
Montana will participate in review and recommendations.
Reviewed brochure.

ODFW
1
Write informational article for the ODFW Monitor or Inside Tracks 
Due to the departure of project staff, and the anticipated delays in filling 

on the Fish Presence Survey database development and its utility.
these positions, it is anticipated that no further efforts will be made on this 


task.


ODFW
2
Write informational article for the ODFW Monitor or Inside Tracks 
No efforts were made this quarter. The barrier data is still being compiled 

on the Barriers database development and utility
and validated.  It would be premature to publish an information article until 


the bulk of our data has been completely reviewed.


ODFW
4
Write informational article for the ODFW Monitor or Inside Tracks 
Wrote draft Inside Tracks article describing the Oregon salmonid 

on distribution data development efforts.
distribution data.  Refrained from submitting article due to recent 


significant developments in supplementary ODFW databases containing 


fish presence information and the need to reconcile the current distribution 


data with these data.


Region
1
Update the existing StreamNet brochure
Began review of the existing StreamNet brochure.

Region
3
Prepare reports, documents or presentations as needed to 
Wrote a report on StreamNet project accomplishments for the Pacific 



describe project actions and accomplishments
States Marine Fisheries Commission annual report.

Objective
5
Task
4.a
Fiscal Year 2000 Fourth Quarter 
Page 42 of 43

Objective  5

Project Management / Coordination
Task   4   Prepare Public Information Materials.
Task
4.b
Participate in informational meetings/conferences

Participate in appropriate state, regional, and national educational and professional conferences, including, where applicable, giving presentations, 

preparing poster session materials, and contributing to conference proceedings.

  Project
Work Element
Accomplishments, Fourth Quarter, FY2000

CRITFC
1
See task 3.5
See report for task 3.5.

IDFG
1
Participate in state, regional, or national educational or 
Attended NW ESRI Users Group Conference in Skamania, WA.

professional conferences. 


IDFG
2
Serve as chairman and organizer for the 2001 ArcInfo User's 
Gathered information for the 2001 NW GIS Users Conference.

Group Conference scheduled for October 2001.


ODFW
1
Participate in appropriate meetings & conferences as 
1.  Staff attended the Organization of Fish and Wildlife Information 

opportunities arise to highlight StreamNet programs & data
Managers (OFWIM) Conference in Silver Creek, Colorado in August.


2.  Attended the Or. Plan monitoring team meeting and briefed the team 


on upcoming efforts.


3.  Attended the annual Fish Biologist meeting and presented a summary 


of upcoming efforts.


4.  One staff person attended a Library Procedures class at PCC. This 


class will continue through the fall.


5.  One staff person attended MS Access Level I & II training.


Region
1
Participate in appropriate meetings to explain the StreamNet 
The Program Manager and Database Manager participated in the annual 

project, solicit new data and information, or to present relevant 
meeting of the Organization of Fish and Wildlife Information Managers.  


data from the SN database
The agenda theme was web distributed information systems and 


approaches.  The StreamNet site was cited as an example of a well 


designed web page.  Among the technical information presented was the 


value of using web based scripting in serving interactive GIS data.


Objective
5
Task
4.b
Fiscal Year 2000 Fourth Quarter 
Page 43 of 43
� EMBED Word.Document.8 \s ���








[image: image2.wmf]_1048322700.doc
[image: image1.png]






