StreamNet

BPA Project Number 198810804
Fiscal Year 2001

Second Quarter Progress Report
Bruce Schmidt

Pacific States Marine Fisheries Commission
Cooperators:

Phil Roger, Columbia River Intertribal Fish Commission

Bart Butterfield, Idaho Department of Fish and Game

Janet Hess-Herbert, Montana Game, Fish and Parks

Cedric Cooney, Oregon Department of Fish and Wildlife

Steve Pastor, U.S. Fish and Wildlife Service

Dick O’Connor, Washington Department of Fish and Wildlife


[image: image1.png]




Table of Contents

Introduction
2

Objective 1.  Data Development
3

     Task 1.  Anadromous Fish  
3

     Task 2.  Resident Fish and Other Aquatic Species
10

     Task 3.  Habitat
15

     Task 4.  Facilities
16

     Task 5.  Habitat Improvement/Restoration Projects
19

     Task 6.  Subbasin Planning
20

Objective 2.  Database Management and Delivery
22

Objective 3.  Library / Reference Services
36

Objective 4.  Services to the Fish and Wildlife Program Activities
39

Objective 5.  Program Management / Coordination
44

Introduction
This report presents accomplishments of the StreamNet project for the Second Quarter of Fiscal Year 2001 (January through March).  The report is organized to clearly link accomplishments by the project participants to the tasks and responsibilities detailed in the FY 2001 Statement of Work.  It is organized by objective and task for all project participants rather than by individual participant.  Since not all tasks are addressed each quarter, and project participants often work on different tasks at different times, some tasks do not show activity in the Second Quarter.  Those tasks with no activity are not listed in this report.

Project participants contributing to the StreamNet project were Columbia River Intertribal Fisheries Commission (CRITFC), US Fish and Wildlife Service (FWS), Idaho Department of Fish and Game (IDFG), Montana Fish, Wildlife and Parks (MFWP), Oregon Department of Fish and Wildlife (ODFW), Pacific States Marine Fisheries Commission (Region), and Washington Department of Fish and Wildlife (WDFW).  The Shoshone-Bannock Tribes (SBT) have been a participant for a number of years, but they are currently fazing out their participation in the project due to other workloads, and were not active this quarter.


Introduction



Fiscal Year 2001 Second Quarter 
Page 2 of 50
Objective 1
 Data Development

Increase the knowledge base concerning the region’s fish and wildlife resources through the acquisition of new information that responds to emerging needs as well as the updating and enhancement of production and survival trends and other existing information.

Objective
1
Data Development
Task
1
Anadromous Fish

Acquire data sets related to salmon, steelhead and, where data are readily available, other anadromous fish populations from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:
Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.a
Distribution, Life History (use type), and Barriers

Document the occurrence, distribution and habitat use of anadromous species, related barriers to migration, and life history characteristics

Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
Identify and update missing data in anadromous barrier data.
1)  Conducted initial compilation of trapping and tagging sites for Idaho 

Supplementation Studies, Bureau of Reclamation, Fish and Wildlife 


Service, state and federal hatcheries into a GIS layer for barriers. Will 


migrate to data exchange format later.


2)  Updated our diversions database to the current barrier data exchange 


format. Made corrections to some of the locations


ODFW
1
Update, maintain, correct and exchange barrier information.
1)  Incorporated updates to the Barrier table for the NE Oregon basins.

2)  Enhanced the forms and subforms in the barrier database.


3)  Drafted the data entry instruction manual for the barrier database.


4)  Contacted numerous ODFW field staff to obtain reference information 


for barriers contained in the database. This reference information is 


needed in order to submit these barriers to StreamNet.


ODFW
2
Update, maintain, correct and exchange anadromous fish 
1)  Reconciled differences between Aquatic Inventory Project coho 

distribution information (DistUse and DistPresence tables).
distribution and the existing NRIMP Coho distribution dataset for the lower 


Columbia.  


2)  Submitted entire set of ODFW DistPres data and updated DistUse data 


to StreamNet.


3)  Modified spring chinook distribution in the upper Willamette in response 


to feedback from ODFW field staff.


Objective
1
SubTask  1.a
Fiscal Year 2001 Second Quarter 
Page 3 of 50

ODFW
3
Modify / refine the automated approach to populating the 
1)  Incorporated updates to the FishBarrier table for the NE Oregon basins.

FishBarrier table (as needed) and rectify any new anadromous 
2)  Evaluated assumptions made as part of the automated FishBarrier


distribution information with the barriers database.
 attributing process.


ODFW
4
Design and develop a database to capture carcass placement 
Duplicate task - information provided under Obj. 1, Task 5.b - Work 

data.
Component 2.


ODFW
5
Update (and modify if needed) the Fish Presence Survey 
Continued to enter data into the Fish Presence Survey Database which is 

database which helps populate the DistPresence table.
designed to capture Oregon’s upper fish distribution and culvert information


collected by ODF/ODFW surveyors.  To date, 2,485 records have been 


entered.


ODFW
6
Update (and modify if needed) the Incidental Fish Observation 
Continued to enter forms as they came in - currently, 29 of the 101 records

database, which captures incidental species observations not 
in the database are for Col. Basin streams. New information will not be 


routinely reported in agency documents, which helps populate
processed and submitted to StreamNet due to budget cuts.


the DistPresence table.


ODFW
7
Identify appropriate documents/references for anadromous fish 
Identified (and created references for) two dynamic databases that 

distribution data in order to populate the DistPresence table.
represent a significant new source of DistPres data.


Ongoing management and maintenance efforts.


ODFW
8
Update, maintain, correct and exchange photographic
Added 2 new barrier photos to the database.

information (MapCat and related tables).


ODFW
9
Populate the genetic origin and production origin fields in 
This task was dropped due to budget cuts. Standards and definitions need 

StreamNet distribution exchange format for all anadromous
to be developed in order for this work to occur.


fish distribution data in the Columbia basin.


Region
1
Compile distribution updates (tabular events) as they arrive.  
1)  Compiled, QA'd, and integrated complete ODFW anadromous update of 

Create anadromous fish distribution GIS coverages from these 
DistUse data to the StreamNet database and online system.  Created new 


event tables, and post the shape files to the StreamNet website 
GIS files from this information and posted these, along with updated 


as downloadable GIS coverages.
documentation, to the StreamNet site for download.  Compiled and updated


revised total anadromous distribution GIS layer with this new information.


2)  Compiled, QA'd, and integrated  ODFW anadromous distpresence data 


set to the StreamNet database.


3)  Revised database application to aggregate anadromous distribution, 


fixing errors and adding the capability to summarize this information by 


watershed (4th code HUC)


Objective
1
SubTask  1.a
Fiscal Year 2001 Second Quarter 
Page 4 of 50

Region
3
Assist StreamNet partners with acquisition, development, 
Regional Staff helped WDFW staff read Quattro files that they were unable

formatting and submission of data.
to open, and discussed coding for fish distribution with WDFW personnel.


WDFW
1
Review barriers in the anadromous fish distribution layer, based 
Using Arc Explorer and the SDE coverages, Lensegrav prepared a stream 

on SSHIAP information and indicators in the Stream Catalog. 
barrier map for WDFW's Pat Hanratty.  *O'Connor coordinated salmon and 


Update and exchange the data with the regional database.
steelhead distribution updates for the Yakima Basin with Washington 


Conservation Commission, Yakama Nation, WDFW, and PSMFC-StreamNet


staff, as part of the data compilation required for the NPPC's Rolling Review


of the Columbia Plateau Province. Mapped updates will be integrated into 


WDFW-StreamNet coverages in late Q3 or early Q4, once WCC delivers the


maps.

Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.b
Adult Abundance

Escapement, redd counts, trap counts, dam counts, hatchery returns

Project
Work Element
Accomplishments, Second Quarter, FY2001

FWS
1
Compile FWS hatchery return data for FWS hatcheries
Corrected problems with submitted hatchery return data

IDFG
1
Compile 2000-field season redd count data and 2000 field
1)  Started process to tie chinook and steelhead redd count transects to 

season hatchery return data and submit to the regional
100k LLID routes. Converted map of redd count transects to PowerPoint 


database.
for review by Fisheries Bureau. Made corrections. 


2)  Created an ArcView project to facilitate continued transect definitions.


3)  Implemented data entry and edit screens. Used these to start reviewing 


and editing existing redd count data for future migration to data exchange 


format.


ODFW
1
Update existing abundance and index trends (escapement,
1)  Added 42 new trends (8 Adult Return - Peak/Other Spawning counts, 

redd counts, trap counts, peak/other spawning counts, etc.) for 
10 Adult Return - Dam/Weir counts, and 24 Adult Return - Redd counts.


anadromous species through 1999 and modify as needed to 
2)  2064 records were identified with some magnitude of coding errors by 


adhere to the 2000.2 Data Exchange Format.  Four data 
either ODFW staff or StreamNet staff. The data was reverified using 


submissions are planned.
reference material and corrections were made.  These corrected trends 


will be submitted to the StreamNet database along with the added and 


updated trends in April.


ODFW
2
Compile data on returns to ODFW hatchery facilities (updated
No effort was made this quarter - no database manager was on staff.

for 1997, 1998,  and part of 1999 returns).


Objective
1
SubTask  1.b
Fiscal Year 2001 Second Quarter 
Page 5 of 50

WDFW
1
Update and exchange hatchery returns through 1999 in 
1)  Didn't add this back from budget cut until Q3 but in January, Sikora and 

StreamNet data exchange format.
Woodard confirmed for Kinney that 6 trends were incorrectly coded to an 


obsolete RefID and needed to be changed to RefID 10164. The returns data


was not re-exchanged for this correction and Kinney, Sikora and 


Woodard just corrected their own databases accordingly.


2)  Sikora organized her hatchery returns files and gave Woodard all 


pertinent information since he is the lead on returns data. She also helped 


Woodard get a copy of WDFW's Hatchery Division 1999 Hatchery 


Escapement (returns) report. Woodard also collected and rolled up the 


Hatchery returns data for return years 1999 and 2000 from WDFW's Form 


5 database. This data is in the exchange format but it needs to be proofed 


and a discrepancy with the Final Hatchery Division report needs to be 


resolved. Unfortunately, error tracking is an ongoing process. Another look


at the 1996 data is needed, as this was the startup year of the Form 5 


database and errors prevail.


WDFW
2
Update and exchange natural spawner data (returns and/or
1)  In January, Sikora sent Emily Greenberg (StreamNet data user) the 

redd counts) through 1999 for available species (CR, PS)
correct Lewis River basin steelhead data. She also clarified how the data 


will appear in the next data exchange to accommodate new DEF format 


potential for previously exchanged data that used two records to report a 


count\mile TypeID and Redd Count TypeID for the same area.


2)  Woodard collected Columbia River escapement estimates for the 2000 


return and put the data into report form for entry into the escapement 


database. Final numbers are not complete yet for the Lewis River. 


Changes are due in June. He also collected Puget Sound escapement 


estimates for the 2000 return year for chum and pinks and entered the data


into the escapement database. 


3)  In January, Sikora re-directed Jim Cummins' Yakima basin escapement 


data from Lensegrav to Woodard to compare it to his data and include as


warranted. Woodard was retasked for this job since the files could be linked


to several of his datasets, leaving him more equipped than Lensegrav to


make the comparison. In March, Sikora helped Woodard to find more


potential redd count data, revealing escapement data from WDFW's Bruce


Sanford. O'Connor also passed the data to WDFW's Ann Blakely and Bill


Gill to research the compatibility with SASSI data. Blakely and Gill saw


enough differences to inspire their intent to work on coordination.


4)  Smith returned to StreamNet work Jan. 16th after time on another project.


She marked for deletion 60K PSMFC trends WDFW already had covered


by 100K. In February, Smith compared the Puget Sound pink and Chinook


data with her B11X escapement database and the PSMFC 60K trends.


Objective
1
SubTask  1.b
Fiscal Year 2001 Second Quarter 
Page 6 of 50

5)  Smith also contacted Travis Nelson and asked for Puget Sound chum 


and pink escapement data. Sikora gave Woodard and Smith a file with 


tentative TrendStatIDs, summarizing the data gaps for the current salmon 


data file to aid the HistStatID assignments. Late February and March, Smith 


researched which codes should be assigned. Her review of the gaps 


revealed that some data records were missing and not just gaps in 


WDFW's raw data collection. Smith contacted Travis Nelson about missing 


Puget Sound chum data. This data was located and completed.


6)  Late in March, Smith organized data to be entered into the new 


escapement database.. She built relationships between the separate trend 


and natural spawner tables, created and linked look-up tables, and made 


the new data entry form. Once the database was up and running, Smith 


started entering back logged escapement data and all known TrendStatIDs 


and HistStatIDs. She compared the Puget Sound Chinook data from Bruce 


Sanford with the SASSI stock information for similarities.


7)  Lensegrav started collecting life cycle information for the anadromous 


species and drafted visual aids to display the cycles. Aids will be revised if


warranted to become the best quick reference for these species' cycles


because it can give clues about data accuracy and predict data availability.

Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.c
Juvenile Data

Sample records, abundance indices (as available)

Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
Finalize the incorporation of the IDFG General Parr Monitoring 
Began development of Juvenile Trap Operations interface for Idaho 

(juvenile) data into StreamNet.
Supplementation Studies.


ODFW
1
Prepare and submit recommended modifications of the draft 
This task was dropped due to budget cuts.

Juvenile abundance portion of the DEF.


ODFW
2
Update Oregon's 10 existing juvenile abundance records to 
No work has been accomplished in this area. ODFW staff is awaiting a 

approved DEF standards.
format change to the juvenile abundance record requirements and 


interface form design.


Objective
1
SubTask  1.c
Fiscal Year 2001 Second Quarter 
Page 7 of 50
Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.d
Harvest

In-river, terminal, and other harvest, as available

Project
Work Element
Accomplishments, Second Quarter, FY2001

WDFW
1
Update and exchange salmon harvest data through 1999, 
Didn't add this back from budget cut until Q3 and no work to report for this 

beginning with Columbia River commercial, sport and treaty 
period.


harvest.


WDFW
2
Update and exchange steelhead harvest through 1998.
N/A - didn't add this back after budget cut.
Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.e
Hatchery Production

Releases and disposition

Project
Work Element
Accomplishments, Second Quarter, FY2001

FWS
1
Compile FWS hatchery release data, w/ added CWT information
Continued compiling hatchery release data

FWS
3
Submit 2000 data to PSMFC via USFWS WWFRO
Submitted hatchery release data for CY 2000

IDFG
1
Compile 2000-field season hatchery returns data.
Began migration for moving legacy hatchery return data into the new data 

exchange format.


ODFW
1
Develop the ability to remotely access the Portland mainframe 
No effort was made this quarter - no database manager on staff.

hatchery database and download hatchery return data consistent


with the StreamNet contract.


ODFW
2
Compile egg-take data into StreamNet format and submit to 
No effort was made this quarter - no database manager on staff.



PSMFC.

Region
3
Acquire hatchery production data through 2000 from the RMIS 
The RMIS Hatchery Production database was acquired in March, 2001.  

database and incorporate into the StreamNet on-line database.
Existing routines built to convert the Pacific Salmon Commission’s Data 


Exchange Format 3.2 into StreamNet’s DEF 99.1 do not readily produce 


data in the current DEF 2001.1 because they used PSC Code to River 


Reach Code conversion tables.  A PSC Code to LLID conversion table 


needs to be created.  WDFW has stated that this cross-reference table is 


under construction for Washington State.  Many combined-location 


“SuperCodes” are required by the rolled-up Coded-Wire Tag releases in the


RMIS system.   The required PSC Code to StreamNet LLID conversion 


process will be much more accurate and the resulting information will be 


much easier to map if “unrolled” release data could be provided to 


StreamNet either in PSC Data Exchange Format or in StreamNet DEF.


Objective
1
TsubTask  1.d
Fiscal Year 2001 Second Quarter 
Page 8 of 50
Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.f
Natural Production

Survival, production factors, spawner recruit

Project
Work Element
Accomplishments, Second Quarter, FY2001

ODFW
2
Compile spawner-recruit data (updated for spring chinook 
This task was dropped due to budget cuts.

surveys in 1998 and 1999, and available time series for fall 


chinook and coho returns)

Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.g
Age

Age/sex composition for returning adults

Project
Work Element
Accomplishments, Second Quarter, FY2001

FWS
1
Update age and sex data through 2000
Corrected problems with submitted Age data

IDFG
1
Compile 2000-field season age and sex composition data.
Researched legacy age data and began revising data structures for 

migration to the  new data exchange format.


ODFW
1
Compile age frequency data (updated for natural spring chinook
This task was dropped due to budget cuts.

in 1998, available time series for natural steelhead in OR portion 


of Columbia basin).


WDFW
1
Provide age/sex data associated with exchanged CRB natural 
Didn't add this back after budget cut until Q3.

returns data.

Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.h
Genetics

Areas where genetics data exists and the sources of these data

Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Develop, with SC input, standardized database format and DEF 
Coordinate with Montana Fish, Wildlife and Parks and University of Idaho on

for existing regional genetic data
genetic data formats used for resident fish. Obtained coastwide salmon 


genetics database from NMFS which was used when developing listings 







under the Endangered Species Act.

CRITFC
2
Provide allozyme and genetic data developed by CRITFC in 
No work this quarter. Waiting to obtain data from other entities and



standard format

integrate information into a proposed DEF.


Objective
1
SubTask  1.h
Fiscal Year 2001 Second Quarter 
Page 9 of 50
Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.I
Populations

Population delineation, as determined by others

Project
Work Element
Accomplishments, Second Quarter, FY2001

ODFW
1
Produce a cross-reference table of ODFW designated Gene 
This task was dropped due to budget cuts.

Conservation Groups (GCG) by subbasin.


WDFW
1
Compile and exchange updated Washington SaSI stock status 
O'Connor summarized SaSI stock status data conversion pilot work and 

data for anadromous fish using newly developed 2000.1 Data 
sent it to Stan Allen. Our fish distribution coverage was found to be 


Exchange Format (see Task 2.3).
out-of-synch with the identified SaSI stock spawning areas, and 


re-alignment work was undertaken. Other funding deadlines for key staff 


postponed completion until Q3 or Q4.

Objective
1
Data Development
Task   1   Anadromous Fish
SubTask
1.j
Historic Range

As available at the watershed-level.  Compilation at the reach level is an option if these data are available

Project
Work Element
Accomplishments, Second Quarter, FY2001

ODFW
1
Work with the Steering Committee to define the term "historic" in 
Received and reviewed the Oregon portion of National Native Freshwater 

the DEF.
Fish distribution database from the Natural Heritage Program
Objective
1
Data Development
Task
2
Resident Fish and Other Aquatic Species

Acquire data sets related to resident fish species, and where specifically identified other aquatic species, from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective
1
Data Development
Task   2   Resident Fish and Other Aquatic Species
SubTask
2.a
Distribution and Life History

Document species occurrence and distribution and life history characteristics

Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
Add additional distribution information from references, collecting 
1)  Fisheries staff continued data entry into reference and collecting permit 

permits and stream and lake surveys for resident fish.
modules.


2)  Conducted initial compilation of trapping and tagging sites for Idaho 


Supplementation Studies, Bureau of Reclamation, Fish and Wildlife 


Service, state and federal hatcheries into a GIS layer for barriers. Will 


migrate to data exchange format later.


3)  Updated our diversions database to the current barrier data exchange 



format. Made corrections to some of the locations


Objective
1
SubTask  2.a
Fiscal Year 2001 Second Quarter 
Page 10 of 50

MFWP
1
Complete conversion of distribution data for all fish species to 
Completed fish survey edit/entry for Federal and Consulting biologists to 

measures using the routed hydrography in western Montana
provide for easier incorporation of their fishery data.


and eastern Montana when it becomes available.  These data 


were collected from biologists in FY2000.


MFWP
2
Provide distribution data in DEF to StreamNet when completed.
Completed 3-01.

MFWP
3
Determine a schedule for updating data in the future and at
Ongoing

what frequency data needs to be collected from field biologists, 


also addressing species of special concern.


MFWP
4
Collect and catalog supporting references to document
Ongoing

distribution and connect distribution to reference.


MFWP
5
Explore the development of a standard field survey form to be 
Completed database structure for Federal and consulting Biologists that will

used by state and federal biologists to record occurrence 
be required as a condition of a state collectors permit.  This might make a 


information.
survey form a mute point for these biologists as we will then get the data in


out required format.


MFWP
6
Continue to work with regional StreamNet staff and SC to 
This effort is still underway.

develop/modify/add to a resident fish data exchange format if 


not completed in FY2000.


ODFW
1
Update, maintain, correct and exchange resident fish distribution 
Updated Bull Trout DistUse data to bring it current with the data that is 

information (DistUse and DistPresence tables).
managed by Mary Hanson.


Region
1
Compile distribution updates (tabular events) as they arrive.  
QA'd Montana resident distribution (DistUse) data submission and returned 

Create and maintain distribution GIS coverages from these
results to MFWP StreamNet component for verification.


event tables and distribute these via the StreamNet web site.


Region
2
Assist StreamNet partners with acquisition, development, 
The Program Manager contacted FWS staff to determine the definitions 

formatting and submission of data.
used for bull trout distribution on a region wide basis.  Currently, bull trout 


are administered by the individual state offices, and so far there has been 


no attempt to standardize distribution information.  This remains an area 


needing further work to achieve any consistent regional data set on bull 



trout occurrence.


Objective
1
SubTask  2.a
Fiscal Year 2001 Second Quarter 
Page 11 of 50

WDFW
1
Update and exchange statewide updated bull char distribution 
1)  O'Connor responded to a Steering Committee e-mail discussion on bull 

data at 100K resolution (see Task 2.3).
trout (char) taxonomic and management distinctions in Washington state 


with clarifying comments and sections from a WDFW report. Discussions 


eventually raised issues of cross-state bull trout distribution data not 


matching up well, and the larger issues of coordinating distribution and use


criteria for critical resident species. WDFW criteria were shared with other


Committee members, and a start at compiling and integrating the criteria 


was initiated.


2)  In late March, USFWS staff ordered WDFW to halt release of 


Washington bull trout distribution and use data, pending resolution of areas 


of dispute in Western Washington. Conversion of data to StreamNet 


formats and compilation of references has begun, but exchange of these 


data with StreamNet will be delayed until at least Q3.

Objective
1
Data Development
Task   2   Resident Fish and Other Aquatic Species
SubTask
2.b
Adult Abundance

Escapement, redd counts, trap counts, dam counts

Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
Coordinate with IDFG personnel to determine the feasibility of 
Fisheries staff continued data entry into reference and collecting permit 

incorporating resident adult abundance.
modules. Captured abundance data where it was available


MFWP
1
Enter 2000-2001 stream fisheries survey data collected for 
Entered/edited some genetic and survey information statewide.

population trends; genetics and escapement, redd counts, trap 


count and other counts during visits to biologists. 


MFWP
2
Collect references for each survey.
Work continued through the quarter.


MFWP
3
Provide data in data exchange format to regional StreamNet staff.
Data not ready to exchange.

ODFW
1
Update existing abundance and indices trends (escapement,
No work has been done to update existing resident trends. We have  37 

redd counts, trap counts, peak/other spawning counts, etc.) for 
trends coded as resident species. Of these, 2 are resident cutthroat, 22 


resident species through 1999 and modify as needed to adhere
are white sturgeon, 1 is bull trout, and 12 are green sturgeon.


to the 2000.2 data exchange standards.  Four data submissions 



planned.


Objective
1
SubTask  2.b
Fiscal Year 2001 Second Quarter 
Page 12 of 50

Region
1
Assist StreamNet partners with acquisition, development, 
1)  Shannon Hurn of ODFW reported several difficulties in making the 

formatting and submission of data.
StreamNet Trend User Interface function with the ODFW database.  


Regional Fisheries Biologist Mike Banach and CRITFC database manager 


Hilary Forrest assisted ODFW with these problems, which were mainly 


related to bad interactions between the interface and a properly set up 


backend database.  Several small programming problems were corrected 


in the Trend User Interface.  Mike Banach and Hilary Forrest traveled to 


Corvallis to meet with Shannon Hurn in person and examine the errors 


occurring.  These three were able to fix all problems, none of which have 


re-occurred.


2)  The Oregon Department of Environmental Quality has developed an 


on-line tool, similar to the StreamNet Event Mapper that can be used to 


determine an LLID and measure from the mouth of points along a stream.  


Regional personnel tested this application for its potential use and to 


determine if we may want to develop a similar application or use this one.  


Evaluations are continuing.


WDFW
1
Explore opportunities to compile, convert, and exchange portions 
N/A - didn't add this back after budget cut.

of the Yakima Basin juvenile and adult abundance data from Ken 


Ham.

Objective
1
Data Development
Task   2   Resident Fish and Other Aquatic Species
SubTask
2.c
Angler Use

Fishing pressure, creel census

Project
Work Element
Accomplishments, Second Quarter, FY2001

MFWP
1
Add FWP 1999 angler survey data collected by MFWP mail
Completed.

survey to MRIS.


ODFW
1
Evaluate available creel data for appropriateness and fit into the 
This task was dropped due to budget cuts.


StreamNet format.
Objective
1
Data Development
Task   2   Resident Fish and Other Aquatic Species
SubTask
2.d
Hatchery Production

Hatchery production (releases and outplants) for salmonids

Project
Work Element
Accomplishments, Second Quarter, FY2001

MFWP
1
Update StreamNet hatchery outplant data in the data exchange 
Data are available for Montana.  No request has been received from the 

format with 1999 data from the FWP Information Services Unit 
region for the information, and the DEF is not complete for resident fish.



Hatchery Database, if changes are made.

Objective
1
SubTask  2.d
Fiscal Year 2001 Second Quarter 
Page 13 of 50

ODFW
1
Acquire trout release data from 1997 through 2000 (by species, 
This task was dropped due to budget cuts.

location, and facility) and compile into SN exchange format.


WDFW
1
Complete conversion and exchange resident fish stocking data 
Sikora corrected the species descriptions in the dataset used to answer 

from 1930-1981, once location coding has been standardized
data requests. Further release work suspended until Lake work 


and verified.
progresses.

Objective
1
Data Development
Task   2   Resident Fish and Other Aquatic Species
Task
2.e
Genetics

Areas where genetics data exists and the sources of these data

Project
Work Element
Accomplishments, Second Quarter, FY2001

MFWP
1
Update genetic spatial and tabular databases that contain the 
Updated databases with results received during the quarter.

results of genetic analysis of populations of Montana's species 


of special concern


MFWP
2
Update fish distribution table when new samples affect fields.
Ongoing.

MFWP
3
Exchange data.
No final DEF yet.

MFWP
4
Work with University of Montana Genetics Lab staff to develop 
Ongoing

a more efficient method of data entry/delivery.

Objective
1
Data Development
Task   2   Resident Fish and Other Aquatic Species
SubTask
2.f
Population

Population delineation, as determined by others

Project
Work Element
Accomplishments, Second Quarter, FY2001
 All




No work was done on this subtask in the second quarter
Objective
1
Data Development
Task   2   Resident Fish and Other Aquatic Species
SubTask
2.g
Historic Range

Develop data on historic range, as available at the watershed-level

Project
Work Element
Accomplishments, Second Quarter, FY2001

MFWP
1
Complete the review of the historic distribution of Montana's 
Ongoing

native species developed by The Nature Conservancy.


MFWP
2
Coordinate the development of a Data Exchange Format for 
Tabled for this quarter; will pick up in 3rd quarter.

StreamNet by working with a Steering Committee subcommittee.


Objective
1
SubTask  2.g
Fiscal Year 2001 Second Quarter 
Page 14 of 50
Objective
1
Data Development
Task   2   Resident Fish and Other Aquatic Species
SubTask
2.h
Status

Population stability index

Project
Work Element
Accomplishments, Second Quarter, FY2001

MFWP
1
Assist regional and state data managers in developing data 
Reviewed hatchery release DEF

exchange format.


MFWP
2
If DEF adopted, submit bull trout, arctic grayling and westslope 
All fish distribution sent this quarter including those mentioned above.

and Yellowstone cutthroat trout data.

Objective
1
Data Development
Task
3
Habitat

Acquire data sets related to fish habitat from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective
1
Data Development
Task   3   Habitat
SubTask
3.a
Stream / Watershed Habitat

Incorporate applicable stream and watershed level habitat and stream survey data, as these become available

Project
Work Element
Accomplishments, Second Quarter, FY2001

MFWP
1
Develop a statewide stream survey form based on information 
Ongoing

provided by Montana state and federal fisheries biologists in 


FY2000.


MFWP
2
Work with regional StreamNet staff on data exchange format, if 
Ongoing


sufficient interest and/or data.
Objective
1
Data Development
Task   3   Habitat
SubTask
3.b
Water Quality

Incorporate existing Clean Water Act 303(d) data and other water quality data as applicable

Project
Work Element
Accomplishments, Second Quarter, FY2001

Region
2
Maintain GIS water quality data event tables from the 303(d) 
Reviewed new Oregon DEQ 303(d) information for mistakes and format 

data on the StreamNet web site.
and reported to OR DEQ and EPA.  Incorporated this new information with 


existing data for StreamNet use in comparisons to fish distribution.

Objective
1
SubTask  3.b
Fiscal Year 2001 Second Quarter 
Page 15 of 50
Objective
1
Data Development
Task   3   Habitat
SubTask
3.c
Miscellaneous Habitat Data

Develop data for miscellaneous habitat related information, as available


Project
Work Element
Accomplishments, Second Quarter, FY2001

ODFW
1
Update key stream management area designations for OR 
This task was dropped due to budget cuts.

including FEMAT key watersheds, AFS aquatic diversity areas, 


ODFW coho source river reaches, ODSL essential salmon 


habitat and Priority Areas.


ODFW
2
Track the progress of ODFW aquatic habitat prioritization model 
1)  Provided technical support to the ongoing ODFW process to identify 

and provide a URL for StreamNet to link to model results when 
"salmonid emphasis areas" on the coast. (Bowers)


they are available.
2)  Provided written comments for a discussion about coastal Priority 


Watersheds development that could not be attended in person.
Objective
1
Data Development
Task
4
Facilities

Acquire data sets related to fishery-related facilities and structures from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective
1
Data Development
Task   4   Facilities
SubTask
4.a
Dams and Fish Passage Facilities

Enhance the existing StreamNet dams data set by updating relevant data from the Pacific Northwest Hydropower Database and Analysis System (NWHS) and the National Inventory of Dams


Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
Incorporate enhanced dams data into StreamNet.

MFWP
1
Combine the StreamNet dams dataset with dams named in the 
Received data and DEF in Kalispell. Will begin working on in 3rd quarter.

GNIS and the National Inventory of Dams, and exchange 


Montana's data.


ODFW
1
Update, maintain, correct and exchange dam information (as
Enhanced the forms and subforms in the Barrier database.



part of the Barrier database).

Objective
1
SubTask  4.a
Fiscal Year 2001 Second Quarter 
Page 16 of 50
Objective
1
Data Development
Task   4   Facilities
SubTask
4.b
Hatchery Facilities

Update and maintain a dataset on anadromous and resident hatchery facilities containing information on location, design, management and authorization

Project
Work Element
Accomplishments, Second Quarter, FY2001

FWS
1
Update hatchery facility records as needed
No corrections or additional information were submitted this quarter.

IDFG
1
Incorporate supporting hatchery structures, such as weirs and 
Implemented hatchery facilities data entry and edit screens. Started 

traps, into StreamNet.
revision of data structures for new data exchange format.


MFWP
1
Provide update of these data if changes have occurred in 
Duties transferred to Jeff Hutten; received data and DEF. Progress will 

Montana's facilities.
begin next quarter.


ODFW
2
Review and update Oregon hatchery facilities data and submit to 
1)  Continued to contact hatchery facilities trying to get updated 

PSMFC.
information.


2)  Updated 6 hatchery facility records


3)  Updated the Hatchery Contact List.


Region
1
Maintain spatial aspect of hatcheries table including location of 
Captured hatchery locations in the Yakima subbasin for a mapping request 

hatcheries and GIS data.  Assist states in tying hatcheries to 
for the Yakama tribe and submitted this information to the WDFW StreamNet


LLID-based stream locations when requested.
component.


WDFW
1
Provide standard geo-spatial coordinates (Longitude-Latitude)
In response to an issue involving assignment of SiteIDs to fixed (hatchery) 

for each facility.
sites, O'Connor contacted Bill Kinney and David Graves about the 


possibility of carrying and using both a CountyID and a SiteID on such data 


records, to better serve clients who seek the data from two different 


perspectives. The current Online system uses a single ID approach; further


discussion was deferred until we gained experience with the dataset 


once exchanged and loaded for access.


Objective
1
SubTask  4.b
Fiscal Year 2001 Second Quarter 
Page 1/ of 50

WDFW
3
Complete, convert, and exchange tabular and spatial data
1)  In January, Sikora and O'Connor met to discuss the status of hatchery 

tables of Washington state hatchery facilities, including federal
facilities. Dean Morrow and Darrell Mills of WDFW's Hatchery Division 


and tribal stations.
assisted Sikora, confirming the locations of various hatchery facilities. 


Sikora corrected the GIS system and tabular management file (0hatfac.db), 


accordingly. In February, Bruce Watson of the Yakima Tribe sent David 


Graves dams and hatchery facility location information and we planned to 


address these additions (and further questions for Darrell Mills) when we 


continued the BegFt work in March. That plan suffered delays.


2)  In March, Sikora planned to prioritize the facility work and also use 


StreamNet's event mapper to identify BegFts for Washington's facilities but 


problems adding our facilities as a background layer weren't resolved until 


April. While Martin worked out misc. issues, including the necessary 


projection factors, Lensegrav's time for this work was re-prioritized. We 


must renew this effort at the next opportunity. Through the trial and error, 


Lensegrav and Sikora continually documented how to maneuver the ARC 


software and Event Mapper to obtain shape files and update event mapper.


3)  Sikora sent Cheri Howe of DNR the GIS metadata documents when her 


interest focused on WDFW's facility codes.


Objective
1
Data Development
Task   4   Facilities

SubTask
4.c
Diversion/screening

Develop a data set for water diversions and screening

Project
Work Element
Accomplishments, Second Quarter, FY2001

MFWP
1
Review regional data exchange format.
We propose to remove this from the workplan.  NRIS is responsible for this 

dataset.  StreamNet can access it over the web.


MFWP
2
Provide input and data to watershed planning projects.
We propose to remove this from the workplan.  This is not a StreamNet 

database responsibility in Montana.


ODFW
1
Develop a database structure and compile Oregon's fish 
Continued database development.  Met twice with the ODFW State Fish 

screening data and submit a draft data exchange format to SC for
Screening Coordinator and once with the ODFW State Fish Passage 


 review and adoption.
Coordinator and other staff members.  Prepared and gave a presentation 


on the preliminary version of the database.  Created and distributed a 


database structure report to ODFW Fish Screening and Passage Program 


staff members.


ODFW
2
Identify fish screening data that is appropriate for the StreamNet 
This task was dropped due to budget cuts.

site and submit test records once an exchange format has been 




adopted.

Objective
1
SubTask  4.c
Fiscal Year 2001 Second Quarter 
Page 18 of 50
Objective
1
Data Development
Task
5
Habitat Restoration/Improvement Projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them in standardized, consistent formats for the following categories:

Objective
1
Data Development
Task   5   Habitat Restoration/Improvement Projects
SubTask
5.a
Fish and Wildlife Program Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects related to the Fish and Wildlife Program

Project
Work Element
Accomplishments, Second Quarter, FY2001

MFWP
1
Data will be updated for FWP Projects during FY-01; the spatial 
Conversion program created by Jeff Hutten; data exchanged.  Several 

data layer of project location will be updated.
projects with missing dates.


Region
3
Assist StreamNet partners with acquisition, development, 
Discussed coding conventions for various work types with several 

formatting and submission of data.
StreamNet partners.


WDFW
1
Follow-up from FY2000 habitat restoration project compilation 
Lensegrav prepared more instruction for Stan Allen on the prototype 

Internet Web Guide by building relationships in the mdb.

Objective
1
Data Development
Task   5   Habitat Restoration/Improvement Projects
SubTask
5.b
Other Projects

Prepare and maintain standardized data relating to tracking aquatic management and restoration projects other than related to the Fish and Wildlife Program

Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
Compile additional information from non-FWP restoration
1)  Performed a series of update queries on the latest MitProjects database

projects into StreamNet.
in order to update codes and values for WorkTypeID.


2)  Continued to pursue Forest Service SOPA data. Met with USFS staff to 


discuss the forests entering their SOPA log data into a GUI the 


incorporates MitProjects data exchange format. 3)  Modified the projects 


database so that the USFS can use in Access2000. Delivered to USFS 







staff along with the StreamNet data exchange format.

MFWP
1
Update Montana's Fish and Wildlife habitat restoration projects
Conversion program created by Jeff Hutten; data exchanged. 

into StreamNet's Restoration and Mitigation database and
Several projects had missing dates.


submit in data exchange format.


Objective
1
SubTask  5.b
Fiscal Year 2001 Second Quarter 
Page 19 of 50

ODFW
2
Design and develop a database to capture carcass placement 
A working beta version of the Carcass Placement Database has now been

data for Columbia Basin activities.
completed. A meeting was held during the quarter with carcass placement


management staff to review the management program and the database 


features.  Hurn and Brodeur collaborated on the design and the database 


creation.


ODFW
3
Provide technical assistance to GWEB and StreamNet staff as 
Responded to questions regarding habitat restoration data updates.

needed to make compilation of ODFW habitat restoration/


improvement projects in the Columbia basin more efficient.

Objective
1
Data Development
Task
6
Sub-basin Planning

Develop consistent data sets and information that are particularly suitable and useful for regional sub-basin planning and make them readily available for planners
Objective
1
Data Development
Task   6   Sub-basin Planning
SubTask
6.a
Provide data for Sub-basin Planning

Organize and distribute the available fish, wildlife and habitat data in a standardized format for use in Sub-basin Planning or other regional planning efforts

Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
Coordinate with sub-basin planning efforts to supply data.
Provided data requests from our Fishery Information System for subbasin 

planning efforts in the Palouse, Clearwater and Salmon subbasins.


MFWP
1
Provide data to planners on request
No requests have been received to date.

ODFW
1
Participate in discussions concerning data needs to support 
Communicated with ODFW staff to discuss the Columbia Basin Subbasin 

sub-basin planning or other processes adopted by the amended 
Summary GIS mapping needs (Bowers & Cooney).


Fish & Wildlife Program. Modify data plan and priorities as 




needed to be responsive.

ODFW
2
Provide consultation services and assistance to ODFW data 
1)  Provided extensive mapping and GIS support to Subbasin Summary 

managers to assist them in meeting Subbasin Planning needs.
planning efforts in the Deschutes, John Day, Umatilla, Walla Walla and 


Grande Ronde basins.


2)  Experimented with ArcView output image formats to obtain the highest 


quality image output that would import into MS Word.  


3)  Worked with Shelly Snyder of WDFW to fill a request for Oregon DEM 


data for her subbasin mapping efforts in the Walla Walla and mainstem.


4)  Processed Oregon and Washington landcover data for the Grande 


Ronde basin as part of the subbasin mapping effort.

Objective
1
SubTask  6.a
Fiscal Year 2001 Second Quarter 
Page 20 of 50

Region
1
Meet with sub-basin planners to discuss data types that may
Completed coordination with Council staff to put together a project to 

be needed, data sources, and to plan integration methods of
custom summarize all data in the StreamNet database for each of the 


the various data sets.  Assist planners acquire needed fisheries.
individual subbasins.  A contract was developed to complete this work 


data
during the summer using staff that would otherwise have been funded on 


other contracts to do other work.


Region
3
Provide StreamNet GIS coverages or other data (on request)
1)  Information and StreamNet data packages were completed for the 

to the entities conducting sub-basin planning.  Assist subbasin 
subbasins in the Columbia Plateau Province (Mainstem Columbia, Crab, 


planners with use of this data as needed.
Deschutes, John Day, Palouse, Rock, Mainstem Snake, Tucannon, Umatilla, 


Walla Walla, and Yakima subbasins), the Blue Mountain Province (Asotin, 


Grande Ronde, Imnaha, and Mainstem Snake subbasins), the Mountain 


Snake Province (Clearwater and Salmon subbasins), the Cowlitz subbasin 


in the Lower Columbia Province, and the Okanogan Subbasin in the 


Columbia Cascade Province.  Hard copy maps and CDs with the data in 


spreadsheets and with GIS data layers were prepared for each subbasin 


and delivered to each of the subbasin planning groups. 


2) Data were custom assembled for the Rock Creek subbasin at the request


of CBFWA for use in a subbasin assessment specific to this drainage.


3)  A package of specialized maps were made for the Yakima and Rock 


Creek subbasins for inclusion with subbasin assessment reports.  This task 


involved substantial work in converting textual descriptions of current and 







historic species extents from the Yakama tribe into a mappable format.
Objective
1
Data Development
Task   6   Sub-basin Planning
SubTask
6.b
Capture information from Sub-basin Planning

Acquire information developed during subbasin planning to update anadromous fish, resident fish, and wildlife data sets

Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Develop applications and procedures to update watershed 
No work this quarter. Regional discussions on final subbasin assessment 

assessment data during subbasin planning
guidelines and tools are proceeding slowly.


MFWP
1
Collaborate with regional staff and Montana CBFWA 
Subbasin planning is not yet underway.

representative when data become available

ODFW
1
Evaluate Subbasin Summaries and other Subbasin Planning 
This task was dropped due to budget cuts.

related documents related to Oregon, identify data which are not 


contained in StreamNet and adjust staff work plans to capture 




new data if appropriate and applicable.

Objective
1
SubTask  6.b
Fiscal Year 2001 Second Quarter 
Page 21 of 50

Region
1
In collaboration with CRITFC staff, provide subbasin planners
Gathered textual information on historic and current distribution of 

with computer applications to enter and edit information
anadromous species and hatchery facilities in the Yakima subbasin based 


developed during subbasin planning as described in Tasks 1.1 
on information from the Yakama tribe.  Converted this information into a 


through 1.5above.
standard format and submitted to the WDFW component of the StreamNet 


project for reconciliation with their information.


WDFW
1
Provide data compilation, conversion, and analytical services in 
Didn't add this back after budget cut until Q3.

support of the subbasin assessment process, the NMFS Viable 


Salmon Populations model, and related NWPPC needs.

Objective
2
Data Management and Delivery

Provide high quality data management services, with specific emphasis on the creation of regionally consistent data sets and the timely delivery of data to users in formats that meets their policy, planning, and management needs

Objective
2
Data Management and Delivery
Task
1.
Database Management

Maintain functional database programs at the state and regional levels to make consistent data sets for anadromous fish, resident fish and to a lesser extent wildlife available through the StreamNet online database system.  At both the regional and state levels, provide database management and administration necessary for accomplishing StreamNet objectives, to include: 1) maintaining regional and state-level StreamNet data sets, 2) processing exchange data into the regional database, 3) transporting data to the SQL environment, 4) enhancing StreamNet database structures and capabilities, and 5) providing programming services to project participants to allow for efficient data entry and transfer.


Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
After beta testing, implement Fish Information System in IDFG 
1)  Developed an Access database and GUI to track data requests.

StreamNet and IDFG Fishery Bureau
2)  Continued development of Fish Information System including 


development of data entry and edit screens for Reference Module, 


Collection Permits, Hatchery Facilities, Juvenile Trapping Operations, and an


 interface to the PTAGIS database.


IDFG
2
Continue development and improvements to Fish Information 
See work component 1. These are basically the same tasks.

System.


MFWP
1
Provide state-level data management services, emphasizing 
Ongoing.

coordination with StreamNet regional staff, MFWP and other state 


and federal natural resource agencies and encourage the use of 




consistent data attributes and data sets among all agencies.

Objective
2
Task
1.
Fiscal Year 2001 Second Quarter 
Page 22 of 50

MFWP
2
Provide high quality data management services with specific 
Ongoing

emphasis on creation of regionally consistent data sets and the 


timely delivery of data to users in formats that meet their policy, 


planning, and management needs.


MFWP 
3
Update existing data sets as described in Task 1 and provide data
Bull Trout barriers and Western Montana Fish distribution data were sent

 to the regional StreamNet office in DEF.  Provide data as sub-sets
to the StreamNet regional office.


 are updated rather than waiting for entire data to be complete.


ODFW
1
Provide state-level StreamNet database management / 
1)  Worked to develop ArcView / Access tools to facilitate data capture 

administration / development.  Enhance StreamNet and ODFW 
directly from field biologists without having to use hardcopy maps as an 


database structures, interfaces, tools, and capabilities as needed.
interim step.


2)  Worked with Mike Banach and Hilary Forest to enhance the Trend 


Interface, version UI-3-b4. Errors in the joining of tables in the backend 


database and interface were corrected.  Interface design errors were also


found and corrected.  More problems were encountered in March and are 


currently being resolved through collaboration with StreamNet staff.


3)  Enhanced the Riparian Lands Tax Incentive Program database user 


interface.


4)  Developed an example of how we might compile life-stage timing data.


ODFW
2
Develop custom GIS products and database structures that help 
Updated online 8.5 x 11 PDF maps of salmonid distribution data by 4th field 

improve data management and transfer with ODFW staff.
hydrologic unit.  Updated web interface to facilitate access to these maps.


Region
1
Maintain and manage the StreamNet database so information / 
Routine management and maintenance of the StreamNet database and 

data are available internally to project participants and externally 
online query system were continued in order to continue availability of data


via Internet.
via the www.streamnet.org website.


Region
2
Add data submitted to the StreamNet regional office into the SN 
The data provided to the StreamNet regional office, as detailed in the 

database within ~30 days of receipt from the project partners.
individual project accomplishments under Objective 1, were incorporated 


into the StreamNet database.


Region
3
Assist data-providing agencies with error checking of data sets.
1)  Regional personnel found hatchery return records with no values.  The 

Regional Database Manager consulted with ODFW to determine the proper 


steps to take, and the errors were corrected in both databases.


2)  Regional personnel conducted various data integrity checks of the 


existing data in StreamNet.  One of these was a list of data category and 


data type, in order to ensure they matched correctly.  A number of 


instances of mismatched categories and types were found.  These 


possible discrepancies were relayed to the appropriate data providing 


agencies, who made necessary corrections and then resubmitted those 







data to the central StreamNet database.

Objective
2
Task
1.
Fiscal Year 2001 Second Quarter 
Page 23 of 50

Region
4
Coordinate database compilation between agencies, helping to 
Regional staff managed creation of new lookup codes in a number of 

ensure that data submitted are usable, scientifically sound, and 
tables, ensuring that duplication, ambiguities, and errors were minimized.  


consistent.
(Species; habitat restoration; others)


Region
5
Update the database structure as new data categories are
The StreamNet database continued to change in order to optimize the new 

added or categories are changed.
web query system based on LLIDs through the use of views to create 


binary lookup tables and stored procedures to generate a matrix of all data 


combinations for the Web Query System.  Work was done to synchronize 


the database structure with the Data Exchange Format.  Preparations for a 


new database server were also made.


Region
7
Document all additions/changes to data structure, exchange 
1)  Compared the current Data Exchange Format to the current tables in the

formats, interface tools, etc.
SQL database.  Where discrepancies were found, appropriate changes 


were made in the DEF or the SQL tables.  The changes to the DEF were 


presented to the Steering Committee, and they were accepted for inclusion


in the DEF.  The new DEF version was accepted for  adoption, pending 


minor changes, at the March Steering Committee Meeting in Olympia, 


Washington.


2)  Many minor changes to the DEF were performed, both in anticipation of 


the Steering Committee meeting and after the meeting.  Many changes 


were performed which were not substantive in regards to the database 


structure, but hopefully will make the document easier to use and navigate 


within.  Attempted to automate creation of an appendix to the DEF which 


would house all lookup codes, but was unsuccessful.


Region
8
Develop metadata for all spatial data sets posted to the
Updated metadata for anadromous distribution layers and lakes layers to 

StreamNet GIS web page.
document changes to these themes.


Objective
2
Task
1.
Fiscal Year 2001 Second Quarter 
Page 24 of 50

Region
10
Provide programming services to project participants to assist 
1)  Shannon Hurn of ODFW reported several difficulties in making the 

with efficient data entry and data transfer
StreamNet Trend User Interface function with the ODFW database.  


Regional Fisheries Biologist Mike Banach and CRITFC database manager 


Hilary Forrest assisted ODFW with these problems, which were mainly 


related to bad interactions between the interface and a properly set up 


backend database.  Several small programming problems were corrected 


in the Trend User Interface.  Mike Banach and Hilary Forrest traveled to 


Corvallis to meet with Shannon Hurn in person and examine the errors 


occurring.  These three were able to fix all problems, none of which have 


so far re-occurred.


2)  The Oregon Department of Environmental Quality has developed an 


on-line tool, similar to the StreamNet Event Mapper, which can be used to 


determine an LLID and measure from the mouth of points along a stream.  


Regional personnel tested this application for its potential use, and to 


determine if we may want to develop a similar application or even use this 


one.  Evaluations are continuing.


Region
13
Ensure georeferencing of data is accurate and complete.
1)  Regional personnel encountered errors in the GIS cross-reference 

tables.  The Regional GIS Specialist was informed, and made the 


appropriate corrections, as well as informing the state partners as 


necessary.


2)  Reviewed, and corrected where necessary, georeferencing for 


multistream and coastal port trend data locations.


WDFW
1
Washington state data maintenance and exchange support 
1)  Before we temporarily lost Brown to another project, Lensegrav met 

services, including updated exchange format system, support for 
with Brown to discuss general compiling issues and ideas for programmed


MS Access 97, and support for new data categories and fields.
tools. Sikora starting building a summary of how to perform standard 


Paradox maneuvers in MS Access. Lensegrav started building Directory.db


to clarify the purpose and location of relevant files frequently used by 


StreamNet staff.


2)  Brown finished memotool.fsl, started fieldcompare.fsl and started 


requested revisions on casetext.fsl, while Sikora tested and edited the 


on-screen help for the tools. Memotool either counts the maximum 


characters used by the longest field entry or compares memo field entries 


in a single table. Fieldcompare makes it easier for users to compare 


non-memo field entries in two tables. Casetext converts the case text 


entries (i.e. upper, lower, first word upper or individually for specific 


words defined in a dictionary [i.e. O'Leary]. 


3)  Lensegrav tutored WDFW's Laurie Peterson on how to use ArcView 


and access the SDE coverages. To assist future users, he also improved 


the instructions.


Objective
2
Task
1.
Fiscal Year 2001 Second Quarter 
Page 25 of 50

4)  Sikora called Cedric Cooney, Bart Butterfield and Stephen Pastor to 


confirm for Mike Banach that they were in agreement with the minor 


changes that were discussed by email after hat-format4 was distributed. 


In the March SC meeting, all SC members approved Banach's 2/26/2001 


version with two caveats (some BegFt references needed to be fixed and 


the coordination requirements needed re-wording). Banach delivered the 


revised DEF late in April and changed the WBID coding convention for 


OutflowTypeID from centroid of the marine water body to always Pacific 


Ocean. This issue must be discussed.


5)  Sikora relayed the history of StreamNet's RetToStream field conventions


for Mike Banach and the other state's StreamNet staff.


6)  Woodard worked more on designing the separate internal WDFW 


hatchery returns and escapement database but he awaits a file from 


Sikora before he finalizes the escapement database.


WDFW
2
Update existing data sets as described in Task 1 and provide
See Obj 1 Task 1.b Comp 1 for issues Kinney found with the oct/dec2000 

data to the regional StreamNet office in Data Exchange Format
exchange of returns data. We didn't re-exchange a file and Kinney just 


(DEF).  Provide data as subsets are updated, rather than
fixed the entries.


waiting for entire data set to be complete.

Objective
2
Data Management and Delivery
Task
2.
Data Plan

Update and maintain a project data plan that identifies 1) current data holdings at the regional level, 2) data items to be incorporated in the current contract period and in future years, and 3) expectations for data development and delivery from participating organizations within the current contract period


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Provide input to the data plan to keep it responsive to subbasin 
Kept Steering Committee apprised of regional discussions, issues and 

planning and Framework needs and schedules.
developments concerning subbasin planning. While discussions are 


sometimes intense, regional consensus on an approach to subbasin 


planning is slow to achieve. Key data needs are fairly unchanging during 


these discussions, however, and these were provided to the Steering 


Committee.


ODFW
1
Work jointly with other participants to modify elements of data
Modified one staff member's work plan to include responding to a data 

plan or priorities based on needs arising out of sub-basin
request for hatchery mass-marking information.


planning or other processes that drive Basin data needs through 


the amended Fish &Wildlife Program.


Objective
2
Task
2.
Fiscal Year 2001 Second Quarter 
Page 26 of 50
Objective
2
Data Management and Delivery
Task
3.
Data Exchange Standards

Establish and maintain data exchange standards that ensure consistent format and content of data that originated from the multiple agencies and data sources in the basin.  Included will be proposed and adopted data exchange formats, metadata and location look-up tables for specific data items as described under Objective 1.  At the regional level, this task will provide technical assistance regarding standard codes and exchange formats for Fish and Wildlife Program and ESA- related projects, and for applicable tribal data compilation activities.  At the state level, this task will provide similar technical assistance for state agency data activities applicable to StreamNet.


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Participate in the design, development and maintenance of 
Reviewed DEF issues as they were presented to the Steering Committee. 

standard codes and data exchange formats. This will occur 
Assist ODFW and StreamNet staff with database problems.


through involvement on the Steering Committee and technical 


work groups.


IDFG
1
Participate in the design, development and maintenance of 
Provided review, input and approval of new data exchange formats, 

standard codes and data exchange formats. This will occur 
including 2001.1 and fish distribution.


through involvement on the Steering Committee and technical 


work groups. There is no set schedule for this task, because it is 


highly dependent on issues facing the Steering Committee. 


Potential new data exchange standards may include juvenile 


abundance, genetics, stream habitat, stream temperature and 


resident fish releases.


MFWP
1
MFWP StreamNet will participate in the design, development
Ongoing.  Will finalize 4th quarter.

and maintenance of standard codes and data exchange formats 


through involvement on the Steering Committee and technical 


work groups.


ODFW
1
Participate in the design, development and maintenance of 
1)  One staff member was assigned to a three-person work group to find 

standard codes and data exchange formats. This will occur 
duplicate references in the StreamNet library system. Work is still in 


through involvement on the Steering Committee and technical 
progress.


work groups. There is no set schedule for this task, because it
2)  Provided comment on whether or not we should keep RRN in the 


is highly dependent on issues facing the Steering Committee. 
StreamNet exchange format. The consensus in Oregon was as long as 


Potential new data exchange standards may include juvenile 
data that is currently web accessible is not impacted, and there are no 


abundance, genetics, stream habitat, stream temperature and 
NHD issues, Oregon has not problem with removing RRNs.


resident fish releases.


WDFW
1
Compile and review the specific criteria used by participating 
O'Connor participated in some initial comparative discussions of fish 

agencies in describing fish distribution, use, or extent information, 
distribution and use criteria that go beyond the current StreamNet 


in order to find and adopt common standards among data 
standards for anadromous fish (specifically using WDFW/USFWS criteria 


providers.
developed in 2000 for bull trout). Integrating these with Montana's parallel 


but distinctive approach to describing resident species will be a complex 


challenge that hasn't progressed beyond the share-and-compare stage at 



this point (see 1.2a.1).


Objective
2
Task
3.
Fiscal Year 2001 Second Quarter 
Page 27 of 50

WDFW
2
Analyze Hatchery Returns exchange format and explore
Additional Steering Committee member comments on the draft hatchery 

whether a second table (covering Spawning and Disposition
returns format were sent in to O'Connor. The task of compiling these into a 


data fields) is needed to more accurately meet the needs of
revised and broadened format proposal has been shifted to Q3 due to 


the Artificial Production Committee.
competing priorities.


WDFW
4
Move toward complete adoption of LLIDs as the standard
1)  In February, Lensegrav finished assigning StreamNet location codes to 

stream referencing code by reviewing and completing the RRN-
the simple PSC codes (using files Supercode.db, 1gil-redo-some-LLIDXPSC


to-LLID conversion, addressing supercode issues, and assuring
&more.db, 3wdfw-supercodelocs.db and 3wdfw-Supercode).  That work


that LLIDs are assigned to all locations where StreamNet data
followed with research of the complex PSC codes covering several rivers.


exist.
Lensegrav compared the rivers included in each complex PSC code against


the rivers included in a relevant HUC or WRIA (using and updating file


research-big-superids.db).  In March, Lensegrav finished building a table to


assign supercodes to group PSC codes that couldn't be mapped by HUCs or


WRIAs (file groupXindivpsc.db).


2)  O'Connor generated a document describing the process of assigning 


"site-Ids" to Washington marine areas. The procedure involved generated a


LongLat value from the centroid of the polygon formed by each 


commercial and sport salmon area in Puget Sound, the Straits, Grays 


Harbor, Willapa Bay, and the Washington Coast. These will be used to 


address (and replace) the marine "supercodes" previously assigned to 


trends from Washington marine areas.


3)  Sikora also had Lensegrav start a small step (building a table with 


records for each county touched by WDW's Snum codes) in an effort to 


globally assign county codes to the Walocs file. To date, WDFW's Brodie 


Cox can't completely answer release data requests based on counties. 


After we started this first step, Sikora discovered only a few Walocs 


records need county codes and she must renew discussion with Brodie 


Cox about the true extent of the need and the best approach to adopt.


WDFW
5
Provide metadata for tabular and spatial datasets according to 
When tabular data is exchanged, Sikora submits the relevant 

guidelines adopted by the Steering Committee.
metaform.doc. No exchanges occurred during this period.


WDFW
6
Construct a new data compilation and conversion system to 
See Obj 2 Task 1 Work Element 1 for details.

provide data in MS Access according to the most recently 


adopted exchange format version. Begin exchanging data in 


MS Access form by winter, 2001.


Objective
2
Task
3.
Fiscal Year 2001 Second Quarter 
Page 28 of 50
Objective
2
Data Management and Delivery
Task
4.
GIS Data System

Establish and implement procedures for coordination of StreamNet-related spatial data activities among participating organizations, to include regular meetings and or other communication links among participating GIS specialists. Designate and maintain metadata format for spatial data to be used by StreamNet participants. Prepare map products in hardcopy and/or electronic format for use in Program-related aquatic resource policy, planning, and management.  Provide for distribution of spatial data in GIS and tabular format and as GIS products.


Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
Maintain and enhance a geographic information system (GIS) 
1)  Moved our core GIS layer to a new file server, purchased by IDFG. This

related to regional and state-level StreamNet goals and
allows greater access to GIS data by IDFG staff.


objectives.
2)  Developed a custom ArcView application for filling species list data 


requests. This increases our speed and accuracy in filling information 


requests.


IDFG
2
Prepare data and map products from StreamNet data on request
Responded to 10 requests for GIS data, mostly for fish distribution layers.

MFWP
1
Maintain a state- level GIS program (state and StreamNet 
Surplused one Unix box to BPA; the other to State of Montana. Received 

funded)
1.75 permanent FTE from legislature for GIS MFWP program for FY02. 


FTE will be split among ISU staff that is also responsible for StreamNet. 


Had temporary FTE for the last two years.


MFWP
2
Prepare map products in hardcopy and/or electronic format for 
Filled 21 Fisheries related GIS map and data requests during the quarter.

use in Program-related aquatic resource policy, planning, and 


management.


ODFW
1
Participate in planning and coordination meetings for state-
Updated metadata for primary anadromous salmonid distribution data 

level 24k hydrography layer to ensure compatibility with the 
layers.


StreamNet's adopted hydrography.


ODFW
2
Maintain and enhance a geographic information system (GIS) 
1)  Reviewed Oregon Natural Heritage Program's latest list of T&E species 

related to regional StreamNet goals and objectives (general 
designations which highlighted that fact that some of our state ESA coding 


maintenance, metadata development and maintenance,
in the distribution data needs to be updated.


planning and coordination activities, etc.).
2)  Various system admin related tasks including ArcView upgrade, 


resolving disk partition / space constraint issues and backup scripts.  


Successfully loaded the Oregon Dept. of Forestry's Image locator 


extension to ArcView.  This extension allows the user to create an index 


to the DRG's and then with the "image tool" the user can click anywhere on


the view and that DRG will load into the view.  This will save immense 


amounts of time when compared to the process of loading DRG images 


manually and should be useful in future distribution development efforts.


3)  Modified Event Editor tools to facilitate update of Bull Trout event data in 


StreamNet format.


Objective
2
Task
4.
Fiscal Year 2001 Second Quarter 
Page 29 of 50

ODFW
3
Prepare spatial data and map products in hardcopy and/or 
Provided feedback on the online habitat restoration data.

electronic format for use in Program-related aquatic resource 


policy, planning, and management.


Region
1
Maintain and enhance a geographic information system (GIS) 
1)  Changed computers and re-installed and configured GIS software 

related to regional StreamNet goals and objectives.
completely on primary and secondary computers.  This was done to 


increase computing speed, and was made possible by replacement of the 


database server freeing up one computer that had been held as backup for


the server with the bad hard drive in its RAID system.


2)  Revised the StreamNet lakes GIS layer to include updated information 


from WDFW.  Posted this GIS layer, along with updated documentation, to 


the StreamNet web site for download.


Region
2
Prepare GIS data and map products from StreamNet data.
Prepared GIS data and map products from StreamNet data, as needed.  

Responded to all requests from the public and prepared GIS data, maps, 


and other products for 38 public requests.  Requests were from a variety 


of sources including private citizens, environmental consulting firms, 


government agencies, educators, and students.  Prepared more detailed 


map products for requests from the NWPPC and associates for use in 


reports, etc.  Examples included the design of a database application to 


trace and summarize the downstream stream path to the ocean of 


hatchery releases from virtually any location in the Pacific Northwest and a


trio of maps of select watersheds in Southwest Washington.


Region
3
Integrate the functioning of the GIS system with the StreamNet 
1)  Determined and added improved tributary flow information to stream 

fisheries and habitat database, in support of the query system.  
information in the database.


Create cross tables and queriable maps used via the StreamNet 
2)  Continued to improve and refine cross tables where errors were found.


web interface.
3)  Determined complete cross tables for new Montana hydrography, 


intersecting the new stream layer by county, subbasin, region, and 


watershed (HUC), and adding this information to the database to make 


Montana data queryable.  Revised this information for the updated Idaho 


hydrography but did not add this information to the database pending 


upcoming data submissions from IDFG.


Region
4
Direct users to other GIS resources when requests exceed
Directed users to other GIS resources when requests exceeded StreamNet 

StreamNet capability
capability.


WDFW
1
Create approved reference documents for all exchanged spatial 
Didn't add this back from budget cut until Q3 but see Obj 3 Task 1 Comp 1.

data sets. (See also Task 2.3, work component 5)


Objective
2
Task
4.
Fiscal Year 2001 Second Quarter 
Page 30 of 50
Objective
2
Data Management and Delivery
Task
5
StreamNet Internet Site

Continue to maintain and enhance the existing client-server system to provide access to StreamNet data products through the Internet.  The StreamNet home page will continue to be recognized as the project's primary data delivery vehicle.  Priority will be given to incorporating data developed through Objective 1 and providing access to reference materials secured through Objective 3.  Appropriate training on the use of the system will be provided through a combination of on-line help and in-person training sessions.

Objective
2
Data Management and Delivery
Task   5   StreamNet Internet Site
SubTask
5.a
Maintain the StreamNet Client Server system

Project
Work Element
Accomplishments, Second Quarter, FY2001

Region
1
Maintain, upgrade as needed, and administer the StreamNet
An increasing amount of daily maintenance and frequent restarts were 

web servers.
necessary to keep the StreamNet web server up and running.

Objective
2
Data Management and Delivery
Task   5   StreamNet Internet Site
SubTask
5.b
Enhance and improve the StreamNet website

Maintain and enhance components of the StreamNet home page and incorporate new features that complement existing components

Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Work with subbasin planners to identify modifications and new 
Library staff worked on scanning the 1990 subbasin plans.  They were 

uses which will make the website more useful to them
added to the Library web pages on Subbasin planning.


CRITFC
2
Identify changes and new features which will improve delivery
Web page went live with access to the electronic catalog and began 

of Library services
adding PDF files to the Subbasin planning section.


Began using Ariel document transmission/receipt software to enable faster


receipt of journal article interlibrary loans.


CRITFC
3
Work with regional staff to implement changes identified above.
Began talking to Karen McGill about web site design and coordination of 

library web site with Project web site.


IDFG
1
Recommend and/or take part in review of new products and 
Provided feedback during Steering Committee meetings on new website.

features.  Provide feedback on content, suitability, navigability 


and data currency issues.


ODFW
1
Recommend and/or take part in review of new products and 
1)  Investigated differences between ArcView 8 and Arc Info 8.

features.  Provide feedback on content, suitability, navigability
2)  Developed survey to query users of the salmonid distribution data to 


and data currency issues.
better understand how they are using the data and how we may be able to


improve upon it to meet their needs.


Objective
2
SubTask  5.b
Fiscal Year 2001 Second Quarter 
Page 31 of 50

Region
1
Summarize results from the StreamNet online user survey.  
1)  Due to a persistent problem that was not quickly overcome, an 

Compile a list of recommended changes and improvements to
alternative query site was created on a server in Boise, Idaho, for those 


the online data system
users who were unable to use the regular StreamNet query system.  This 


system was installed, debugged, and linked to for several weeks.  The 


problem that necessitated this alternate query site was subsequently 


identified and corrected, and the alternate query site was taken down after


 we were certain the original problem had been fixed.


2)  The StreamNet query system was updated and had errors fixed.  


These error fixes and enhancements were tested and then ported to the 


production web site.


3)  Several corrections were made to the Glossary in the Fish Facts 


section of the web site.  The wording was improved on a number of pages



on the site.


Region
3
Plan to enhance the website content by adding additional kinds
During a Power Planning Council meeting the Council requested that, to the 

of information that will support the Fish and Wildlife Program.  
degree possible within existing project scope and support, we should 


Develop concept for increasing information by coordinating
attempt to begin acquisition and public posting of more data related to 


with regional data users
resident fish species.  Staff discussions were held to determine how best 


to approach that request.  We determined that we will begin to contact 


sponsors of resident fish projects funded by BPA to locate resident fish 


data.  For any data that fit current data categories, we will work with 


sponsors to acquire the data for inclusion in the StreamNet database.  For 


other data, we can obtain electronic data sets and make them available as 


'Independent Data Sets' and post them in an archive in whatever form they 


currently exist.


WDFW
1
Take part in review of new products and features. Provide 
O'Connor compiled comments on the draft StreamNet Online User's Guide 

feedback on content, suitability, navigability and data currency 
from six WDFW staff and sent them to Bruce Schmidt.


issues, especially issues related to providing static or dynamic 


map capabilities. 

Objective
2
Data Management and Delivery
Task
6.
1:100,000-scale Hydrography

Maintain the 1:100,000-scale PNW hydrography for purposes of attaching StreamNet data.  Coordinate with efforts to prepare a National Hydrographic Dataset (NHD). Develop a standardized method for incorporating lake hydrography and attribute information.


Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
1
Maintain the Idaho portion of the 1:100,000-scale PNW 
Identified needed new routes and some corrections to make. Changes not 

hydrography for purposes of attaching StreamNet data.
yet made.


Objective
2
Task
6.
Fiscal Year 2001 Second Quarter 
Page 32 of 50

IDFG
2
Participate in coordination of the National Hydrographic Dataset 
Provided feedback to other state agencies regarding relations of PNW river

(NHD).
reach files and NHD. Also provided feedback on development of 24k 


hydrography layer for Idaho.


MFWP
1
Support the efforts of the NHD and convert Montana
Coordinated with NRIS on work to convert Montana hydrography to NHD; 

hydrography to NHD upon receipt.
assigned tasks and began work.


MFWP
2
Enhance layer with LLID and stream level routing.
Completed assignment of LLID and stream level routing for western 

Montana.  Converted MRIS data to routed hydrography for western 


Montana.  Regional StreamNet staff assisted in the process of assigning 


LLID and other quality checking.


MFWP
3
Coordinate with NRIS in the QA/QC of the NHD for Montana 
NRIS staff began QA/QC of NHD files. StreamNet staff assisted by building 

including the development of a lakes layer (funding provided by 
ArcView interface to help with the QA/QC.


the BOR for lakes).


ODFW
3
Provide technical advice on hydrology routing and other issues 
Provided technical support to ODFW staff working with routed 

including those related to working with higher resolution 
hydrography.


hydrography.


Region
1
Continue to maintain the regional 1:100,000-scale PNW 
Routine maintenance and management of the hydrography continued.

hydrography.


Region
2
Implement updates to the 1:100,000-scale PNW hydrography
1)  Completed review of updated IDFG hydrography, reconciling all border 

from state cooperators.
issues between other state hydro sets. 


2)  QA'd Montana hydrography and finalized this data set in coordination 


with MFWP StreamNet component.  Reformatted this final Montana 


Hydrography data set to match PNW Reach file format.


Region
3
Update and serve a regional web version of the 1:100,000-scale 
Corrected file errors in some of the hydrographic files and updated the 

PNW hydrographic set from the StreamNet website.
corrected files to the StreamNet website.


WDFW
1
Complete Steering Committee discussion about lake attributes 
See Obj 2 Task 6 Work Element 2.

useful to share in a regional database; determine support for a 


new data format.


WDFW
2
Compile, standardize, and exchange point, line, and polygon 
1)  To coordinate StreamNet's lake layer with the WaterBodyIDs used in 

information for lakes stocked with fish that appear at 100K (or 
returns data, Hudson sent David Graves a copy of WDFW's Lake layer just


higher) resolution.
before we renamed the misnomer LLID field to WBID (waterbodyID). Sikora


warned Graves of the change and confirmed that our internal tabular file 


that is used to assign codes for the returns data does coincide with that 


spatial layer.


Objective
2
Task
6.
Fiscal Year 2001 Second Quarter 
Page 33 of 50

2)  In January, Bob Huxford demonstrated for O'Connor, Sikora and 


Lensegrav the independent GIS layer in his commercial Lakes of 


Washington product. Lensegrav reviewed Huxford's product further and 


we will buy at least a few copies when it is ready for sale. Sikora and 


Lensegrav responded to a few request for lake bathymetric (topo) maps. 


Sikora discovered that old Washington Department of Wildlife publications 


(several publications titled as ...High Lake Surveys...) are a source of lake 


topo maps. Lensegrav compared the SW Washington high lakes surveys 


against a requestors Washington lakes website and found both are good 


resources for common and unique lake topo maps. In February and March, 


Sikora identified 18 WBID codes that are also used as LLID codes. 


Coincidentally, 32 different hatchery facility site codes (concatenated 


longitudes and latitudes) are also used as LLIDs. O'Connor's research 


revealed that DOE adopted WBIDs that are sometimes far from the centroid 


of the lake. He raised concerns with DOE about their process for assigning


WBIDs. We've yet to learn the scope of the issue or to interest DOE in our 


concerns - further research is needed.


3)  Sikora researched and sent WDFW's Stacie Kelsie historical information


about lake sections that are reported as greater than 36.


4)  Sikora sent Bob Pfeifer of Parametrix a copy of our lake layer shape 


files and began her first effort to compare the Lakes.dbf shape file against 


the statlake.dbf that is dumped from Hudson's spatial interface. Lensegrav 


helped organize all available information by building lake-fields.db to show 



all fields common or unique to each lake related source.

Objective
2
Data Management and Delivery
Task
7.
Data Requests

Receive and respond to requests for data, source materials, and custom products.  Response to requests will be honored within the limits of available resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.  Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural resource management activities.


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
See Tasks 1.1h, 1.6, and Objective 3
Answered requests for materials as in Objective 3.

Further discussions with Drew Parkin made clear that the development of 


bibliographies was not going to be fiscally feasible.


IDFG
1
Continue to respond to requests for information from StreamNet 
Completed 44 requests for location specific fish species list and other data 

database, including requests for fishery information that comes 
requests.


into the Idaho Conservation Data Center (Natural Heritage 


Program), other IDFG programs and personnel, and outside 


agencies and consultants.


Objective
2
Task
7.
Fiscal Year 2001 Second Quarter 
Page 34 of 50

MFWP
1
Receive and respond to requests for data, source materials, and 
Supported FWP Fisheries Division Native Species Management, Westslope 

custom products.  Respond to requests within the limits of 
Cutthroat Trout Priority Areas and Yellowstone Cutthroat Trout Data 


available resources, with priority given to information requests 
Collection.


having direct relevance to the FWP.


ODFW
1
As requested, consistent with other deliverables in this contract, 
A total of 9 data,  76 document, 3 map, and 10 'other'  requests were 

receive and respond to requests for data, source materials, 
answered during this quarter. A detailed list by requester and request type


technical training, and custom products.
 can be made available upon request.  The number of data downloads from


 the ODFW FTP site is not available for this quarter.


Region
1
Respond within one day whenever possible to all user requests 
Responded to over 80 requests for data, GIS assistance, or general 

received via email, phone, or other medium.  Typical requests 
information.


received include help using the query system, complex data 


requests not easily done with the query system, and requests for


GIS coverages and maps.


Region
2
Fill requests for data not available via the web in an expeditious 
1)  We received a request from NWPPC late in the quarter for mass adipose 

manner, with highest priority for people working for the NPPC's 
fin clipping data.  This request will be addressed in the third quarter.


Fish and Wildlife Program.  Requests from outside the Fish and 
2)  We obtained funding this quarter for special assistance in gathering 


Wildlife Program or participating agencies will be addressed on
subbasin planning data.  This work will be conducted in the third quarter.


an 'as possible' basis.


WDFW
1
Generate maps, data reports, and electronic copies of datasets 
Didn't add this back from budget cut until Q3 but continued answering data 

as requested.
requests. Important data requests are reported under the task number 


pertinent to each dataset because requests often reveal data issues or 


inspire different compiling approaches. Upon request, the details for each 


data request is also available from a detailed tracking file (internally stored 


on WDFW's server at S:\Fish\Groups\BDS\Streamnt\Requests\Datareq.db). 


Overall, WDFW StreamNet staff provided anadromous and resident fish 


release information, salmonid escapement estimates, barriers data, and 


over 250 maps and 12 digital GIS coverages featuring fish distribution/use 


and hydro layer data to clients representing USFS, Eastern Washington 


University, Snohomish County, CRITFC, WDFW, the Washington 


Environmental Council, and various private citizens.


WDFW
2
Provide PRIORITY data support for subbasin assessments and 
O'Connor and stiff member Brodie Cox provided detailed Yakima Basin 

other new elements of the NWPPC Fish & Wildlife Program.
resident and anadromous fish stocking data as well as several maps in 


support of the Columbia Plateau Province's data review as part of the 


Council's Rolling Review process. O'Connor attended the data review and 


responded to fish data and GIS questions.


Objective
2
Task
7.
Fiscal Year 2001 Second Quarter 
Page 35 of 50
Objective
3
Library / Reference Services

Provide a full service regional library for fish (and to some degree wildlife) literature (published and gray), including documentation of all data in the StreamNet database.

Objective
3
Library / Reference Services
Task
1.
Collection Development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document data source materials, Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies, interested parties, and other libraries.


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Coordinate source material submissions for data compiled
Received and cataloged submissions from Project members.



under Objective 1. Develop standards for document submissions

CRITFC
2
Collect and catalog documents prepared by contractors
Continued project of filling in gaps in runs of annual reports from various 

(including final products published by BPA and draft documents
projects. Identified need for tracking a particular bit of information in regard 


suitable for public release) under the Fish and Wildlife Program.
to BPA publication and contracts.


Work with Publications distribution for better publication 


notification and deposit system.


CRITFC
3
Collect and catalog documents from the Council's Fish and
Completed cataloging the books in the NPPC Fish and Wildlife Program 

Wildlife Program-related collection.
collection.  Began working on new documents received that include 


memos, notices and other internal documentation.


CRITFC
4
Collect and catalog additional books, journals, agency reports, 
583 records were added to the online catalog. These include new 

gray literature, research reports, and documents that are 
materials, as well as older, donated materials.


applicable to management of the region's aquatic resources.


MFWP
1
Provide an update to the electronic version of documents used
Sent CD to StreamNet library.  Fisheries Division staff continued to maintain 

as source materials for data compiled in Objective 1. 
library.  StreamNet staff worked with contractor who enters records to 


add species lookup and LLID lookup. Began assigning library reference to 


species level data in MRIS.


ODFW
1
Provide originals/copies of all documents and reports referenced 
1)  Drafted and submitted reference memos and the associated metadata 

in the compilation of new StreamNet data holdings, but not
for two dynamic databases related to Oregon DistPres data.


already housed in the StreamNet Library.
2)  Spent time cataloging all new references related to abundance trends 


for a future library submission.


ODFW
2
Update the set of historic (pre-1975) Oregon Fish Commission
This task was dropped due to budget cuts and the fact that the StreamNet 

and Game Commission reports and provide to the StreamNet
Library is running out of physical space to hold new materials not linked to 


Library as available.
StreamNet trends.


Objective
3
Task
1.
Fiscal Year 2001 Second Quarter 
Page 36 of 50

ODFW
3
Update library bibliography of ODFW, Fish Commission, and
Continued to perform numerous maintenance, update and correction 

Game Commission reports with historic and current publications
activities to the InMagic bibliography, however the bibliography is not yet 


and make the bibliography available for reference via StreamNet
ready for online access because there is no database manager on staff to 


and ODFW websites.
perform the necessary tasks.


WDFW
1
WDFW StreamNet will continue to collect documents used as 
1)  Sikora compared Oregon's reference records with the July 2000 

source materials for data in Objectives 1 and 2. Documents will
StreamNet mdb to identify the differences against StreamNet's reference 


be assigned reference numbers and forwarded to the StreamNet 
table and found no alarming differences. ODFW data has few differences 


library as per established SN guidelines.
because they adopted the StreamNet entries about a year ago. Because of


the Feb 28 earthquake, Sikora couldn't produce a printed report for the 


March SC meeting. But she started discussion on how the reference 


record data flows with hopes to reveal how the differences occurred for 


WDFW records. At the outset of the discussion, greater issues were 


revealed on how to assign a RefID. Collectively the designated team 


(Oftedahl, Shannon and Sikora) must resolve conventions for RefID 


assignment before we discuss reference record data flow issues. We're 


waiting for Oftedahl's report on all publications that have more than one 


RefID.


2)  In February, using the Fish Distribution spatial data reference 


assignment, Sikora began training Burns on how to manage, scope, and 



document data files and issues.


Objective
3
Library / Reference Services
Task
2.
Provide Access to Collection

Provide user access to the materials described in Task 3.1 by providing facilities for storage of paper and electronic copies of documents, an online catalog of all documents in collections, and staff to answer location questions and respond to requests.


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Maintain an appropriate facility for the storage and public use of 
Space for collection maintained.  Began discussions with CRITFC 

the physical collection.
operations staff about expansion and library growth.


CRITFC
2
Catalog, organize and maintain the collection for appropriate 
1)  Continued cataloging materials.  

on-site use.
2)  Worked on space planning issues with regard to rapidly expanding 


periodical collection.


CRITFC
3
Provide access to the StreamNet Library Catalog.
Access to the StreamNet Library catalog was added to the web page.

CRITFC
4
Develop a schedule for regular updates of the reference table.
Continue working with staff on reference table updates and what is still 

necessary now that the reference table is no longer acting as our web 


access catalog.


Objective
3
Task
2.
Fiscal Year 2001 Second Quarter 
Page 37 of 50

ODFW
1
Enhance, maintain, and update ODFW Library software and 
No effort was made this quarter - no database manager on staff.

procedures to ensure adequate tracking of information requests, 


key word searches, and easy comparison to the StreamNet 


Library holdings.

Objective
3
Library / Reference Services
Task
3.
Improve Electronic Access

Enhance the online capabilities of the StreamNet Library, including catalog access via the internet and an electronic archive of key Columbia Basin documents.


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Manage and maintain the Library catalog server
Server received from CRITFC technical support.  Set up library web page 

and settled DNS entry problems.


CRITFC
2
Integrate the library catalogs into a single web application using 
Received updated catalog from Montana.  Began trying to import catalog 

TextWorks Web Publisher
into the Library catalog.


CRITFC
3
Develop an electronic archive of key Columbia Basin documents
Continued digitizing the 1990 subbasin plans.

CRITFC
4
Make electronic documents available through the Library web 
Library web0pages working.  Electronic documents are being added.

page.


Objective
3
Library / Reference Services
Task
4.
Library Services

Manage the StreamNet Library and provide library services to the StreamNet user community and the general public.

Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Provide access guide to outline services for patrons. 
Added the access guide to the library web site as a page titled Services.

CRITFC
2
Assist users to locate information by providing reference, 
1)  Answered approximately 346 requests for information.  

referral, and computer based search services.
2)  In addition to the directional requests that are not counted, we received 


several email requests for information from the library website.


CRITFC
3
Provide document delivery services, including inter-library
1)  We lent 26 books to other libraries.  

lending and borrowing.
2)  We provided materials to distant clients in Enterprise, OR; Pendleton, 


OR; and other locations.


CRITFC
4
Maintain hardcopy files of draft and final documents related to the 
1)  Continued to archive electronic files on the Library server.  

NPPC amendment process, subbasin planning, and Columbia 
2)  Continued to identify which documents should be printed for paper 


River/Portland harbor dredging
archives.


ODFW
1
Respond to requests for ODFW documents and other source 
Provided 209 hardcopy documents and 5 electronic documents to 64 

materials.
individual users during the quarter.


Objective
3
Task  4.




Fiscal Year 2001 Second Quarter 





Page 38 of 50

Objective
3
Library / Reference Services
Task
5.
Inter-library Coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other collections that will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Collect information about other regional fish and wildlife library 
Continued efforts at locating fish and wildlife libraries in the region.

collections and access policies.


CRITFC
2
Provide consultations for agencies and groups on ways to 
Visited WDFW-Vancouver office to assist with library development.

coordinate catalogs and services.


CRITFC
3
Coordinate with users, agencies, and regional libraries to 
1)  Needs assessment was completed.  Returns were minimal, so there 

improve services and avoid unnecessary duplication.  Perform
wasn't much to analyze.


a needs assessment for the Library.
2)  Continued to update records of library periodical holdings.


CRITFC
5
Maintain presence in related Library groups (i.e. IAMSLIC, NRIC)
1)  Renewed membership in SLA, include the Oregon Chapter and 

to provide access to knowledge on Best Management Practices
Environmental Resources Management Division.


for libraries and current awareness of subject-related materials.
2)  Attended annual Cyamus (IAMSLIC west coast chapter) in Monterey.


ODFW
1
Coordinate with the Oregon State Library system to enhance 
1)  Processed 24 Inter-Library Loans for the sturgeon project through the 

access to published periodicals, journals, and other documents 
Oregon State Library.


for StreamNet users.
2)  Attended open house at State Library and met with the State Librarian 


regarding library issues.

Objective
4
Services to Fish and Wildlife Program Activities

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife Program projects

Objective
4
Services to Fish and Wildlife 
Task
1
Monitoring and Evaluation

Assist in the development of products that contribute to the monitoring and evaluating (M&E) of Fish and Wildlife Program effectiveness.  Specific area of involvement will include: 

Objective
4
Services to Fish and Wildlife 
Task   1   Monitoring and Evaluation
SubTask
1.a
M&E Participation

Participate in Program-related monitoring and evaluation work groups

Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Assist basin wide efforts to develop an R/M/E plan consistent 
No work this quarter. This has been an inactive issue, regionally, since 

with the regional Framework
CBFWA and the NWPPC staffs completed their reports last year. It is 


expected to be actively discussed again as subbasin planning efforts begin.


Objective
4
SubTask  1.a
Fiscal Year 2001 Second Quarter 
Page 39 of 50

IDFG
1
Participate in discussions concerning data needs to support 
Participated in discussions at Steering Committee meetings.

processes adopted by the amended Fish & Wildlife Program for 


Monitoring and Evaluation. 


MFWP
1
Participate in discussions concerning data needs to support 
Discussed at SC meeting; had to attend via conference call.

processes adopted by the amended Fish & Wildlife Program for 


Monitoring and Evaluation.


ODFW
1
Participate in discussions concerning data needs to support 
Reviewed NMFS's data needs as related to the Viable Salmon Population 

processes adopted by the amended Fish & Wildlife Program for 
analysis and the Regional Data Management Committee's papers related to 


Monitoring and Evaluation.
data management needs in the basin.


Objective
4
Services to Fish and Wildlife 
Task   1   Monitoring and Evaluation
Task
1.b
Evaluation

Periodically re-evaluate the StreamNet data plan to ensure consistency with M&E needs

Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Keep Steering Committee apprised of regional R/M/E plans and 
Presentations are made regularly to the Steering Committee when new 

needs
information or action occurs at the regional level.


ODFW
1
Participate in discussions concerning the StreamNet data plan
Received and reviewed Gustavo Bisbal's "Conceptual design of monitoring 

to ensure it supports processes adopted by the amended Fish & 
and evaluation plans for fish and wildlife in the Columbia River ecosystem" 


Wildlife Program for Monitoring and Evaluation.
document.


Region
1
Keep abreast of regional data needs related to Fish and Wildlife 
In response to a request from NMFS, we prepared an inventory of redd 

Program Monitoring and Evaluation and plan for StreamNet 
count data in the StreamNet database to make it easier for them to locate 


database's ability to fulfill these needs.
data needed to evaluate salmon viability.


Objective
4
Services to Fish and Wildlife 
Task   1   Monitoring and Evaluation
Task
1.c
M & E Reporting

Prepare reports and data products that illustrate key M&E topics

Project
Work Element
Accomplishments, Second Quarter, FY2001

ODFW
1
No work planned but we are willing to adjust work plans to 
This task was dropped due to budget cuts.

address amended Fish and Wildlife Program needs.


Objective
4
SubTask  1.c
Fiscal Year 2001 Second Quarter 
Page 40 of 50

Objective
4
Services to Fish and Wildlife 
Task
2.
Watershed Projects

Provide data and data services to Fish and Wildlife Program-sponsored watershed planning and assessment projects

Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Assist subbasin planners to develop monitoring and evaluation 
Subbasin planning activities have yet to begin. No activity this quarter.

activities for watershed projects that will integrate smoothly with 


StreamNet databases (cost sharing)


MFWP
1
Participate in watershed and, sub-basin planning to the extent 
No requests for participation were received.

requested by the Council and other regional participants.  


Coordinate with Montana CBFWA representatives in the process 


and assure a valuable product.  Volunteer to complete a pilot 


sub-basin in the process within Montana.


Objective
4
Services to Fish and Wildlife 
Task
3.
Stock Assessment Projects

Provide technical assistance to the Upper Columbia Basin and Upper Snake River Basin resident fish stock assessment projects, including a) identification of regionally consistent data exchange standards and b) Internet access to project data and other information. Specific actions will be defined in consultation with stock assessment project managers


Project
Work Element
Accomplishments, Second Quarter, FY2001

ODFW
1
Provide assistance as needed.
This task was dropped due to budget cuts.

Objective
4
Services to Fish and Wildlife 
Task
4.
Service to Other Fish and Wildlife Program Projects and Activities

In consultation with CBFWA, the Council, and BPA StreamNet will provide technical assistance and data services to select Program projects

Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Collaborate with CBFWA, NPPC, and other fish and wildlife 
Discussed possible StreamNet services with NWPPC and NMFS staffs. No 

programs in the Columbia Basin to identify and provide technical 
specific services were identified due to the slow progress of subbasin 


and other services to the Fish and Wildlife Program
planning discussions.


IDFG
1
Provide technical and other services to other FWP projects 
Coordinated with Idaho Supplementation Studies project personnel to 

occurring in IDFG. 
enhance their data management needs and facilitate the flow of data to 


StreamNet. Included development of a juvenile trapping operations 







database and adult redd count database.


Objective
4
Task
4
Fiscal Year 2001 Second Quarter 
Page 41 of 50

ODFW
1
Provide technical assistance and data services to F&W Program 
In response to a request from the NWPPC (through Regional StreamNet), 

projects as needed and adjust work plan priorities accordingly.
scoped the effort it would take to compile tagged and untagged hatchery 


release data for 1999 and 2000 and planned releases for 2001.


ODFW
2
Produce pre- and post-season harvest and stock status reports 
Continued progress on reformatting State Report and Recreational 

for Columbia River fish runs and fisheries and make reports 
Fisheries report for inclusion in the web site


available via either via the StreamNet site directly or via the 


ODFW Columbia River Management site with a link from StreamNet.


ODFW
3
Draft a summary of real-time data services that can be provided 
Began work on reorganizing current web site to better incorporate 

as well as a description of how these services differ from 
real-time data.




current data services provided in the Basin.

Region
1
Work with Fish and Wildlife Program projects throughout the
NPPC requested data on mass marking of salmon for selective fisheries.

basin to assist with providing information needed by the projects
We requested and received clarification on what data were needed.  The


and acquiring and distributing information generated by the
requested information was found to not be readily available in any regional


projects.
database and would have to be put together by the state StreamNet projects.  


We agreed to take on the request during the next quarter.

Objective
4
Services to Fish and Wildlife 
Task
5.
Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas dataset, b) archive the official version as a historic record, and c) in consultation with the Council, respond to requests for information concerning Protected Areas


Project
Work Element
Accomplishments, Second Quarter, FY2001

Region
1
Maintain the existing Protected Areas database.
Ongoing

Objective
4
Services to Fish and Wildlife 
Task
6
Basin Data Needs

StreamNet will provide information and assistance to regional reviews of data management projects and data management needs conducted by the PPC, ISRP, ISAB and other regional entities


Objective
4
Services to Fish and Wildlife 
Task   6   Basin Data Needs
SubTask
6.a
Data Management Needs

Work with regional entities to develop an analysis of regional data management needs, challenges and capabilities

Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Participate on Council advisory committees to identify data
RAAC committee agreed on key data and analyses needed to validate the 

needs and data gaps
EDT method of subbasin assessment. These data needs and activities 


were reported to the Steering Committee.


Objective
4
SubTask  6.a
Fiscal Year 2001 Second Quarter 
Page 42 of 50

MFWP
1
Provide review of any and all regional data management issues
Attended StreamNet Steering Committee meeting where this topic was 

discussed.


ODFW
1
Assist as needed with identifying data needs of the amended
Reviewed and commented on a few drafts of a project proposal to compile

 Fish and Wildlife Program
all fish related data in the Willamette Basin to support and populate NMFS's 


Viable Salmon Population analysis.


Region
1
Encourage and work with regional entities to respond to the 
No specific actions have come out of the ISRP review.  During the quarter 

recommendations made by the ISRP database project review.  
we participated in a Regional Data Management Committee meeting in 


Assist with efforts to standardize data collection methods and 
hopes of contributing to a regional discussion of information management 


develop regional data priorities.
needs and approaches.  No specific actions were taken pending agreement


on committee organization and direction between the Council and NMFS.


WDFW
1
Participate in regional discussions of data needs and data 
1)  O'Connor briefly reviewed the historic fish distribution database for 

management strategies in support of the newly amended Fish
Washington state compiled by The Nature Conservancy and advised that 


and Wildlife Program.
StreamNet provide a link to the TNC site for data access, rather than trying 


to incorporate these data into the current StreamNet distribution dataset.


2)  O'Connor responded to several requests from NPPC consultant Drew 


Parkin, including providing copies of SaSI stock status documents and 


stock delineation definitions, providing follow-up comments on his 


assessment of subbasin GIS activities, and attending a Washington 


coordination meeting in Olympia with staff from the EDT Project, NPPC, 


NMFS, and Washington's Salmon/Watershed Information Manager, to 


describe the StreamNet and WDFW contributions to these efforts.


3)  O'Connor participated in a conference call to discuss progress and 


futures of the Regional Data Management Committee, an effort co-led by 


NMFS and the NPPC.


Objective
4
Services to Fish and Wildlife 
Task   6   Basin Data Needs
SubTask
6.b
Data Needs Workshop

Promote organization of a regional 'data needs workshop' to establish regional data / information needs and priorities and to develop recommendations for roles and responsibilities for acquiring and providing the needed data / information


Project
Work Element
Accomplishments, Second Quarter, FY2001

All




No effort was directed toward this subtask this quarter.

Objective
4
SubTask  6.b
Fiscal Year 2001 Second Quarter 
Page 43 of 50
Objective 
5  Project Management / Coordination

Provide effective leadership that ensures the production of high quality products targeted at critical applications and the development of these products in a timely, cost-effective manner.


Objective
5
Project Management / Coordination
Task
1.
Manage Project Activities

Administer all aspects of the project at the regional and sub-contractor levels, including oversight of budget, personnel, work statement preparation and implementation, coordination among participating agencies, active participation in steering committee work, and project reporting


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Provide normal supervision of StreamNet Library staff and the 
Normal supervision of staff was provided as required.

CRITFC database Programmer.


CRITFC
2
Produce quarterly reports within 1 month after the end of each 
Report was delayed.



Quarter

CRITFC
4
Participate in Steering Committee meetings
One Steering Committee meeting was attended this quarter.

CRITFC
5
Collaborate on developing a final detailed Statement of Work for 
Adjusted CRITFC budget to restore some of the funds cut by the Council.

the current contract and for the coming year


FWS
1
Represent FWS in Steering Committee meetings
Attended March Steering Committee meeting in Olympia

FWS
2
Produce quarterly reports w/in 30 days of quarter end
Submitted Q1 activity report


IDFG
1
Participate in Steering Committee activities. Manage all aspects
Conducted all parts of StreamNet management for IDFG, including progress

of StreamNet in IDFG, including budget, personnel, and work 
reports, budget management, work management, and supervision.


management. Products will include:  Annual IDFG StreamNet 


work statement; Quarterly and annual reports of progress; and, 


Participation in Steering Committee activities.


MFWP
1
Administer all aspects of the project for Montana, including 
Received additional funding for FY01.  Did necessary paper work 

oversight of budget, personnel, work statement preparation and 
preparation


implementation, coordination, and project reporting. Participate 



in Steering Committee.


Objective
5
Task
1
Fiscal Year 2001 Second Quarter 
Page 44 of 50

ODFW
1
Administer all aspects of the project for Oregon, including budget 
1)  Attended the NWPPC meeting in support of restoring StreamNet's 

oversight, personnel, staff work plans, project implementation
budget to full funding.


and coordination, Steering Committee and technical issues
2)  Regarding the hiring of our database manager: resubmitted the DBM 


meeting attendance.
announcement to personnel for posting, drafted and submitted a 


newspaper ad, drafted and submitted a Monster.com ad, reviewed the 12 


DBM applications that came in - identified 5 to interview, contacted 


applicants and scheduled DBM interviews.


3)  Attended the StreamNet Steering Committee meeting in Quakeville 


(Olympia), WA.


4)  Held a meeting with ODFW Headquarters staff to negotiate moving the 


library to a larger, more suitable location.


ODFW
2
Participate/attend appropriate training and conferences in order
1)  Two staff attended a 5-day Visual Basic (VBA) training course.

to enhance technical skills which are relevant to StreamNet's 
2)  One staff member worked through a Visual Basic training manual to


mission.
 become more familiar with database development.


3)  Two staff attended the OSU Forestry department's Arc 8.0 training class.


4)  One staff completed the on-line ArcView training course through ESRI.


5)  Two staff attended the OSU lecture, "Estimating species extent: surveys,


sampling, and semantics."


6)  Two staff participated in a review of Jim Lannan's comparison of genetics


in wild and hatchery fish.


7)  One staff attended the first and third of eight 21st Century Government


training sessions. Second session was missed due to a schedule conflict.

ODFW
3
Produce and provide a Statement of Work, budget proposal, 
Submitted the 2000-4 Oregon StreamNet quarterly report to Regional 

quarterly reports, and annual report for Oregon.
StreamNet.


Region
1
Provide oversight for the StreamNet Program
Normal program administration continued during the quarter.

Region
2
Supervise StreamNet regional staff.  Provide training
1)  Routine supervision of project staff continued.

opportunities for project staff to further their technical
2)  The Regional Fisheries Biologist continued with self-directed Visual 


development and capabilities.
Basic training.  He also attended the annual meeting of the Oregon Chapter 


of the American Fisheries Society, where sessions on the biology of 


coastal cutthroat and redband trout, and habitat/watershed restoration 


were presented.


3)  PSMFC staff participated in a Leadership Development Workshop.


Region
3
Develop program budgets and manage / monitor expenditures
Work continued on getting a cost of living adjustment added to the FY2001 

budget.  The budget had been approved with no increase at all, resulting in 


several staff members having to conduct work on outside contracts, 


leading to deferral of some project tasks.  The NPPC finally approved a 5% 


cost of living adjustment for the project.


Objective
5
Task
1.
Fiscal Year 2001 Second Quarter 
Page 45 of 50

Region
6
Coordinate with regional management agencies / entities and
Attended an open house for the habitat projects being conducted by the 

data using entities to determine information and data service
NMFS Northwest Science Center.  Discussed the inventory of redd count 


needs and to assure rapid response to reasonable data and
data available in StreamNet with members of the Salmon Watershed 


information needs.
Assessment and Monitoring project.


Region
7
Produce quarterly reports within 1 month after the end of each 
1)  Work continued on the FY2000 report database.  A quarterly report 

quarter
template was produced and the Third Quarter report was completed and 


submitted.  The Fourth Quarter report was nearly complete at the end of 


the quarter.


2.  A database was created for tracking all user requests.  This database 


provides a central location for storing information on the types of users 


seeking help, the help they are seeking, and how we were able to help 


them.  This database should help in the timely production of our quarterly 


and annual reports.


Region
8
Produce final report within 2 months of the end of the contract 
Work continued on the Fiscal Year 2000 annual report.

period


Region
9
Manage and serve the StreamNet Steering Committee through:  
The spring quarterly meeting was held in Olympia on March 1 and 2.  All 

Organizing and conducting committee meetings at least quarterly; 
PSMFC staff participated in the meeting.


Calling additional meetings as needed to address timely issues; 


and, Actively consulting with Steering Committee on program 


activities

WDFW
1
The WDFW StreamNet state coordinator will participate in all 
1)  Lensegrav and Smith attended employee orientation in February. Sikora 

Steering Committee and StreamNet Project management
responded to WDFW's Personnel issues about her job duties and 


activities. The state coordinator and the state data manager will
classification (CQ). She also attended two days of WDFW supervisor 


jointly manage all aspects of StreamNet in WDFW, including
training in March.


budget, personnel, work scheduling, and product delivery. 
2)  In February, Lensegrav inherited a newer PC to accommodate the bulky


GIS tools he uses. Late in March, he finally resolved all the configuration 


issues to access the GIS tools.


3)  O'Connor and Sikora attended WDFW's February and March DMAD 


meetings.


4)  O'Connor and Sikora hosted the March 1 and 2, 2001 SC meeting in 


Olympia. O'Connor provided input on re-arranging the agenda for Day 1 


discussions, to link similar topics more closely. At the meeting, O'Connor 


provided project updates on administrative aspects, while Sikora and 


Woodard provided data updates. Brief follow-up assignments were 


completed within three weeks. There are still some outstanding data issues


that have not moved toward resolution.5)  O'Connor finalized and submitted


FY2000 fourth quarter and final (annual) reports to Bruce Schmidt.


Objective
5
Task
1.
Fiscal Year 2001 Second Quarter 
Page 46 of 50

5)  O'Connor drafted two versions of work statements and budgets for 


FY2001 in response to changes in available BPA funds and a new WDFW 


ruling about using BOTH overhead rates when state rates change in the 


middle of a contract period. Based on Woodard and Sikora's input, 


O'Connor finalized WDFW's March 26, 2001 buy back plan for work cut 


from our Statement of Work due to budget cuts effective earlier this fiscal 


year. O'Connor and Sikora developed a harvest data proposal to use 


potential new money (not the potential new habitat restoration money). One


final round of budget and work statement adjustments was due to be 


completed in Q3.


Objective
5
Project Management / Coordination
Task
2.
Participate in Fish and Wildlife Program Development Activities

Organize, facilitate, and/or participate in appropriate coordination meetings with BPA, CBFWA, the Council, ESA officials, ISAB/ISRP, and/or staff and management of participating organizations aimed at identifying ways that StreamNet might more effectively contribute to the Fish and Wildlife Program (FWP). Participate in advisory groups, task forces, and other groups whose purpose is enhancing the effectiveness of the Fish and Wildlife Program and its data development activities.


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Participate in appropriate coordination meetings with BPA, 
Discussions regarding StreamNet role under the Fish and Wildlife program 

CBFWA, the Council, ESA officials, ISAB/ISRP, and/or staff and 
continued with NWPPC staff and contractors and with the RAAC group. 


management of participating organizations aimed at identifying 
These issues are moving slowly and no specific conclusions were reached,


ways that StreamNet might more effectively contribute to the
although Council staff still sees a limited role for the project.


Fish and Wildlife Program.


CRITFC
2
Where appropriate, participate in advisory groups, task forces, 
Approximately 6 formal and informal meetings of the above groups were 

and other groups whose purpose is enhancing the effectiveness 
held this quarter.


of the Fish and Wildlife Program and its data development 


activities, with particular emphasis on subbasin planning and 


R/M/E issues.


MFWP
1
Participate in appropriate coordination meetings with BPA, 
Participated in the quarterly Steering Committee meeting.

CBFWA, the Council, ESA officials, ISAB/ISRP, and/or staff 


and management of participating organizations aimed at 


identifying ways that StreamNet might more effectively 


contribute to the Fish and Wildlife Program.


ODFW
1
Participate in activities aimed at identifying ways that StreamNet 
Received and reviewed the Plan for Plan Work Group members list and 

might more effectively contribute to the Fish and Wildlife Program, action notes from CBFWA's Regional Data Management Committee 


including participation in Fish and Wildlife Program advisory 
January 10, 2001 meeting.


groups and applicable regional policy, planning, and 


management forums.


Objective
5
Task
2.
Fiscal Year 2001 Second Quarter 
Page 47 of 50

Region
1
Participate in appropriate coordination meetings with BPA, 
StreamNet participated in a BPA staff meeting, presenting an overview of 

CBFWA, the Council, ESA officials, ISAB / ISRP, and/or staff
the project, its capabilities and function, and the kinds of data that are 


and management of participating organizations aimed at
available.  StreamNet also participated in meetings of the Regional Data 


identifying ways that StreamNet might most effectively
Management Committee in order to contribute recommendations based on 


contribute data / information and support to the FWP. 
experience with data management and to determine how StreamNet can 


best contribute to the regional data management efforts.


WDFW
1
No specific work planned; available as needed for coordination 
O'Connor attended the Council Fish and Wildlife Committee's meeting on 

(see related work under Tasks 1.6, 2.2, 2.7, 4.2a, 4.7a).
January 16 to become familiar with this process and to be available for any


questions following Bruce Schmidt's StreamNet presentation. In March, 


O'Connor met with Brian Walsh and Council co-chair Larry Cassidy for a 


follow-up meeting to discuss StreamNet key role in Columbia Basin data 


management, following a detailed StreamNet presentation given at PSMFC 



by Bruce Schmidt.

 Objective   5    Project Management / Coordination
Task
3.
Coordinate with Other Related Activities

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities to identify means for collaborative data collection, storage, and dissemination. Collaborative data activities will target tribal fishery programs within the Columbia Basin, federal land managers’fishery programs, state fish and wildlife agencies, and, with respect to water use and stream development, state water resource management agencies. Collaboration with coast-wide and private data collection/compilation efforts will be pursued when this supports overall project goals. Areas of particular emphasis are 1) participation in Fish and Wildlife Program monitoring and evaluation activities, and 2) exploring opportunities for integration of StreamNet data exchange formats into Fish and Wildlife Program contract terms and conditions.


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Seek closer cooperation, coordination, and consistency of 
No activity this quarter. It is most likely that coordination of information 

information management practices and standards between 
management across programs (e.g. the Power Act, Forest Service, and 


salmon restoration programs in the Columbia Basin (e.g. 
LSRCP) will surface during subbasin planning in the second half of this 


Mid-Columbia PUD's, LSRCP) by participating on appropriate
fiscal year.


work groups.


MFWP
1
Maintain communication, help coordinate activities with Montana 
Ongoing.

Department of Natural Resources, Department of Environmental 


Quality and the Natural Resource Information System as they 


relate to StreamNet activities.  Participate in appropriate 


conferences by preparing papers and giving presentations. 


ODFW
1
Establish / maintain working relationships with data collection 
1)  Reviewed NMFS's  Info. Sys. Development Plan for the Columbia.

projects within and outside ODFW to promote efficient and 
2)  Reviewed and commented on HB 2675 and the potential changes to 


beneficial data sharing.
Essential Salmonid Habitat guidelines that it might cause.


Objective
5
Task  3.

Fiscal Year 2001 Second Quarter 
Page 48 of 50


Region
1
Coordinate the efforts of the StreamNet project with other data
1)  Personnel from the Nez Perce Tribe contacted StreamNet and 

compilation projects occurring in the region.  Address issues
subsequently met with the Regional Fisheries Biologist.  The Nez Perce are 


of data gaps, duplication of effort, data set integration, 
beginning a formal habitat restoration program, and they expressed a 


georeferencing standardization, scientific rigor, management 
desire to collect and manage their data in a manner that would make it 


needs, etc.
widely available and useful.  StreamNet personnel discussed basic 


database management concepts, showed them how they could store data 


in StreamNet format by using existing StreamNet databases and tools, and 


put them in touch with Hilary Forrest, CRITFC StreamNet programmer, to 


manage codes that the Nez Perce will need to use for data entry.  


StreamNet personnel from PSMFC and CRITFC also helped the Nez Perce 


Tribe personnel in getting Microsoft Access running on their computers.


2)  Responded affirmatively to a question from NPPC whether we could 


assist the  NMFS SWAM project by hiring a statistician for them on Council 


funding through the StreamNet project.


WDFW
1
Maintain working contact with Washington Hydro Framework 
O'Connor drafted some ideas for out-of-Basin data development activities, 

partners and USGS Regional Ecosystem Office staff to promote 
including analysis of connections to current StreamNet Basin-related work,


effective sharing of hydrology base layers and attached fish and 
for future funding scenarios.


habitat data.


Objective
5
Project Management / Coordination
Task
4
Prepare Public Information Materials.

As needed, produce public information materials including updated versions of the project brochure, computer demonstration materials, and/or other appropriate materials


Objective
5
Project Management / Coordination
Task   4   Prepare Public Information Materials.
SubTask
4.a
Prepare Public Information Materials

As needed, produce public information materials including updated versions of the project brochure, computer demonstration materials, and/or other appropriate materials


Project
Work Element
Accomplishments, Second Quarter, FY2001

CRITFC
1
Produce and update a Library brochure and Access guide listing 
Migrated library brochure and access information to the website.  Brochure

services, hours and cost recovery fees.
is printed on an as-needed basis.


MFWP
1
Montana will participate in review and recommendations.

ODFW
1
Write informational articles on StreamNet data activities for
1)  Bourne, Bowers, Brodeur, Cooney, and Hurn attended the ODFW 

natural resource oriented publications and give oral
Habitat Division Retreat - we shared information about StreamNet efforts 


presentations to relevant user groups.
and obtained a better idea of ODFW's information management needs.


2)  Prepared and gave a presentation on the ODFW Riparian Lands Tax 



Incentive Program Database.


Objective
5
SubTask  4.a
Fiscal Year 2001 Second Quarter 
Page 49 of 50

Region
1
Update the existing StreamNet brochure
The StreamNet brochure was updated during this quarter with new 

information, graphics, and layout.  Copies were made for distribution, and 


the new brochure is now distributed to interested parties.  It was also 


made available from the StreamNet web site.


Region
3
Create a demonstration of the data and services available by 
A slide show presentation of StreamNet's purpose, history, methodologies,

StreamNet.  Update this presentation as necessary.  Materials 
and ways to obtain StreamNet data was created and presented to the 


developed will be for presentations covering the data and 
Bonneville Power Administration's Fish and Wildlife and NEPA groups on 


services provided by StreamNet, and how to use the StreamNet 
March 20 at BPA's office.  The presentation was slightly modified and 


web site to obtain data.
presented to NWPPC Chairman Larry Cassidy and staff member Brian 


Walsh at PSMFC on March 28.  The March 28 demonstration was 


conducted with a live hookup to the online database.


Objective
5
Project Management / Coordination
Task   4   Prepare Public Information Materials.

SubTask
4.b
Participate in informational meetings/conferences

Participate in appropriate state, regional, and national educational and professional conferences, including, where applicable, giving presentations, preparing poster session materials, and contributing to conference proceedings.


Project
Work Element
Accomplishments, Second Quarter, FY2001

IDFG
2
Serve as chairman and organizer for the 2001 ArcInfo User's 
Continued work on 2001 Northwest GIS User Group Conference.

Group Conference scheduled for October 2001.


ODFW
1
Participate in appropriate meetings & conferences as 
Attend the Multi-state Aquatic Resources Information System (MARIS) 

opportunities arise to highlight StreamNet programs & data
meeting.  MARIS has primarily focused on Great Lake data, but they are 


now interested in branching out to stream level data and possibly linking 


with StreamNet in the PNW.


WDFW
1
Participate as opportunities arise to highlight StreamNet
Late January, Lensegrav manned a WDFW information booth at the 

programs & data
Western Washington Sportsman's show to enhance awareness about 



StreamNet and WDFW's agenda.


Objective
5
SubTask  4.b
Fiscal Year 2001 Second Quarter 
Page 50 of 50
_1068885008.doc
[image: image1.png]






