[image: image1.wmf]
StreamNet Project
BPA Project No.  198810804

Fiscal Year 2002
First Quarter Progress Report
October 1, 2001 through December 31, 2001

Bruce Schmidt
Pacific States Marine Fisheries Commission

Cooperators
Phil Roger, Columbia River Intertribal Fish Commission
Bart Butterfield, Idaho Department of Fish and Game

Janet Hess-Herbert, Montana Fish Wildlife and Parks

Cedric Cooney, Oregon Department of Fish and Wildlife

Steve Pastor, U.S. Fish and Wildlife Service

Dick O'Connor, Washington Department of Fish and Wildlife

Table of Contents


Introduction…………………………………………………………….
  2

Objective 1.  Data Development and Update, Priority Data Sets…...
  6

Objective 2.  Data Development and Update, Other Data Sets……..
15

Objective 3.  Data Management and Delivery……………………….
24

Objective 4.  Library / Reference Services…………………………...
42

Objective 5.  Services to Fish and Wildlife Program Activities……..
46

Objective 6.  Project Management / Coordination…………………..
50


Introduction
StreamNet is a cooperative, multi-agency data compilation and data management project authorized by the Northwest Power 
Planning Council’s Fish and Wildlife Program (FWP) and is funded primarily by the Bonneville Power Administration.  The project is administered by the Pacific States Marine Fisheries Commission.  Three fourths of the project consists of sub-projects within the state fish and wildlife agencies, Columbia River Intertribal Fish Commission and the US Fish and Wildlife Service to develop databases within the respective agencies and facilitate data transfer regionally. 

The StreamNet Project compiles, manages and distributes information related to fish resources in the Columbia River basin, with additional information available for the rest of the Pacific Northwest.  The state, tribal and federal fish and wildlife 
agencies collect and utilize data related to the region’s fish and wildlife resources to meet their own mandates.  A subset of these data, primarily the annually collected types of information that are routinely used to monitor trends within fisheries and populations and provide management information, are compiled by StreamNet into regionally standardized formats and publicly distributed.  In this manner, data common to fisheries management but collected and stored in multiple formats by the individual agencies are standardized and made uniformly available basin wide.  StreamNet also ties all data to the regional 1:100,000 scale routed hydrography (GIS stream network) so that different kinds of data can be compared on a geographic basis and mapped.  The project utilizes the Internet as its primary means of data distribution, but also provides custom data services to FWP participants.  The StreamNet web site provides access to information in a queriable database and also provides maps, individual data sets not contained in the queriable database, and library references.  All data in the StreamNet database 
are referenced to source documents that are housed in the StreamNet Library.


Introduction


6/24/02
Page 2 of 58
Work priorities for FY 2002 include updating existing long term data sets, managing the data and infrastructure necessary to maintain and deliver data, maintaining the StreamNet Library, providing data services to regional entities associated with the Fish and Wildlife Program, and project administration.  This year the distinction between anadromous and resident fish data in the data development objectives was dropped, and the annual statement of work was reorganized to reflect that change in approach .  This year, the agencies indicate in each individual job whether the work is directed toward anadromous or resident species for each particular data type.  This change is a change in organization, not project direction.  The majority of work remains focused on anadromous species due to the sport and economic value of these species and because of associated Endangered Species Act aspects.  However, efforts are also underway to develop increased information on resident species distribution, and increased effort is directed toward identifying resident species information that may be developed by other projects funded through the FWP and obtaining those data for archiving so that they are more widely available.

This report documents accomplishments made by the project and its cooperators during the first quarter of Fiscal Year (FY) 2002.  Since the cooperating agencies work on different jobs throughout the year, and not all agencies address the same jobs in their respective portions of the Work Statement, the work accomplished in this quarter varies by cooperator.  Tasks and jobs that did not have any work addressed during the quarter are not included in this report. Activities in the First Quarter of FY 2002 included routine development, maintenance and posting of various data sets, as well as routine administrative activities to continue project function.  Key highlights of activities this quarter are presented by cooperator, as follows:

CRITFC

1. Normal library services were maintained and expanded at the StreamNet Library.  Usage continues a steady increase and this was accommodated with existing staff and resources.  Library space is becoming a growing concern and is a limit to providing additional services.  

2. A new high-speed scanner has been integrated into the library at no additional cost to the project.  CRITFC acquired the scanner with its own funds and staff were trained in its use.  Key documents are being scanned and added to the web site as time permits.  

3. A prototype genetics data catalog was developed and presented for Steering Committee consideration.  

4. The Steering Committee member has been actively representing the project as the Council proceeds through its Provincial Review process and develops its strategy for subbasin planning.  This has involved a sometimes intense set of meetings and discussions. Regular updates were provided for the Steering Committee.

IDFG

1.  Using outside funding, we completed an updated the database of bull trout survey data for the Clearwater and Salmon River basins.  Two major data sources, the General Parr Monitoring and the Salmon Region's stream survey database were combined into a single database for the US Fish and Wildlife Service.  The data were formatted for inclusion into the StreamNet data.  In addition, the Salmon Region now uses the StreamNet stream referencing system (LLID and measures) for their database, easing the future addition of data into StreamNet.


Introduction


6/24/02
Page 3 of 58
2.  After noticing some anomalies in existing data, we began a thorough review of hatchery return and redd count datasets.  Included are a check on survey locations and verifying data entry with original sources. We completed the hatchery returns for1961 through 1999 and several years of redd count data.

3.  We have developed a set of ArcView tools for IDFG biologists to use for referencing their data to the StreamNet 100K hydrography.  The tools were installed in the IDFG Fisheries Bureau and several regional offices.  By creating such tools, IDFG biologists find it easier to record data in formats more easily migrated to StreamNet.

4.  Using funds supplied by IDFG, we began to purchase hardware and software to develop a modern information system for fish and wildlife data.  Built upon StreamNet data formats, this information system will be the central storage location for IDFG fishery data.  It will include automated tools for converting that data into StreamNet data exchange formats.

MFWP

1.  The project has begun collection of 2000-2001 distribution and survey data from MFWP biologists, and we continued to input the information into the database.  

2.  We completed and exchanged Dams, Hatchery Facility and Protected Areas databases to StreamNet regional staff.  Work continued on Barriers data. 

3. The MFWP genetics database was sent to the CRITFC StreamNet Project as we move toward developing a DEF for this type of data.   

4.  We accomplished normal project activities, including attendance and participation in the StreamNet Steering Committee meeting in Seattle, where the Distribution and Use DEF was successfully discussed.


ODFW

1. Using StreamNet funds, we continued to develop distribution data for cutthroat trout in the Hood basin at the 1:100,000 and 1:24,000 scale. Efforts were also made to acquire and combine cutthroat related information from other areas in order to build a ‘first-cut’ cutthroat distribution layer for the Oregon portion of the Columbia basin.

2. Using funding provided by the Governor’s Natural Resources Office and Oregon Watershed Enhancement Board, we continued to update 1:100,000 scale fish habitat distribution data in the entire anadromous zone of Oregon, and also to develop fish habitat distribution data at the 1:24,000 scale for this same area. This effort will greatly improve the accuracy of StreamNet’s fish distribution data.

3. A significant amount of time was spent updating the locational information related to Oregon hatchery facilities, as well as adding new records that previously did not exist in the database.

4. We developed and populated a life-stage timing database structure.

5. We provided significant data and technical support to the Willamette/Lower Columbia Technical Recovery Team by completing the development of a TRT-focused data system and populating that system with existing StreamNet data and new information that was acquired directly from data developers.

Objective
1
Task:
1
6/24/02
Page 4 of 58
6.  We accomplished normal project activities, including completion of quarterly reports, FY-2002 budget and Statement of Work documents, attendance and participation in the StreamNet Steering Committee meeting in Seattle, and reviewing and commenting on Data Exchange Format related issues.
USFWS

The smallest component of the StreamNet Project, FWS activities centered around routine work, including obtaining and entering fall release information from Warm Springs NFH and participating in the quarterly Steering Committee meeting.

WDFW

1.  WDFW StreamNet staff used additional funding from EPA to generate standard metadata for the statewide bull trout distribution/use database, as well as to begin to build basic capability for spatially-enabling field sampling points to allow incorporation of fish survey data, particularly for resident fish.  Our salmonid spawner survey field data from the Lower Columbia River is hampered by the use of non-standard location identifiers. We are working to build the capability to easily generate LLIDs and measures (Begin/End points) for each of these locations so that these data can be spatially referenced in our GIS and to facilitate the process of conversion to StreamNet exchange format.

2.  We also spent considerable time working the “people” side of the data delivery pathway. Upon request, our Vancouver office staff “adopted” a key database of wild juvenile and adult migrant data from the Cedar Creek watershed. This database was suffering from lack of standard data values and delays in updates. In addition, there was a sharp increase in requests from other WDFW staff for help in operating software, running database routines, etc. We find that our investments in building and maintaining data flow infrastructure always pay off, both in better and more timely data, and in the positive relationships that are built. Such relationships are key to getting our future needs addressed as a high priority by grateful field staff.

Region (PSMFC)

In addition to routine and ongoing work to keep the project functioning and current, significant progress was made in the first quarter toward upgrading the online data query system.  Greg Wilke, project programmer, came on board at the end of the last quarter of the previous year.  This quarter he began an intensive process to learn the existing system in preparation for his taking over maintenance and improvement of the system.  Greg worked closely with Doug Reece, the contract programmer responsible for development of the system, and rapidly learned the program and began making corrections and improvements.  Other key accomplishments include conclusion of the project to provide information on mass adipose marking of hatchery salmon and steelhead as requested by the Power Planning Council, and revision of the work statement to improve organization and prioritization of work.


Objective
1
Task:
1
6/24/02
Page 5 of 58

Objective
1
Data Development and Updates, Priority Data sets

Support the need for region wide fisheries data for research, monitoring, modeling, and management through acquisition and regional standardization of new information and updates to previous information for priority fishery data types.  These priority data types will be addressed by all data providing agencies, or for specific data types by a single cooperating agency on behalf of the entire project.  This Objective addresses both anadromous and resident fish species, although priorities may differ.


Objective
1
Data Development and Updates, Priority Data sets

Task
1
Distribution and life history (use type)

Document the occurrence, distribution and life history characteristics of native fish species, both resident and anadromous.  Project

participants have placed a high priority on updating these data during the fiscal year, utilizing newly re-defined use types.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Compile available IDFG data on fish distribution into the 
1. Data continued to be entered into the Fish Information System (FIS). 

IDFG/StreamNet Fish Information System. These data will 
The FIS was built in a collaborative effort between  IDFG/StreamNet and 

come primarily from Collecting Permit reports and IDFG 
IDFG fish biologists to facilitate data compilation and exchange with the 

files being digitized via a BLM Challenge Cost Share grant. 
regional StreamNet database. The data being entered came from two 

Both of these data entry efforts are independent of 
primary projects. The first is an ongoing effort to enter historical fish 

StreamNet. Other data will be collected from incidental 
collecting reports. The second is a project to compile historical data from

observations in other tasks. Convert these data into 
IDFG regional offices. Some of these data are electronic and some are 

StreamNet data exchange format and send to PSMFC as they 
paper. Both projects are funded outside StreamNet.

become available.
2. The IDFG/StreamNet program received funding from USFWS for 1 

month of our data manager to compile bull trout data from the IDFG 

Salmon and Clearwater regional offices. The data were combined with data

already in the FIS to provide an updated picture of bull trout distribution, 

survey sites, and relative abundance in the two drainages.

3. Using the Spawning Ground database developed by IDFG/StreamNet and

the Idaho Supplementation Studies (ISS), fish biologists added incidental 

fish species from juvenile trap data into the FIS.

MFWP
1
 Complete Distribution and Use Types dataset from data 
Work is ongoing; we will exchange these data next quarter.

collected from biologists, documents and reports during 

1999-2000 using LLID stream routes.  Exchange the data to 

the StreamNet database in the approved DEF format.

MFWP
2
Visit MFWP biologists in 2002 to collect 2000-2001 fish 
Work is ongoing.  We met with southwestern Montana biologists in 

distribution and supporting survey data and references.  
December, and will schedule the rest of the state next quarter.

Obtain data from federal biologists using our developed 

interface.  Input all this information into the MRIS tables.


Objective
1
Task:
1
6/24/02
Page 6 of 58

ODFW
1
Update, maintain, correct and exchange anadromous and 
1.  Jon processed the latest version of our Fish Presence Survey data into 

resident fish distribution information (DistUse and 
GIS format with the intention of gleaning out the cutthroat observation 

DistPresence tables).  Efforts will focus particularly in the 
data. He was able to identify 23 points that were located beyond Oregon's 

Upper portion of the basin (NE Region, upstream of the 
borders and 96 records that fell within a particular HUC that did not have 

Hood River basin).
matching HUC coding. The information was provided back to our data 

entry person for further evaluation and correction.  We're holding off for 

now on using this for cutthroat documentation until errors are corrected.

2.  Jon initiated work on Coastal Cutthroat distribution data development 

in the Willamette and Lower Columbia basins. He assembled data from 

past distribution data development efforts (WDESH I and II, Aquatic 

Inventory Project, ODF Fish Protection Watershed data, the Fish 

Presence Survey database, Mt. Hood National Forest, BLM Salem and 

Eugene districts and the Incidental Fish Observation database). He began 

processing the data into a compatible format and developed an order of 

precedence and a draft approach for converting it into a comprehensive 

linear distribution for this area. Data development is focusing on 

developing documentation (DistPres) data since it will drive the 

development of the distribution data.  Through both automated and 

manual means, he was able to convert Mt. Hood National Forest, 

BLM-Salem, and BLM-Eugene District GIS data into StreamNet 

compatible documentation format. 

3.  Jon created Reference Memo's, organized Reference Metadata and 

assigned RefID's for Mt. Hood National Forest, and Salem and Eugene 

district BLM GIS data containing fish distribution information.   He also 

acquired a Reference document for a steelhead survey conducted on the 

Illinois River.

4.  We synchronized a replicate copy of the distribution database with the 

Design Master, which incorporated twelve new 100K records, primarily in

the Clackamas and Sandy basins.

5.  Jon compiled Baseline97, 1:24,000 scale DLG hydrography in 

preparation for developing an initial, "presumed" coastal cutthroat 

distribution dataset. Since these data are not comprehensive, Jon is still 

working to track down additional hydrography data to completely meet 

our needs for this project.

6.  Jon reviewed existing cutthroat data to evaluate whether it should be 

included in the Distribution database.

7.  Jennifer used the Data Capture Tool to enter Coastal Cutthroat data 

for the Hood area (Scott Canyon HUC).  Additionally, she (re-) entered 

some cutthroat data that was displayed on the original maps and approved

by Hood biologists, but was not contained in the distribution database.

Objective
1
Task:
1
6/24/02
Page 7 of 58

ODFW
2
Update (and modify if needed) the Fish Presence Survey 
1.  Stacy entered fish presence survey data for the South Willamette 

database which helps populate the DistPresence table.  These 
Watershed District during this quarter. As of 12/17/2002, we have 6,067 

data will update the distribution data developed under Task 
records in the Fish Presence Survey database.

1.1.
2.  Jon processed the most recent replicate copy of the FPS database in 

order to derive cutthroat documentation data.

3.  Bill began work on the Fish Presence database to enhance the User 

Interface based on suggestions giving to him by previous data entry staff.

WDFW
1
Incorporate field updates for Washington fish distribution and
1.  Using a series of queries, Sikora generated a list of suspect Bull Trout 

use data (when provided) into WDFW's GIS database, with 
distribution data split into more than one record without obvious cause or 

emphasis on bull trout and other sensitive salmonids this 
realistic begin points.  O'Connor, Sikora, Hudson and Burns met October 

year. Update tabular files via export from the GIS database. 
12 to discuss the expectations and realities of how the spatially generated 

Convert spatial and tabular data to new StreamNet exchange 
data would output as tabular data.  A few issues were fixed directly in the 

formats and submit to PSMFC.
spatial data.  The others must be corrected in the tabular output just 

before it is sent to StreamNet because we do not have the manpower to 

revise the spatial program at this time.  Following the meeting, Sikora 

tested her queries against the issues revealed using David Grave's 

EventCompare tool.  The queries and the EventCompare tool caught 

many of the same errors but each maneuver caught one thing that the 

other did not.  When the data exchange format (DEF) is finalized we will 

work out the combination of maneuvers that is needed to fully proof and 

correct the data before exchange.  To insure our input for the DEF stays 

on track, Sikora also created a cross-reference table showing the expected 

draft StreamNet code translation of WDFW's existing presence and 

usetype code combinations.

2.  Sikora researched StreamNet's current snapshot of WDFW salmon 

distribution data after a user questioned the validity of the data since the 

hydrolayer portrays stream names contrary to local names.  The data was 

created by looking at stream orientation on a map (not by names), so 

Sikora and Banach were able to assure the user that the distribution data 

was correct.

3. O'Connor and Lensegrav did preliminary work to spatially enable 

resident fish stream sampling data from the Yakima Basin (Ecological 

Interactions Team data).  Data originally entered into ArcView was 

proofed and prepared for conversion into data records with 100K LLID 

codes and Begin/End measures as appropriate. The tools and procedures 

under development will help us convert other resident fish datasets into 

StreamNet formats, once the new FishSurvey DEF is complete.

Objective
1
Task:
2
6/24/02
Page 8 of 58

Objective
1
Data Development and Updates, Priority Data sets

Task
2
Adult abundance in the wild

Develop and maintain information on adult abundance for native fish species, resident and anadromous, including escapement,

redd counts, peak spawner counts, trap counts and dam and weir counts.  Also included in this data category are data gathered

during spawning ground surveys regarding straying of hatchery fish onto spawning areas, i.e., marked/unmarked ratio.

Priority is given to updating these data through 2000.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Update existing tribal escapement data through 2001
Existing adult abundance trends were updated through 2000.

CRITFC
2
Update mainstem Columbia and Snake River dam counts 
All mainstem dam counts were updated through 2000.

through 2001and provide updated data to the StreamNet 

database.

IDFG
1
Submit 1998, 1999, and 2000 field season redd count data.
1. We conducted a thorough visual review of 1988, 1953, and 1954 redd 

count data and transect locations in the IDFG/StreamNet database. 

Additional years will be reviewed next quarter. Corrections that we made 

included: 1) verified the transect location and count values for each 

transect, 2) corrected mislabeled species, and 3) examined the location of 

each trend over time. We found that many trends had a large variation in 

position and length over time. Such transects probably do not provide 

comparable data from year to year. We think a complete overhaul to 

trends in the Idaho redd count data is required.

2. Sockeye and steelhead redd counts were added to the database.

IDFG
2
Compile year 2001 field season redd count data and submit to
2001 field season redd count data were not yet available.

PSMFC.

MFWP
1
Complete input of 1999-2000 data, including trend, count 
Work is ongoing.

and references; exchange to StreamNet.

MFWP
2
Collect all 2000-2001 survey data during field office visits.
Work is ongoing.  We met with southwestern biologists with MFWP and 

USFS and collected existing field data, and will input the data next quarter.

MFWP
3
Input 2000-2001 data into MRIS, including trend, count and 
Work is ongoing.

references. Provide data in data exchange format to regional 

StreamNet staff if completed.

Objective
1
Task:
2
6/24/02
Page 9 of 58

ODFW
1
Update existing abundance and indices trends (escapement, 
1.  Bill and Shannon added additional fields to the queries designed last 

redd counts, trap counts, peak/other spawning counts, etc.) 
year for updating the abundance trends. As part of this update effort, they

where data collection continues for anadromous and resident 
discovered missing contact information, duplicate HUCs in the 'allstream'

species through 2000 and modify as needed to adhere to any 
table, and trends outside the Columbia Basin and coastal range which 

new data exchange standards.  Three data submissions are 
weren't being updated. They fixed the query problems, and completed 

planned.
other preparatory measures for updating trends through 2000 which will 

now allow Shannon to contact biologists for data.

2.  Shannon telephoned and e-mail 22 of the 24 contacts identified as trend data

providers. She compiled and entered trend data into the interface, from the sources

that responded to her request. Some staff actually responded on the day of the

request, but most responded a week or more after the request was made.

WDFW
1
Research, compile, convert and submit natural spawner data 
1.  Smith received the 2000 Columbia River Chum return report and 

updates (returns and/or redd counts) through 2000 (and 2001 
finished updating the escapement database for chum.  Smith also contacted

as available) for available species (Columbia River and Puget 
various regional biologists to collect escapement data needed to fill data

Sound).
gaps.  This data is being documented and added to the escapement database.

2.  Woodard was asked to take over the Cedar Creek adult and juvenile trap

database from John Weinheimer and Dan Rawding.  Woodard created an adult

and juvenile database in MS Access 2000 to store data that has been collected

back to 1998.  This data was not consistently collected or recorded from year

to year and business rules were not in place, allowing many data entry errors.  

Smith took on the job of proofing the adult data while Woodard built the storage

facility and supporting files.  Together, Woodard and Smith spent considerable

time on the Cedar Creek data. From now on they will handle the maintenance

and data entry yet this extra responsibility may save time in the long run.  After

the work progresses, the data will be added into our WDFW StreamNet

databases, summarized and delivered to PSMFC.


Objective
1
Data Development and Updates, Priority Data sets

Task
3
Hatchery releases

Develop and maintain information on the release of hatchery reared fish.  Priority is given to updating anadromous release records

using RMIS data for anadromous species through 2000.  Release data for resident species are currently low priority and will

require specific resources in the future.  Efforts this year will focus on creating cross references between PSC release codes and LLID

stream location identifiers.  We will explore means of providing data on specific release locations rather than more general PSC codes.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

FWS
1
For anadromous hatchery releases, compile FWS hatchery 
Steve received fall release information from Warm Springs NFH, and 

release data, w/ added CWT information.  Transform data to 
integrated it with other 2001 release information in CRiS.

format 032.  Submit 2001 hatchery release data to PSMFC 

via USFWS WWFRO.

Objective
1
Task:
3
6/24/02
Page 10 of 58

Region
2
Assist data contributing agencies in development of data, 
The database manager inquired about any potential availability of existing 

including formatting, coding, data entry, error checking, and 
mapping of PSC codes to the Pacific Salmon Commission's Data Standards

submitting to the regional database.
Working Group, but none appears to exist.
WDFW
1
For anadromous species, research, compile, convert and 
Hatchery releases continue to be a highly requested data category and 

submit existing WDFW anadromous release data as detailed, 
Lensegrav continued to handle these requests.

"unrolled" records directly to StreamNet (instead of via RMIS).

As warranted, organize procedures to ease future updates.


Objective
1
Data Development and Updates, Priority Data sets

Task
4
Hatchery returns

Develop and maintain information on the return, disposition and straying of adult fish returning to hatcheries, including information

on coded wire tags.  This is an anadromous related task only.  Priority will be placed on updating total return and egg take data

through 2000.  Development of disposition data is lower priority and would require additional resources.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Submit 1998, 1999, and 2000 return season hatchery return 
1. Upon inspection of our existing hatchery return data, we noted a 

data.
number of various errors. Before submitting these data to PSMFC, we need

to complete a thorough review of all of our hatchery return data,  We 

completed the review for data from 1961 through 1999. We verified and 

corrected, where necessary, all values. We made sure that each record had 





                                                                           an associated trap and hatchery. We also checked for completeness for


each hatchery and year.  This was necessary before final incorporation in 

the FIS and eventual submission to regional StreamNet. Corrections and 

updates that we performed included 1) insure each record has a valid hatchery

and trap,  2) added comments on differences found between reported totals

and calculated totals, 3) added comments on inferred or derived subtotals,


4) made changes to account for historical management changes, 5) updated

the reference information, 6) corrected mislabeled species.

2.During the review process, we added age composition data to the 

hatchery return data.

3. Incidental resident fish presence is sometimes noted at anadromous hatcheries.

When found, we also added that data to the hatchery return database.


IDFG
2
Compile year 2001 return season hatchery return data and 
2001 field season hatchery return data were not yet available.

submit to PSMFC.


Objective
1
Task:
4
6/24/02
Page 11 of 58

Region
1
Assist data contributing agencies in development of data, 
PSMFC and ODFW StreamNet personnel worked on definitions and data 

including formatting, coding, data entry, error checking, and 
needs for capturing "hatchery fraction" data.  This type of information is 

submitting to the regional database.
useful for run reconstruction to determine wild and hatchery components 

of fish returning to a dam or to spawning grounds.  ODFW is pursuing this 

type of information in support of state management needs and is hoping 

to integrate this information with that from Washington and Idaho.  We 

began the first steps toward defining data structures, brainstorming on 

where such information could be obtained, and how it might be made 

accessible via StreamNet.


WDFW
1
Research, compile, convert and submit hatchery returns 
Woodard completed the WDFW Master Hatchery database and updated it with

updates through 2000 in StreamNet data exchange format.  
2000 returns data.  All supporting tables were added and updated with StreamNet

This submission includes new data and corrects errors that 
codes.  The age database link was not added to the Master Hatchery database

were previously submitted for post-1995 data.   Work further
yet due to other priorities.  Following the November submission of the hatchery

with WDFW's Hatchery Division to improve their original 
facility database, WDFW was free to submit the returns data that is highly

database source and collection procedures as an investment in
dependent on the facility data.  After WDFW updated the dependent hatchery

future timely and accurate StreamNet updates.
facility data, Woodard summarized and submitted the returns data to Sikora.

She proofed the data and StreamNet conversion, focusing on the LLID entries.

With work that bridged into the next quarter, Sikora and Woodard swapped

more information needed for the exchange.


Objective
1
Data Development and Updates, Priority Data sets

Task
5
Dams and Fish Passage Facilities

Develop and maintain information on dam facilities.  Enhance the existing StreamNet dams data set by updating relevant data from

the Pacific Northwest Hydropower Database and Analysis System (NWHS) and the National Inventory of Dams.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Submit dam facilities table in data exchange format to 
Our work reviewing and updating the redd count and hatchery return data sets,

PSMFC.
as well as preparing the necessary interfaces took longer than anticipated.  We

were unable to prepare our dams facilities data for submission to regional 

StreamNet. This task will be accomplished later in this year.


MFWP
1
Complete the creation of a Montana dams spatial coverage 
We completed the spatial layer and the tabular data were exchanged to the

and associated data in the StreamNet exchange format.  
StreamNet database in Gladstone.

Layer and data are being created using the NWHS and the 

National Inventory of Dams.  Tasks to date include 

combining the data from the two sources; manual checking 

needs to be done before the final product is completed.  

Exchange the Dams data set to the StreamNet database.


Objective
1
Task:
5
6/24/02
Page 12 of 58

WDFW
1
StreamNet currently carries Washington dam information 
1.  Lensegrav researched the available fish passage data for Washington 

that wasn't officially exchanged by WDFW.  We will 
dams so O'Connor could respond to a general request and weight the scope

compare StreamNet's existing Washington dams data with 
of future efforts to compiling this data.

WDFW's internal dam layer and any other dam data resource 
2.  In November, Lensegrav started WDFW's effort to submit dam facility

(i.e. DOE's dams), adjust the WDFW layer accordingly and 
data by reviewing the files compiled by the Department of Ecology 

submit to StreamNet.
(DOE), StreamNet and dams already on WDFW's spatial layer.  DOE's 

dataset is more comprehensive and seemingly the most reliable overall.  

Lensegrav drafted damsevalproc.doc to outline his plan to proceed with 

efficient research and data compiling. Using Aforg.exe software, 

Lensegrav also reviewed and documented older dam files on Sikora's 

desktop.  Sikora reviewed the plan and issues and before the file clutter 

grows, it is vital to get all existing dam sites in one place, preferably 

registering the exact same site as the original source.  More progress is 

thwarted because the GIS manager does not have the time to add the DOE 

dams to WDFW's layer.

Objective
1
Data Development and Updates, Priority Data sets

Task
6
Hatchery Facilities

Develop and maintain information on anadromous and resident hatchery facilities, including information on location, design,

management and authorization.  Information will be updated through 2001 for required fields.  We will review the optional

(non-required) fields in the DEF.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Submit hatchery facilities table in data exchange format to 
Some new hatchery facilities data came to us, mostly changes in hatchery 

PSMFC.
managers. We updated our internal dataset, but because our work reviewing

and updating the redd count and hatchery return data sets, as well as 

preparing the necessary interfaces took longer than anticipated. We were 

unable to prepare our hatchery facilities data for submission to regional 

StreamNet. This task will be accomplished later in this year.


MFWP
1
Update the StreamNet hatchery database with Montana's 
We completed the spatial layer and the tabular data were exchanged to the

public and private facilities.  Exchange with StreamNet upon 
StreamNet database in Gladstone.

completion.

Objective
1
Task:
6
6/24/02
Page 13 of 58

ODFW
2
Maintain hatchery facility records and update location 
1.  Jon initiated work on Oregon's Hatchery facilities data reconciliation and update.

information as available.
He downloaded approximately one half of the state's DOQ's in SID format from the

ODF FTP site, which proved useful in our effort to more accurately identify

hatchery facility locations. Additional facility location data for rearing and

acclimation ponds as well as traps was also obtained. Jon was able to complete the

hatchery data clean-up which included the creation of coordinate data for 82

records, as well as adding 7 new records to the hatchery table.  He submitted the

data to Susan for incorporation in the new Hatchery database, then created metadata

for the new coverage, posted it on the FTP site, and updated the web links.  The

data will be provided to SN during the fourth quarter of this fiscal year.

2.  Susan and Jon collaborated to improve the Hatchery table. They agreed that for

clarity, the TYPE field should be renamed MgmtAgencyType, and the 

HATCHTYPE field should be renamed ProductionType, and they added a

FACILITYTYPE field into the table.


WDFW
1
In an on-going effort, digitize hatchery facility sites and correct
Lensegrav and Sikora continued to add or correct hatchery facility site 

existing site locations as more site information is learned.
locations based on any new information, including select sites for Yakima 

Complete, convert, and submit  Washington state hatchery
area hatchery activity.  Lensegrav assigned OutFlowTypeID codes and 

facility data (including federal and tribal facilities as available),
determined BegFt based on the October 2001 version of StreamNet's 

focusing on the location related fields per the 2001.1 format
EventMapper.  Sikora submitted the data to StreamNet on November 9, 

and facilities needed to support hatchery release and returns
2001 also directing StreamNet to purge redundant hatchery codes.

data.  As time permits, update other hatchery facility related

fields (including the water source table).

Objective
1
Data Development and Updates, Priority Data sets

Task
7
Harvest

Develop and maintain information on sport and commercial harvest.  Higher priority is assigned to anadromous species.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Review ocean and mainstem Columbia River harvest data 
The existing ocean harvest data tables were examined. Serious omissions were

presently in the StreamNet databases and report findings to 
identified in the data bases and the report formats were determined to be

Steering committee
confusing and of marginal value to users. It was recommended that the entire

harvest data system be rebuilt. The new system should not try to include

primary harvest data (landing records) which are capably managed by individual

state agencies. Rather, summary data would be more appropriate for the StreamNet

system and would be more useful to managers.


ODFW
1
Compile and exchange updated and/or new tributary sport 
The database is up-to-date to the extent possible, and we are awaiting 

harvest data.
sport catch updates from the ODFW propagation section, so no specific 

work was completed on this task this quarter.


Objective
1
Task:
7
6/24/02
Page 14 of 58

WDFW
1
As funding and time permits, compile freshwater harvest for 
1.  Smith worked on completing the sport snout recovery tables for the 

key Columbia Basin salmonid stocks for both anadromous and
1999 and 2000 harvest years.  Three tables were completed and delivered 

resident data , using existing WDFW data sets (i.e. Angler 
to Susan Markey, covering the 1999 and 2000 Sport Salmon and 

Fish Database) and other sources.  Standardize the data (to 
Steelhead CWT recoveries and the Salmon/Steelhead CWT mark rates 

stock if possible), convert and submit it to PSMFC.
observed in the 2000 sport fisheries.

2.  Lensegrav assisted on one day of field collection for a selective fishery

study.

3.  Late this quarter Sikora started reviewing the viability of port 

locations for old StreamNet Washington harvest data.


Objective
2
Data Development and Updates, Other Data sets

Support the need for region wide fisheries data for research, monitoring, modeling and management through acquisition of new information and updates to previous information for data sets of medium or lower priority as time and funding allow.  This objective includes anadromous and resident species.


Objective
2
Data Development and Updates, Other Data sets

Task
1
Habitat Restoration/Improvement Projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations within

the Columbia Basin and compile and maintain them in standardized, consistent formats.  This data category is still being organized,

but interest in this information is growing.  Existing data sets will be maintained and enhanced as practical.  Additional sources of

this information will be explored.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

MFWP
1
Continue to collect, centralize and maintain all stream 
New projects are being entered on the biannual cycle with MFWP; data 

restoration projects for Montana using the "Future Fisheries 
will be exchanged as scheduled.

Interface" which StreamNet staff maintains and the Fisheries 

Division inputs data.  Exchange data to the Region twice 

during the year.


ODFW
1
Maintain, correct and exchange existing restoration project 
There were no requests to update or correct existing records this quarter.

information.


Objective
2
Task:
1
6/24/02
Page 15 of 58


WDFW
1
If new funding permits, finalize conversion of  Washington's 
1.  Lensegrav created an ArcView project covering Water Resource 

IAC's (Interactive Committee for Outdoor Recreation) 
Inventory Area 5 (WRIA 5) for the Limiting Factors Analysis to 

PRISM database for WRIA 5 records and submit to 
investigate the feasibility of using ArcView for this type of application. 

StreamNet.  Build an ArcView project file that incorporates 
The outside funding to complete this never materialized; a pilot might be 

Washington Salmon Recovery Funding Board data, 
created in the Columbia Basin if additional funding is found or if current 

basin-specific salmon habitat limiting factors (LFA) and 
StreamNet priorities change.

potentially SaSI stock status.  Assess if this tool allows 
2.  Lensegrav provided specific advice and data examples to O'Connor for 

managers to effectively compare relative expenditures (and 
his presentation to the OFWIM Annual Meeting in November (see 

the factors they intend to address) to identify priority issues 
Objective 6, Task 4).

in the basin and the utility of creating similar products for 
3.  Mike Banach submitted a draft exchange format late in FY2001 to 

other basins.
WDFW only.  Lensegrav reviewed it, verifying the changes would have 

little impact on how we represent Washington's data, and presented a 

draft of his report to Sikora/O'Connor for review.

Objective
2
Data Development and Updates, Other Data sets

Task
2
Barriers and diversion/screening

Develop and maintain data sets for barriers to fish migration and diversion structures with information on screening status.  

This category is still being organized.  Existing data on adult barriers will be maintained and updated as practical.  Other sources

of data will be explored.  Work on juvenile barriers, culverts and diversion screening may require additional resources.  The

primary emphasis is on anadromous species except in non-anadromous areas.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

MFWP
1
Continue to collect barrier location, species affected and 
Work is ongoing and on schedule.

other fields on stream barriers in Montana.  Information will 

be collected on all species regardless of life history.  

Exchange Barriers data with the StreamNet database.


ODFW
1
Update, maintain, correct and exchange adult migration 
1.  Initiated efforts to reconcile hatchery data from the Barrier database 

barrier information.
and hatchery data in GIS coverage format.  The end product will be a 

hatchery table that contains coordinate information for all hatchery 

related facilities which matches the coverage point locations for these 

facilities.  Modifications will also be made to the hatchery table to facility

type information. See Objective 1, Task 6, Component 2 for specific details.

2.  Several staff met to discuss the status and direction of the barrier 

database.  We discussed what constitutes the core components of the 

database, some potential approaches for modifying it, and also how to go 

about making it more comprehensive. Following the meeting, the 

overhaul of the barrier database was initiated.


Objective
2
Task:
2
6/24/02
Page 16 of 58

ODFW
2
Update, maintain, correct and exchange anadromous and 
Jon investigated the criteria that were developed by the Cooperative 

resident fish barrier data.
Forest Ecosystem Research program in regards to passage of cutthroat 

trout over natural barriers. The CFERP found that height alone was not a 

reliable indicator to determine passability of a particular barrier. 

Variations in the structure of barriers strongly influence their passability 

(i.e., whether a falls is a straight drop or actually a series of steps). This will

have implications for our efforts to develop data that distinguishes 

between mixed sea-run / resident and resident only populations of coastal 

cutthroat trout.


WDFW
1
If funding and time permits, review existing Washington state
As of January, 2002 WDFW Habitat Program was reviewing the future of 

barriers (in GIS format) and identify additions and 
the SSHIAP Project and proposing its future focus be tasks such as 

corrections needed and plan for future exchanges.  Any 
integrating and truthing the several barriers files that exist for 

barrier work plan will depend first on establishing a WDFW 
Washington state. O'Connor will participate in this decision via the 

Dams spatial layer (see Objective 1, Task 5, Job 1).
agency's Corporate Data Oversight Committee, and work to integrate any

barriers data efforts they undertake with this StreamNet Task.

Objective
2
Data Development and Updates, Other Data sets

Task
3
Juvenile data, abundance and outmigration

Develop and maintain information on smolt production (as determined from smolt traps), juvenile abundance (as determined

through snorkel, electrofishing, and other surveys), and smolt density model estimates.  Primary emphasis will be on maintaining

the existing smolt density model data.  The rest of this data category is still under development and may require additional

resources to accomplish.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Begin design and collection of  juvenile trapping component 
The Idaho Supplementation Studies used the IDFG/StreamNet Juvenile 

in IDFG/StreamNet Fish Information System. At current 
Trapping database and interface to compile their data last field season. 

funding levels this task will be of lower priority than 
During this quarter we developed and implemented a methodology to 

Objective 1 data components and progress will depend on 
transfer that data into the IDFG/StreamNet FIS. This will facilitate the 

completion of Objective 1 tasks. This task is also dependent 
flow of data to StreamNet.

on collaboration with non-StreamNet projects in IDFG.


IDFG
2
Incorporate the General Parr Monitoring database into the 
The Fisheries Bureau, using funding outside StreamNet, worked to attach 

IDFG/StreamNet Fish Information System and submit to 
general parr monitoring sites to StreamNet stream LLIDs and measures. 

PSMFC.
This will make attaching the GPM data to the hydrography and 

eventually incorporating into StreamNet easier.


Objective
2
Task:
3
6/24/02
Page 17 of 58

Objective
2
Data Development and Updates, Other Data sets

Task
4
Age

Develop and maintain information on age/sex composition of returning adults, primarily for anadromous species.  This is a medium

priority, with the primary focus on developing data for a test location for each cooperating agency this year as a means of testing

data organization/format and utility.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Compile year 2001 Age/Sex Composition data.
During our review of our hatchery return data, we summarized age composition

data from length frequency tables in the Stock Summary Report. The data

were added to the IDFG/StreamNet hatchery returns database.

MFWP
1
During the field office visits in 2002, the availability of age 
We will request this information from field biologists during the regularly 

data will be determined.  Information will be gathered on what
scheduled visits.

is being collected, in what format and for what geographic 

areas.  Data will be acquired, if available, and reviewed with 

the Steering Committee.


WDFW
1
Research, compile, convert and submit age data for natural 
1.  Woodard provided ongoing support for the Region 5 scales database.  

spawner data (salmon and steelhead) in one prototype 
The data in this database includes age specific data for sport, escapement, 

subbasin (probably Lower Columbia R).  This effort is to 
and hatchery returns.   This database is also the core of Region 5’s run 

assess any problems with the existing 2001.1 format, 
reconstruction of escapement and hatchery returns to the Columbia River 

standardization with any other agencies' data already 
and the source for the WDFW StreamNet database.

submitted to StreamNet, and plan for further data submittals.
2.  Woodard and Smith added the age database to the escapement database.

 Smith spent time getting familiar with the reporting of age data and the 

links to the escapement detail data.  Smith worked on updating the 

statistical age data for return years 2000-01.  This statistical data (Mean, 

Number, Standard Deviation) is now added to the age database along with 

the overall age composition by age.

3.  Woodard and Sikora gave feedback to IDFG's Evan Brown so he could 

standardize his data entry for the CountValue field when this information 

was not provided by the biologists.


Objective
2
Task:
4
6/24/02
Page 18 of 58

Objective
2
Data Development and Updates, Other Data sets

Task
5
Production factors and run reconstruction

Develop and maintain information on survival, production factors, spawner / recruit estimates, and run reconstruction.  This is

currently a low priority, but the existing spawner / recruit estimate data will be maintained.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

All
1
On an opportunistic basis, acquire run reconstruction and
No work was done on this task by any of the projects this quarter.

production data from developing entities if any become available.


Objective
2
Data Development and Updates, Other Data sets

Task
6
Habitat

Acquire data sets related to fish habitat (including water quality, stream/watershed habitat quality, temperature, invertebrates, and

miscellaneous habitat data) from the multiple agencies, tribes and organizations within the Columbia Basin and compile and maintain them

in standardized, consistent formats or archive them in original format, as appropriate. This is currently a low priority under the existing

contract, and data development will be pursued only on other funding. Data developed on other funding will be organized and included in the 

StreamNet database.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

Region
1
Coordinate with regional entities on habitat data needs and 
We reviewed a WDFW/WDOE report proposing standard stream habitat

availability.  Begin developing an approach toward capturing 
measurement methods.  Because the topic "habitat" is so broad, if the StreamNet

high priority data types.  New development of habitat data 
project was to pursue this type of data in the future, we would need to work with a

may require additional resources.
wide variety of data providers to determine the types of data that could be collected

at a regional level and account for the variety of methods.  This report is only one of 

many such materials that would need to be evaluated.

Objective
2
Data Development and Updates, Other Data sets

Task
7
Genetics

Develop and maintain information on genetic information and data sources for areas where genetics data exist.  Efforts this year

will concentrate on organizing existing information, and then working on a Data Exchange Format.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Develop prototype genetics data application using CRITFC 
A prototype application was presented to the Steering Committee.  

genetic data.
Primary genetic data is rapidly evolving and constantly changing.  We 

proposed that StreamNet maintain a catalog of available genetic data sets 

and contact information, rather than the primary data itself.


MFWP
1
Obtain results from genetic analysis from the University of 
Work is ongoing.

Montana Genetics Lab for sampled populations of Montana's 

species of special concern.


Objective
2
Task:
7
6/24/02
Page 19 of 58

MFWP
2
Update fish distribution table when new genetic samples 
Work is ongoing.

affect fields/records.


MFWP
3
Exchange data to the StreamNet regional database when a 
The DEF is not yet ready.  We have sent our database to CRITFC, and 

DEF is approved by the Steering Committee.
hopefully they will complete a DEF this FY.


Objective
2
Data Development and Updates, Other Data sets

Task
8
Information generated during Subbasin Planning

Work with Subbasin Planners to acquire information that is developed for Subbasin Plans and make it available basin wide in a

standardized format.  Data that fits existing DEF will be incorporated in the queryable database.  Otherwise, data will be posted 'as is'

and made available on the StreamNet website.  Actual data development beyond the existing DEF would require additional resources.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Work with Oregon Technical Support Team (when funded 
Draft work statements and budgets that included data management support

and formed by NWPPC) to obtain existing data in electronic 
for subbasin planning in Oregon were developed and presented to the 

format
Council.  No data assembly will actually occur until the Council makes its 

final decisions about how to conduct subbasin planning.


CRITFC
2
Work with Oregon Technical Support Team (when funded 
The Council has not adopted a subbasin planning strategy yet.  No work 

and formed by NWPPC) to develop applications to capture 
was performed this quarter.

additional data generated during subbasin planning

MFWP
1
Will communicate with Montana's CBFWA representative to
There are no apparent needs at this time.

better understand where they are in the planning process. 

Currently we receive all survey data generated from BPA 

contracts in Montana.  Will discuss other products that may 

become available.


Objective
2
Task:
8
6/24/02
Page 20 of 58

Objective
2
Data Development and Updates, Other Data sets

Task
9
Supplemental data sets

Obtain data sets that are important to regional monitoring and management but that do not fit the existing DEF for posting 'as is' on

the StreamNet web site.  Primary emphasis will be toward resident fish data developed by BPA funded fish and wildlife projects, data

developed by cooperating agencies on other funding, and data developed by the FWP.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

ODFW
1
Pursue supplemental datasets on an opportunistic basis 
1.  Shannon worked on locating resident species information by calling 

consistent with StreamNet direction.
Chris Moyer for Redband survey results on the Deschutes River and its 

tributaries. He requested that she call back at the end of December for 

finalized data. She also called Chuti Fielder for bull trout data from the 

Hood Basin - this data was promised "soon" via fax.

2.  Shannon spoke with Restoration and Enhancement Program staff 

about a grant proposal we submitted to help compile species location 

information. There were problems with the contact person information, 

and with signatures, but these issues were cleared. We were assured that the

proposal is intact and will be reviewed in February.

3.  Michael worked with Fish Division Natural Production staff to develop

standard definitions for Origin and Present Production categories for fish 

populations.


WDFW
1
Work with participants in the Blocked Area Resident Fish 
O'Connor participated in the November JSAP Steering Committee 

Stock Status Project to obtain copies of their fish sampling 
meeting to discuss the need for common field sampling data formats 

data.  Assess the "fit" to existing StreamNet data exchange 
among the four JSAP sampling agencies (WDFW and three tribes in the 

formats.  Convert and submit data as appropriate.
Upper Columbia). He helped write an RFP to seek a contractor to assess 

the internal formats currently in place and to propose a format that can 

integrate as much data as possible from the four disparate sources.  

O'Connor will guide development of this format to make conversion to 

StreamNet exchange format as simple as possible.  StreamNet target 

formats would be the FishSurvey table (under construction) and possibly 

one of the (draft) Habitat data tables.


Objective
2
Task:
9
6/24/02
Page 22 of 58


Objective
2
Data Development and Updates, Other Data sets

Task
10
Carcass placement

Work with agencies to capture information on placement of salmon carcasses and results from carcass placement projects.  This is currently

A low priority and will require additional resources to take on as a primary data type.  Existing data may be acquired for posting 'as is'.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

ODFW
1
Exchange carcass placement report 'as is' for 1999 placement
To date, no information has been submitted by ODFW Carcass Placement

efforts.
staff. Once data comes in, we will review and process it and submit it to 

StreamNet.  We did package and ship a Carcass Database CD to a new user

(a field biologist) upon his request.


Objective
2
Data Development and Updates, Other Data sets

Task
11
Populations - status and delineation

Develop a data set to describe population status as determined by other agencies.  This is currently a low priority, and efforts will be

exploratory in nature during FY2002.  Links to existing data may be posted on the StreamNet web site.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Begin design and development of incorporation of population
We did not work on this job component during the quarter.

status and legal designation into the IDFG/StreamNet Fish 

Information System.


MFWP
1
Species of Special Concern are currently identified on the MRIS
MFWP is working toward moving their website to a new design.  We will 

website; when the MT Natural Heritage Program website includes
incorporate this feature when the move is completed, probably in the 3rd 

status information on these species, we will create a link between
quarter.

our sites.  Will also look into linking to USFWS website if

information is available on Threatened and Endangered Species. 

Will link to MFWP new native species web page when available.


Objective
2
Data Development and Updates, Other Data sets

Task
12
Develop other data sets

On an opportunistic basis, develop data that relate to other existing data sets in the StreamNet database or would be useful for regional

planning, monitoring or management efforts.  This is a low priority, but some efforts may be expended if the data appear useful and they

can be obtained within current resources.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Work with IDFG biologists to incorporate other data sets 
While we worked closely with IDFG fish biologists to incorporate their 

into the IDFG/StreamNet Fish Information System, dependent
data into the FIS and StreamNet, we did not start any new data categories, 

on the time available after completion of higher priority tasks
which this task addresses.

and opportunistic collaboration of non-StreamNet IDFG projects.

Objective
2
Task:
12
6/24/02
Page 22 of 58

ODFW
1
Update, maintain, correct and exchange photographic 
Susan submitted updated MapCat (photographic) data to StreamNet in early

information (MapCat and related tables).
October. Susan also compiled a list of barriers and dams in the Bend area

for which we do not have photographs.


ODFW
2
Compile and exchange marked-to-unmarked ratio data 
Columbia River Management staff conducted fall chinook spawning 

(relative to dam, weir, spawning ground, etc. counts) for an 
ground surveys on Oregon tributaries to the lower Columbia River and 

undetermined location in the Oregon portion of the Columbia
documented fin marks and recovered CWT's. This information will be 

basin as a prototype for these data.
provided to StreamNet as it is finalized.


ODFW
3
Compile and exchange hatchery-wild fraction data for an 
ODFW Columbia River Management staff provided Shannon with estimates of 

undetermined location in the Oregon portion of the Columbia
hatchery and wild summer steelhead returning to the Columbia River in 2001.

basin as a prototype for these data.  It is not clear if these 
This information will first be processed for use in the Willamette-Lower Columbia

data are still available since the dissolution of PATH, and the 
TRT effort, then it will be passed back to Shannon who will put this information 

data developed by PATH, which are not in StreamNet, need 
into the proper format and submit it to StreamNet.

to be captured so that they are not lost.  We intend to 


attempt to locate and obtain the data in some fashion.


Objective
2
Task:
12
6/24/02
Page 23 of 58

Objective
3
Data Management and Delivery

Provide high quality data management services, with specific emphasis on the creation of regionally consistent data sets and the timely delivery of data to users in formats that meets their policy, planning, and management needs


Objective
3
Data Management and Delivery

Task
1
Maintain and enhance tabular database systems at the project and regional levels

Maintain functional tabular database programs at the agency and regional levels to make consistent tabular data sets for anadromous

fish, resident fish and to a lesser extent wildlife available through the StreamNet online database system.  At both the regional and

agency levels, provide database management and administration necessary for accomplishing StreamNet objectives, to include:

1) maintaining and updating the hardware and software systems necessary to support the StreamNet project, and2) enhancing or

optimizing StreamNet database structures and capabilities.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Maintain and enhance hardware and software for the 
1. We provided routine system administration to the servers and workstations

IDFG/StreamNet Fish Information System. This tasks 
in IDFG/StreamNet. We also developed a comprehensive backup and recovery

includes general system maintenance, addition of new servers 
system for the servers. Future work will include backup and recovery for all the

and workstations, where possible, providing necessary system 
IDFG/StreamNet client workstations.

administration and disaster recovery, and maintaining 
2. We received $60,000 from IDFG this fiscal year to expand the work on the FIS.

software licenses.
Some of the money is earmarked for wildlife, so we have created an umbrella

organization called the Idaho Fish and Wildlife Information System (IFWIS).

IFWIS continues to keep StreamNet and development of the FIS as its core work,

using the IDFG money to leverage work we are doing with StreamNet. The money

this year was all categorized as operating or capital, so we started to develop a

plan to expand and enhance our hardware and software. We will be purchasing new

workstations for all staff, adding 2 new servers, upgrading ArcInfo 7.2.1 to ArcGIS 

8.1, and obtaining internet mapping software to develop Intranet access to the FIS.


MFWP
1
Provide a high-quality, state-level data management system, 
1.  We drafted a Data Dissemination Policy for MFWP

emphasizing coordination with StreamNet regional staff, 
2.  We developed a 4 hour GPS training course and will send  2 staff  to 

MFWP and other state and federal natural resource agencies 
each region during January to present it.

to encourage the use of consistent data attributes and data 
3.  We provided ArcView Training for MFWP staff in December

sets among all agencies.


Objective
3
Task:
1
6/24/02
Page 24 of 58

ODFW
1
Provide state-level StreamNet database management, 
Many activities took place in support of state-level data management:

administration, and development.  Enhance StreamNet and 
a.  Staff coordinated on the development of a Life-Stage Timing

ODFW database structures, interfaces, tools, and capabilities 
Database. We discussed draft database structures, and subset out

as needed.  Maintain hardware and software.
distribution data by timing units within the John Day basin for testing out

different database structures that will facilitate mapping of the data. Bill 

developed 3 logical models for the database in order to evaluate their 

structure against the various requirements of the data and needs of all 

users. Bill then tested the tabular system, while Jon evaluated the spatial 

aspects of the different pilot databases, and provided feedback on 

functionality for mapping the data.  One of the choices was eliminated as 

testing proceeded.  Bill also worked on a demonstration program that can 

graphically display the Timing information into bar graph form.

b.  Susan gave a "refresher" training session for users of the FishScreen 

Database.  This session was mainly to answer questions that the ODFW 

Fish Screening staff had regarding the database.

c.  Shannon requested and obtained new species codes for resident species 

from Mike Banach and updated the OR_Data UI, as well pertinent ODFW

staff with the new codes.

d.  Jon reviewed Draft Info. Sys. Div. policies on Acceptable Use of 

Electronic Systems and Tools; Acquisition & Replacement of Information

Resources; and Disposal of Computer Hardware, Software and Peripherals.

e.  Bill completed the data entry component for the TRT database, but is

 continuing to add user enhancements.

f.  Susan started work on the first draft of the barrier data needs 

questionnaire.

g.  Bill helped Shannon create a query to isolate and present all required 

information that may be needed during biologist contacts.

h.  Bill updated, recompiled and installed a Time Logger system onto 

Shannon's computer.  The application allows Shannon to log time spent 

in particular areas of the data collection process. This is part of our effort

to determine where the most time is spent, and therefore where to look 

for opportunities to improve efficiency in order to save time. The 

information should also help as we look to establish counterparts to 

Shannon in field offices.

Objective
3
Task:
1
6/24/02
Page 25 of 58

Region
1
Locate and evaluate data obtained by the precursor projects 
While moving files from the old web server to the new server, we 

to StreamNet (CIS and NED), including floppy disks and hard 
reviewed files in the ftp directories.  Duplicates were found and deleted.  

copy reports.  Determine the types of data that are available 
Obsolete files were archived on CD and deleted from the system.  The 

in each format and how much are already included in 
Regional Fisheries Biologist located early StreamNet floppy disks (created 

StreamNet.  Determine the feasibility and value of reclaiming
by the Coordinated Information System project, Northwest 

lost data and the workload required.  Prepare a report making
Environmental Database project, and the early StreamNet project) and 

recommendations to the Steering Committee for the possible
copied all files possible onto CD.  Many floppy disks had corrupted files.  

inclusion of those data not already included in StreamNet.
Most of these were recovered using Norton Utilities, but several disks were

unusable and thus information was lost.  The next step in the process is 

to evaluate the files that were recovered and determine what is of value 

for incorporating into StreamNet.


Region
2
Maintain and upgrade StreamNet database servers and 
1.  PSMFC staff obtained a new server to replace the StreamNet web site 

software.  Administer SQL Servers.  Advise on office software
server.  Significant work was done to configure and test this server and to 

acquisition.  Maintain and optimize database structure and 
begin transferring files from the old server.  The old server's hard disks 

function .
were filled entirely, creating severe performance problems.  Several 

hundred MB of files needed to be archived so that the web site could be 

responsive.

2.  The Regional Database Manager and Regional Fisheries Biologist 

obtained new computer workstations.  Time was spent configuring and 

transferring files to these computers.

3.  The Regional Database Manager acquired a laptop computer and a 

printer for ODFW and a laptop computer for WDFW.


WDFW
1
Coordinate activities to maintain all new and existing WDFW
1.  Sikora and Woodard coordinated all database and piecemeal work 

internal tabular databases, code and cross-code assignment 
described in better detail under the specific data categories in Objective 1 

files related to StreamNet tabular and spatial submissions for 
and 2.

data sets defined in Objectives 1 and 2.     Submit any tabular 
2.  Sikora and Lensegrav researched better names for WDFW's marine 

databases as warranted to coordinate with spatial layer 
waterbody codes.

exchanges.  Maintain the hardware and software necessary to 
3.  O'Connor and Hudson began early discussions concerning cleaning up 

the database system.
existing spatial event table data formats in light of upcoming WDFW 

work to integrate the StreamNet,  Bull Trout 2000, and SaSI tables with 

information from the Limiting Factors project (LFA).


Objective
3
Task:
1
6/24/02
Page 26 of 58

Objective
3
Data Management and Delivery

Task
2
Maintain and enhance the GIS and hydrography database systems at the project and regional level

Maintain functional Geographic Information System programs at the agency and regional levels to make consistent GIS 

layers for anadromous fish, resident fish and to a lesser extent wildlife available through the StreamNet online database 

system.  At both the regional and state levels, provide GIS management and administration necessary for accomplishing 

StreamNet objectives, to include: 1) maintaining regional and agency-level GIS systems, including hardware and software, 

and 2) maintaining a regionally consistent hydrography layer at the 1:100,000 scale.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Maintain and enhance hardware and software for the 
1. We provided routine system administration to the servers and 

IDFG/StreamNet GIS and Fish Information System. This task 
workstations in IDFG/StreamNet. We also developed a comprehensive 

includes general system maintenance, addition of new servers 
backup and recovery system for the servers. Future work will include 

and workstations where possible, providing necessary system 
backup and recovery for all the IDFG/StreamNet client workstations.

administration and disaster recovery, and maintaining 
2. We received $60,000 from IDFG this fiscal year to expand the work on

software licenses. We will also be evaluating the impact and 
the FIS. Some of the money is earmarked for wildlife, so we have created 

cost of moving from ArcInfo 7.2.1 and ArcView 3.2 to 
an umbrella organization called the Idaho Fish and Wildlife Information 

ArcGIS 8.1. Depending on that outcome, we may make this 
System (IFWIS). IFWIS continues to keep StreamNet and development of

major software migration this year, including necessary 
the FIS as its core work, using the IDFG money to leverage work we are 

hardware reconfigurations.
doing with StreamNet. The money this year was all categorized as 

operating or capital, so we started to develop a plan to expand and 

enhance our hardware and software. We will be purchasing new 

workstations for all staff, adding 2 new servers, upgrading ArcInfo 7.2.1 

to ArcGIS 8.1, and obtaining internet mapping software to develop 

Intranet access to the FIS. 

3. IDFG/StreamNet provided specifications for the new IDFG computer 

fleet management program for GIS classes of computers. Began to 

research servers and develop infrastructure plan.


IDFG
2
Provide GIS support and data infrastructure to the 
Using non-StreamNet funds we developed a variety of ArcView 

IDFG/StreamNet Fish Information System. The 
applications that provide GIS tools to fisheries biologists. This helps 

IDFG/StreamNet Fish Information System is built upon a 
facilitate the flow of data into the FIS and StreamNet, by ensuring local 

foundation of GIS data and we will continue to provide that 
database efforts match FIS standards, in particularly that they link to 

base. Products from this task will play a key role in 
LLID. New tools include:

integrating GIS with traditional tabular data models, 
1. The Geographic Information Locator (GIL) is a custom front end to 

specifically SQL Server and Microsoft Access.
our large set of GIS data. It eases the use of GIS data for biologists lacking 

important ArcView skills. It provides an easy and convenient way for 

users to locate specific geographic features and display a variety of GIS 

data with it.


Objective
3
Task:
2
6/24/02
Page 27 of 58

2.  One of the largest assistance requests that we get from biologists is to 

project data for them. Idaho is divided into two UTM zones, so in the 

state office we use a modified UTM projection called the Idaho 

Transverse Mercator (ITM). It covers the entire state in one zone. 

Because ITM is not a standard projection, it is not available as such in 

ArcView or for GPS receivers. Therefore, most biologists collect their 

data in UTM using their local zone. To use with our statewide database 

they need to project to ITM. We developed the Idaho Projector 

Extension which provides a custom, simple to use interface to project 

among ITM, UTM, and Decimal Degrees.

3. The Fish Tools ArcView application enables users to associate GPS 

point data to a LLID and computes the measure on the stream that the 

point lands. It allows the user to control the tolerances and exact 

placement of each point. The data are saved to a data table for eventual 

use in the FIS and StreamNet. Fish Tools includes complete  

documentation. It has been installed along with our GIS data sets at 

Nampa Fish Research. We provided on-site training.

4. Our current applications for conducting queries and maps of the FIS fish

distribution data requires an intermediate, temporary view of the data be 

built. We began to develop and application in ArcInfo 8.1 that would 

create a SQL Connection directly to the FIS. We ran into speed problems 

and decided to defer this project until we obtain ArcSDE.

5. Using non-StreamNet funds, we improved the functionality of the 

IDFG/StreamNet data request project. This project accepts of location and

returns a list of special status fish species. The requests  typically come 

from private consultants and organizations for the development of 

environment assessments.

6. Working with IDFG biologists, we identified a few new routes that need 

to be added to the 1:100,000 scale hydrography LLID system.

7. At IDFG/StreamNet, we keep all of our GIS data in the Idaho 

Transverse Mercator projection in meters. This differs from the regional 

StreamNet projection and units. In preparation for submitting data to 

PSMFC, we began to develop an ArcInfo program to translate IDFG 

measures to StreamNet measures.

8. We produced a set of hydrography maps for the IDFG Fisheries Bureau.


MFWP
1
Maintain, update and enhance MFWP GIS data layers, 
1.  Janet met with MFWP Administrators in October to prioritize data 

provide these data as distributed files, on the web or as part of
development needs, and will follow-up with each division.  

map requests.  Integrate the use of GIS into management 
2.  We currently are updating antelope, sage grouse, native fish species 

decision making processes.(Most of this work is conducted 
management areas and tabular data with associated spatial component for 

outside the StreamNet contract with MFWP dollars).  
snow track surveys, fishing regulations, and upland game bird projects.

Maintain the MFWP StreamNet GIS system.


Objective
3
Task:
2
6/24/02
Page 28 of 58

MFWP
2
Work with Natural Resource Information System staff and 
This task was finished.  Maintenance and enhancement with LLID will be 

StreamNet GIS staff to maintain the 1:100 K NHD 
ongoing.

hydrography for Montana.  Data layer will be enhanced with 

lakes and reservoirs and include stream level LLID routes.


ODFW
1
Develop and maintain a fully functioning GIS system and the 
1.  Jon began the process of assembling stream route data in preparation for 

database structures that help improve spatial data 
assessing the synchronization between ODFW's 100k data and the data 

management and transfer with ODFW staff and the regional 
maintained at PSMFC.

StreamNet system..  Maintain the hardware and software 
2.  Jon reviewed an NHD / LLID event conversion application developed in Access

systems necessary for the GIS.
by David Graves and provided comments regarding potential fixes and



improvements.  The application takes event data tied either to an LLID- based or an



NHD route system and converts them so that they will work on the other system.

Region
1
Assist the database manager, as needed, with the spatial 
1.  The GIS Specialist assessed changes between the 1990 and 2001 subbasins

component of data and its implementation online.
at the request of the database manager and prepared a map illustrating these 

changes for future use on the StreamNet web site.

2.  The GIS Specialist determined locations for a set of new macroinvertebrate

sites and reported these back to the Fisheries Biologist.

3.  Errors in the hydrography layer were discovered and reported back to 

WDFW and ODFW for correction.


Region
2
Integrate the functioning of the GIS system with the StreamNet
We developed new cross tables for the map catalog to the subbasins as 

fisheries and habitat database in support of the query system.
defined by the Power Planning Council in 2001.

Maintain up-to-date cross tables used via the StreamNet web

interface to select information by geographic area.


Region
4
Maintain a library of StreamNet GIS layers for internal use 
We revised the metadata format based on feedback from an NBII

and as downloadable data on the web site with complete 
representative and posted updated metadata to the StreamNet web site.

documentation (metadata).
We completed submission of StreamNet metadata to the NBII clearinghouse.


Region
5
Maintain a regionally consistent 1:100,000 hydrography 
1.  The GIS specialist fixed the hydrography in the ID/MT border area where

layer (the PNW Reach File) for internal use and public access 
stream routes on the hydrography were missing due to recent updates in this

through consultation with the state stewards of the 
area by both states.  Updated hydrography files were posted to the internet site.

hydrography.
2.  We created a new EventMapper hydrography layer based on recent

updates and distributed it to registered EventMapper users.


Region
6
Rebuild LLID-based stream route system on the National 
1.  The GIS Specialist rebuilt the LLID-based stream route system on the 

Hydrography Dataset hydrography for Western Montana 
National Hydrography Dataset hydrography for western Montana and 

(this work is complete for ID, OR, WA).
integrated this information into the NHD/LLID data conversion application.

The updated application and GIS files were posted to the StreamNet Internet

site.  The application may now be used to convert hydrography data anywhere

within Washington, Oregon, Idaho or western Montana.

Objective
3
Task:
2
6/24/02
Page 29 of 58

2.  Extensive testing of the NHD/LLID conversion application was conducted.

Errors found were corrected whenever possible.  Some errors could not be fixed









     due to inherent differences between the line work of these two hydrography layers.


WDFW
1
Coordinate activities to maintain all new and existing WDFW
1.  Sikora and Lensegrav attended Hudson’s November 14 demonstration 

internal spatial layers related to StreamNet tabular and 
of his distribution data applications for GIS Day.  Lensegrav also attended 

spatial submissions including but not limited to 100K hydro 
the GIS users meeting.

(streams and lakes), marine areas, distribution, production 
2.  Lensegrav updated our GNIS file and our documentation with a more 

(hatchery and dam), and release site layers.  Manage 
current version.  Lensegrav and Sikora added instructions to our internal 

regionally standard location codes (LLIDs).  Submit any 
interface documentation and general instructions for ArcInfo, describing 

spatial layer as warranted to coordinate with tabular 
how to load the new hatchery facility points layer and how to get the 

exchanges.  Maintain the hardware and software necessary for
hatchery names to show up.  Lensegrav tutored Burns on how to use 

system function.
Topozone, TerraServer, and EventMapper.  Sikora demonstrated the 

WDFW hatchery facility interface for Burns and together they refreshed 

their memory in how the lake interface worked. 

3.  Lensegrav generated MUcodes for I-82 ponds in Yakima County for a 

Region 3 biologist and updated the spatial layer with our most current 

tabular Hatchery Facility work.  Lensegrav assisted a couple staff projects 

by creating ArcView projects.  Burns created a reference file to show the 

LLIDs that cross more than one HUC since these streams are often the 

source of problems.

4.  Sikora and Hudson conferred a few times this quarter about the status 

of future GIS improvements and expected delays.


5.  O'Connor and David Graves (PSMFC) discussed issues related to spatial 

data exchange, not limited to 100K hydro data.  Issues included whether 

PSMFC should generate spatial layers from tabular files received and the 

amount and formality of documentation (metadata, reference documents, 

etc.) required for spatial data exchange. Resolution of these issues awaits 

broader Steering Committee discussion.

6. O'Connor and Burns worked to figure out the MetaMaker product and 

used it to begin compiling metadata for the Washington state bull trout 

distribution/use spatial database.  One of the products will be a list of 

formatting tasks that need to be done "by hand" to the metadata file after

MetaMaker processing, since that product has some inflexible aspects 

with respect to precise formatting of information.

7.  O'Connor rebuilt the WDFW StreamNet GIS Data Dictionary 

document with an additional Bull Trout appendix.


Objective
3
Task:
2
6/24/02
Page 30 of 58

Objective
3
Data Management and Delivery

Task
3
Data management and coordination

This task includes data management after they have been developed.  Once data are submitted to the regional database, assure they

fit established formats, perform appropriate error checks, and load the data into the StreamNet database and perform routine

management of the data.  The regions and contributing agencies will collaborate to fix problems and assure seamless loading of

data into the database.


Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Review and update entire hatchery return dataset, in order to 
1. Upon inspection of our existing hatchery return data, we noted a 

ensure the proper past assignment of trend definitions, 
number of various errors. Before submitting these data to PSMFC, we need

location identifiers, accurate counts, and disposition codes.
to complete a thorough review of all of our hatchery return data,  We 

completed the review for data from 1961 through 1999. We verified and 

corrected, where necessary, all values. We made sure that each record had 

an associated trap and hatchery. We also checked for completeness for 

each hatchery and year.  This was necessary before final incorporation in 

the FIS and eventual submission to regional StreamNet. Corrections and 

updates that we performed included 1) insure each record has a valid 

hatchery and trap,  2) added comments on differences found between 

reported totals and calculated totals, 3) added comments on inferred or 

derived subtotals, 4) made changes to account for historical management 

changes, 5) updated the reference information, 6) corrected mislabeled species.

2.During the review process, we added age composition data to the 

hatchery return data.

3. Incidental resident fish presence is sometimes noted at anadromous hatcheries.

When found we also added that data to the hatchery return database.

IDFG
2
Review and update entire redd count dataset, in order to 
1. We conducted a thorough visual review of 1988, 1953, and 1954 redd 

ensure the proper past assignment of trend definitions, 
count data and transect locations in the IDFG/StreamNet database. 

location identifiers, and accurate counts.
Corrections that we made included: 1) verified the transect location and 

count values for each transect, 2) corrected mislabeled species, and 3) 

examined the location of each trend over time. We found that many 

trends had a large variation in position and length over time. Such 

transects probably do not provide comparable data from year to year. We 

think a complete overhaul to trends in the Idaho redd count data is required.

2. Sockeye and steelhead redd counts were added to the database.


IDFG
3
Add additional stream routes and assign LLIDs to 1:100,000 
Using input from local stream survey databases and the Fish Tools 

scale hydrography. New routes will be added as required to 
ArcView project we have compiled a short list of new streams that need to

support locational data in the IDFG/StreamNet Fish Information
be routed and assigned LLIDs.

System. All new routes will be submitted to PSMFC.


Objective
3
Task:
3
6/24/02
Page 31 of 58

ODFW
1
Work with regional staff as necessary to assure seamless 
Shannon and Bill worked on identifying inconsistencies of Trend numbers between

loading of data into the regional database.
the OR-Data1 database and StreamNet's copy. Rough queries showed that there

were a significant number, 485, of trends that did not match the TRENDID and

LLID in the regional level data.  Shannon was able to correct most of the trends 

identified by Bill Kinney as incorrect (only 5 harvest related records remain to be

corrected). Most involved the stream being referenced by ODFW survey's that

crossed the California border, but also there was an incorrect batch of LLIDs

being used. Some problems were also caused by Oregon (appropriately) deleting

trends in the past and assigning new trends to previously deleted trend numbers.

Somehow the regional and Oregon systems got out of sync, but proper record

keeping allowed us to track down the cause of the inconsistencies.


Region
3
Update and append data as submitted by StreamNet 
1.  Fish Distribution:  Work continued on modifications to our Fish Sightings and

participants.  Isolate erroneous or duplicative data and work 
Distribution tables.  In an attempt to work one state at a time, PSMFC and WDFW

with source agencies to correct problems.  Produce 
worked on changes needed from the perspective of WDFW.  The issue of 

downloadable versions of StreamNet databases.   Maintain 
developing standard definitions for the distribution data was not resolved during the 

logs of data submissions and major database changes.
quarter.  Some errors were found in the existing Fish Distribution layer, and these

were reported to the originating agency (WDFW) for correction.

2.  Adult Abundance:  The Data Manager worked to resolve duplicative TrendIDs

submitted by multiple compilers within one agency, and continued to reassign

TrendIDs which PSMFC had entered to other agencies as replacement data was

submitted.  We received new escapement data from ODFW, adding 58 new 

anadromous species Trends and 285 new resident species Trends.   These new 

Trends were comprised of approximately 1000 new escapement count records.

910 existing Trends were also updated by about 2700 additional records.

3.  Hatchery Releases:   No hatchery release data were provided to StreamNet,

yet the topic of how to deal with these data continued to be debated among the

Steering Committee at their quarterly meetings.

4.  Hatchery Returns:  We received 320 new hatchery returns Trends from ODFW,

comprised of about 4500 new escapement count records.

5.  Dams and Fish Passage Facilities:  New dam facility related data was provided

by MFWP near the end of the quarter.  These data will be loaded in the second

quarter.

6.  Hatchery Facilities: Changes to the draft hatchery facilities DEF were made as

per requests from WDFW.    Hatchery facilities data were submitted by WDFW

and loaded.   Hatchery facilities data were submitted by MFWP at the end of this

quarter, but will not be loaded until the second quarter.  Numerous photographs of

hatchery facilities were provided by ODFW, and these were loaded into StreamNet.

Region
4
Examine the StreamNet database for errors and report any 
Work continued on this ongoing task.

found to the appropriate entity for correction.


Objective
3
Task:
3
6/24/02
Page 32 of 58

Region
5
In order to modernize existing data sets, begin converting the
We initiated a project to georeference the Protected Areas and Smolt Density

georeferencing for the Protected Areas and Smolt Density 
Model data from the 1:250,000 scale (river reach) to the 1:100,000 scale (LLIDs).

Model data from river reach numbers to LLIDs.
Work is ongoing as of the end of this quarter. When completed and quality checked,

we should be able to switch georeferencing for these two data types over to the

LLID system.  These two data types are the last ones still using RRNs, so we will

be able to completely move to the LLID approach when this effort is complete.


WDFW
1
Work with regional staff as necessary to assure seamless 
1.  Sikora drafted instructions on how to write SQL statements commonly useful

loading of data into the regional database.   Explore new ways
for exchanging data.

to simplify the instructions to the Regional Manager on how
2.  StreamNet responded to WDFW's November hatchery facility exchange with

to post our data submission and purge any old records that 
three responses delivered over the following two months. WDFW and StreamNet

are now irrelevant to avoid follow-up issues.
swapped information to resolve the trouble caused with the direction to delete a few

hatchery codes.  A few codes are used in an obscure, old and incomplete table

showing Hatchery Production at each hatchery OR the MapCatalog table that tracks

map submissions by BPA.  The MapCatalog table is documented in the exchange

format and WDFW will start directing StreamNet how to clean this table if it will

be affected by any data submission.

3.  The Hatchery Production table is not documented in the exchange format and

WDFW sees little purpose to the table, as is.  O'Connor will initiate an effort to 

delete or replace this table when the WDFW Hatchery Genetic Management Plans 

are finalized.  For now, Sikora and Kinney resolved how to treat each code related

to the MapCatalog or Hatchery Production table.

Objective
3
Data Management and Delivery

Task
4
Data Exchange Standards

Establish and maintain data exchange standards to ensure consistent content and format of data that originate from multiple data sources.

Track adopted and proposed data exchange formats and location coding (including metadata) for data categories described under Objectives

1 and 2.  At the regional level, this task will provide coordination and technical assistance regarding interpretation of database structures

and codes.  At the agency level, this task will provide similar coordination and technical assistance to activities applicable to StreamNet.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Review and comment on DEF issues brought to the Steering 
We reviewed and participated in DEF discussions.

Committee


CRITFC
2
Propose a draft DEF for genetics data to the Steering 
We Presented a draft DEF for a data catalog as part of the prototype 

Committee, based on the application and comments received 
system presented to the Steering Committee.

under Objective 2, Task 7,  job 1.  Work with MFWP on 

development of the draft.


IDFG
1
Working with the StreamNet Steering Committee, maintain 
During Steering Committee meetings, we discussed the fish distribution and

and enhance the data exchange standards as needed.
hatchery returns DEF.  Neither were completed and await further action.


Objective
3
Task:
4
6/24/02
Page 33 of 58

MFWP
2
Work with CRITFC to develop a draft DEF for genetics data 
We sent the MFWP genetics data structure to CRITFC.  Based on 

for adoption by the Steering committee
agreement in Steering Committee, they will continue the work toward 

developing a draft DEF.


MFWP
3
Work with Regional StreamNet staff and Steering Committee
We contributed to work on the DEF for distribution and use at the 

to create a Data Exchange Format for Distribution and Use 
quarterly Steering Committee meeting.  Progress was made, and hopefully 

Type.
we are close to resolving this DEF.


ODFW
1
Participate in the design, development and maintenance of 
1.  Several staff participated in a regional StreamNet meeting at the 

standard codes and data exchange formats. This will occur 
OFWIM conference where fish distribution and documentation data 

through involvement on the Steering Committee and 
exchange formats were discussed.

technical work groups. There is no set schedule for this task, 
2.  Cedric, Jennifer and Jon coordinated to review StreamNet's proposed 

because it is highly dependent on issues facing the Steering 
Data Exchange Formats for fish survey and distribution data in order to 

Committee.
assemble ODFW comments to be submitted to StreamNet. Jennifer 

rewrote table definitions for both the FishSurvey and 

FishHabitatDistribution tables.

3.  Jon investigated implications of proposed changes to the Distribution 

component of the StreamNet DEF. He mapped out conversion from the 

old structure to the new one in regards to UseType and QualityCriteria 

data that will be merged into the new DistTypeID field.

4.  Jon and Jennifer began process of redesigning the distribution database 

to improve field definitions and validation rules. Also sketched out 

additional modifications to meet new agreed upon StreamNet exchange 

formats.

5.  Jennifer, Jon, and Cedric engaged in discussions with Mike Banach 

regarding updates to StreamNet's coding for cutthroat species. We then 

addressed Coastal cutthroat trout coding issues in regards to differentiating

between sea-run, mixed sea-run and resident, and resident only 

populations. Jon also spoke with Sharon Clarke regarding hydrography 

coverages related to cutthroat data development needs.

6.  Jon reinitiated discussion regarding resident distribution data formats 

with Mary Hanson. The next step will be to design some draft data 

structures that can store all the relevant information that we would like to

capture and manage. Once some draft structures are in place then we can 

solicit feedback from appropriate folks within (and possibly outside) the 

agency.


Objective
3
Task:
4
6/24/02
Page 34 of 58

ODFW
2
Develop and propose a DEF for screening data.
Work on this task centered on developing and refining ODFW's FishScreen

Database. This work is being funded by an outside contract, but once our database

structure is somewhat stable, we will be able to develop and propose a DEF to

StreamNet. Susan completed and released Version 1.1 of the Fish Screening and

Passage Program Database along with customized download instructions for

several staff. Subsequent to that, she provided tech support to several Fish 

Screening and Passage Program staff, and periodically synchronized and created

replicated copies of the database for various staff members, and updated the

reporting capabilities of the database.  Susan also consistently reviewed populated

copies of the database for changes that may affect the database reports and the

development of a DEF.


Region
1
Assist with the design and implementation of data exchange 
Regional staff assisted in Steering Committee discussions on DEF changes related

standards as they relate to the spatial aspect of data in the 
to fish distribution, hatchery, and trend locations.

StreamNet database.


Region
3
Enhance the StreamNet data reference system by repairing or
The StreamNet Library at CRITFC provided a Library data dump to the Data

establishing procedures for updating and reconciling data-
Manager.

related references between the StreamNet database at PSMFC

and the StreamNet Library database housed at CRITFC.


Region
4
Maintain and update the StreamNet Data Exchange Format 
Codes were added to the Data Exchange Format for new calculation methods,

as necessary to incorporate additions and modifications 
species/subspecies, run, and habitat use types.  Redundant species codes for bull

agreed to by the Steering Committee.  Record accepted 
trout were detected and corrected.

revisions in the DEF document.  At least one update of the 

DEF document will be made during the year.


WDFW
1
Engage in data exchange format (DEF) discussions.  Lead new
1.  O'Connor engaged in all efforts to finalize the distribution data exchange

efforts to amend the format as warranted when WDFW's 
format, starting with leading the Steering Committee discussion at the October

data cannot be accurately converted.  Provide metadata for 
meeting, continuing it at the November OFWIM meeting, and providing a summary

tabular and spatial data sets according to guidelines adopted by
of decisions-to-date in November to assist PSMFC staff in the finalization process.

the Steering Committee.
Mike Banach hoped to efficiently manage the responses to his latest draft by

submitting it one-by-one to each state.  WDFW was first.  O'Connor and Sikora

reviewed the draft and Sikora prepared and submitted WDFW's response.  It took

some time to learn of the progress so Sikora contacted ODFW's Cedric Cooney 

directly to research their data collection for migration uses and the implications for

WDFW's format suggestion. O'Connor and Graves exchanged information about

the nature of fish distribution records and the problem of overlapping natural 

events, to correct some mutual misunderstandings about how the data are collected

and how they should be represented spatially.

Objective
3
Task:
4
6/24/02
Page 35 of 58

2.  Lensegrav improved WDFW's draft proposal document 

(prxchfrmt*.doc) to change StreamNet's habitat restoration exchange 

format.  We expect to add more to this document at the earliest 

opportunity.  We do not plan to put it before the Steering Committee 

until the formats for other high priority data categories are resolved.

3.  Sikora reminded Banach that the hatchery facility format should allow 

general marine areas as warranted instead of pointing to the Pacific Ocean

for all saltwater events.


WDFW
2
Develop a revised DEF for Hatchery Return data and propose
O'Connor prepared another draft hatchery return proposal for internal 

to Steering Committee
WDFW review.  O'Connor, Woodard and Sikora met on October 1 to 

confer over features needed in the draft. As follow-up, O'Connor put 

together a table listing potential fish disposition categories and polled 

StreamNet agencies to see what data are readily available. The result and 

proposed "plan to move forward" was projected to be ready at the first SC

meeting of the second quarter.


Objective
3
Data Management and Delivery

Task
5
StreamNet Internet Site

Continue to maintain and enhance the existing client-server system to provide access to StreamNet data products through 

the Internet.  The StreamNet home page will continue to be recognized as the project's primary data delivery vehicle.  

Priority will be given to incorporating data developed through Objectives 1 and 2 and providing access to reference materials 

secured through Objective 4.  Appropriate training on the use of the system will be provided through a combination of 

on-line help and in-person training sessions.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

ODFW
1
Recommend and/or take part in review of new products and 
Staff recommended modification of the CRM web site to include in-season 

features.  Provide feedback on content, suitability, 
updates of catch estimates in Columbia River commercial and sport fisheries.

navigability and data currency issues.


ODFW
2
Work with Regional StreamNet staff to link the StreamNet 
We reviewed a paper describing the Col. River Management web site and how it 

website to available Columbia River fisheries information 
might be linked and related to the StreamNet web site.  The informational text is 

(including Columbia River Compact Action Notices, 
now complete but developing the link between the StreamNet database and the 

In-Season Updates, Joint Columbia River Management Staff 
CRM website needs to be completed.

Reports and possibly in-season catch estimates), along with 

informational text to describe each link.


Objective
3
Task:
5
6/24/02
Page 36 of 58

ODFW
4
Manage and maintain the ODFW Natural Resources 
1.  Susan posted: a) two updates of Winchester and Gold Ray Dam fish counts;

Information Management Program website and it's links to 
b) the POS/Web Programmer Analyst job announcement and skill sheet as a

StreamNet.
service to ODFW; c) the 24K Jan.-Mar. 2001 Progress Report and d) the24K

Fish Habitat Distribution Development Procedures Manual.

2.  Susan enhanced the site by adding a fish inventory web site link, adding a link

to the Idaho Fish and Game Department, and added the latest ESA Candidate List.

3.  Susan performed standard site maintenance including updating the various

StreamNet links.

4.  Susan discussed plans for uniting the NRIMP and GIS@ODFW web sites with

Milt Hill.  She created new web graphics and Javascript features for the prototype

site and added links to the ODFW home, fish, wildlife, habitat, news and agency

pages (on all pages of the site), and a link to the Map Projections for the State of 

Oregon (on the Data Standards page). Susan maintained both the NRIMP site and a

prototype merged site pending approval from ODFW to release the merged site.


Region
1
Maintain the GIS Data, Map, and PNW Reach File Internet pages.
We continued to maintain the GIS Data, Map and PNW Reach File Internet pages.


Region
2
Add an internet mapping component to the StreamNet site 
1.  We installed ArcIMS 3.1 (Internet mapping software) on the new StreamNet

to allow users to access StreamNet data through an 
web server.  This included extensive trials and testing to assure working

interactive map interface.  Internet mapping component will 
configuration with other software and hardware elements.  We duplicated

utilize spatial database engine (SDE) technology to improve 
installation on the GIS Specialist's computer for development purposes and wrote

speed and performance, and will utilize ArcIMS software for 
a technical document on how to install and configure ArcIMS in case the procedure

application design and delivery.  Internet mapping 
needs to be repeated in the future.

component will serve at least 2 purposes:  (1) to provide 
2.  We began development of an online interactive mapping application. Work is

users with a vehicle to display and query StreamNet data in a 
ongoing and will continue into future quarters.

spatial format; and, (2) to provide an alternate means of 
3.  StreamNet personnel reviewed an ArcIMS site set up by California Department

entry to access information in the current StreamNet query 
of Fish and Game in order to explore functionality and to generate ideas for how

system.
the StreamNet ArcIMS system could work.


Region
3
Maintain and enhance the look and usability of the current 
1.  This quarter we added new data criteria selection features to the query system

web-based query system.
for NWPPC Subbasins, Old 1990 Subbasins, Regions, and Huc4.

2.  We completed many requested interface and functionality enhancements /

fixes.

3.  We modified the query system look to more closely match the main StreamNet

web site.

4.   A proposal for changing the geographic criteria available (HUC, subbasin, 

county, etc.) in the query system was developed and delivered to the Steering

Committee.  The change was accepted, and will be implemented when possible.

Objective
3
Task:
5
6/24/02
Page 37 of 58

Region
4
Develop and test a new and enhanced web-based query system
Cold Fusion was installed on the new web server and testing with the new 

based on a more open and flexible programming 
web server software (Apache) was accomplished. This provides a solid, 

environment (Cold Fusion).
more open (more than just the programmer can work on it) foundation 

on which to serve StreamNet data.


Region
5
Deploy features of the new flexible query system as 
Regional personnel worked on the functionality and layout of a data 

components are approved by the Steering Committee
category for fish migration barriers.  This task is more complicated than 

expected because we will permit querying by any barrier, or by barriers 

that affect only a selected species.  Significant progress was made, but this 

was not high priority for implementation during this quarter because the 

barriers data  currently contained in the StreamNet database is quite 

limited.


Region
6
Maintain logs of web query history and error events.  Track 
Usage and error logs were maintained and used to track query system usage

and report internet site usage by month and investigate web 
and to trouble-shoot errors encountered.

query system errors encountered.  Assist programmer in 

debugging web query system problems that may be data 

related.  Maintain and upgrade StreamNet web server and 

software.


Region
7
Guide development and enhancement of the StreamNet web 
With the addition of a full-time StreamNet Programmer to the project, 

query system from the perspective of data users.  Review 
many items which had been languishing were addressed.  The programmer 

changes to the web query system to ensure they are 
worked with the old contract programmer to learn the system.  The new 

implemented appropriately and do not create unforeseen 
programmer also worked with the biologist, GIS specialist, and database 

bugs.
manager to improve the query system in many ways.  This work 

continues, guided by the other regional personnel.


Region
8
Complete review of the existing StreamNet HTML pages.  
A full archive of all StreamNet web pages was created in preparation for 

Decide which pages to archive and delete, which to include in 
transferal of the StreamNet web site to a new server.

the StreamNet web site, and which to modify for inclusion in 

the StreamNet web site.


WDFW
1
As time permits, review new products and features of the 
1. Sikora, O'Connor and other staff gave feedback on the initial StreamNet

StreamNet Internet site. Provide feedback on content, 
Forum site.

suitability, navigability and data currency issues, especially 
2. Sikora and O'Connor did an initial review of the Washington state contents of

issues related to providing static or dynamic map capabilities.
the current Online Map Catalog, and provided input as to which maps to remove

and which to retain.


Objective
3
Task:
5
6/24/02
Page 38 of 58

Objective
3
Data Management and Delivery

Task
6
Tool development and maintenance

Provide programming services to project participants to support efficient data entry and transfer.  Tools may be developed at the

regional or agency levels.  Even when developed for within agency use, tools should be shared among all project participants.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Continue to develop the IDFG/StreamNet Fish Information 
We continued a strong commitment to the development of the FIS. The 

System (FIS). The FIS provides data entry and management 
FIS is intended to provide data management and access functionality to 

tools to IDFG biologists. It also provides for an electronic 
IDFG staff, while facilitating the flow of information to StreamNet. We 

flow of data from the field to StreamNet. It ensures data 
are finding that as we  implemented pieces, IDFG biologists are becoming 

integrity, data and coding standards, and an efficient transfer 
increasingly interested and excited about using it. This will aid StreamNet 

of data from the field to StreamNet.
with a much enhanced flow of data.

Specific accomplishments this quarter include:

1. We researched system requirements and web development tools for a 

web-based data query and GIS mapping tools. We intend to implement a 

data query and access system on the IDFG intranet. This will provide 

broad use of FIS and StreamNet data by IDFG staff. We began work 

building an intranet query and access tools and we implemented IIS on our 

server in anticipation of development.

2. The FIS data structure is a complex set of normalized, related tables in 

a relational database management system (SQL Server). Most biologists 

asking for data wanted a simple flat file of data. We have built an 

FIS-Warehouse to provide non-normalized data set for our FIS data.

3. IDFG is slowly migrating from its current Banyan network to a 

Windows2000 network. We started making plans for the  implementation

of a Windows 2000 network system in FIS.

4. IDFG/StreamNet provide coordination of dataset and interface design, 

administered and maintained the FIS, including the IDFG/BLM challenge 

cost share program and Collection Permits.

5.The IDFG/StreamNet programmer prepared an interface for editing and 

defining trends. This is in response to errors we found in the redd count and

hatchery return data sets.  Also prepared an interface tool that allows the display

of trend locations and provide recommended trend locations and statistics.

6. Working with the Idaho Supplementation Studies, we enhanced the 

Juvenile Trapping and Spawning Ground Survey programs.

7. We began development of a hatchery facilities data entry and 

maintenance module to the FIS.

8. In preparation of moving data to PSMFC,  we began research and 

development of a data transfer method using XML. We implemented an 

XML solution to transfer ISS data to the FIS.


Objective
3
Task:
6
6/24/02
Page 39 of 58

MFWP
1
Maintain and enhance the edit/entry interface for fisheries 
This work is ongoing with the USFS.

survey data distributed to individuals with a MFWP 

Collector's permit, including federal land management 

agencies.


MFWP
2
Explore creating a complete user interface for MFWP 
We worked with some individual biologists on local programming needs.

biologists, preferably a web based system; standardize look-up 

tables across the state.


MFWP
3
Maintain U of M system for genetics analysis input, Future 
Work is ongoing.

Fisheries for restoration project data entry, and other 

interfaces upon request if they relate to StreamNet workplan.


Region
1
On an as-needed basis, update or develop tools to assist with 
No work was done on data entry tools this quarter.  However, the 

data entry and data management.  Assist StreamNet data 
programmer built, tested, deployed a web-based discussion forum for 

compilation agencies with trouble-shooting, modification, or 
StreamNet staff.  The forum rapidly became a primary tool of 

development of data input interfaces.  Tools might include 
communication among all StreamNet staff at both the regional and 

input interfaces, error checking routines, geographic locators,
cooperator levels for discussing and resolving technical issues.  This tool 

 etc.
helped to reduce email clutter and also kept discussions organized by topic.


WDFW
1
Review and give feedback on StreamNet's tools.  Also build 
1.  Lensegrav searched websites for Paradox and dBase import patches for 

internal tabular and GIS tools and procedures to efficiently 
MS Access. 

manipulate data , including the conversion of WDFW's 
2.  Sikora tested StreamNet's EventCompare tool and to date has found at 

Paradox data to MS Access.
least two uses for it.  We downloaded the NHD conversion tool but have 

yet to test it.

3.  Late November, Sikora defined the need for Brown to create a tool to 

merge event records that never should have been split into more than one

record.

4.  WDFW staff updated the EventMapper 100K hydro layer with a new 

version sent by David Graves in October.  Initial tests indicate the new 

layer is a solid product.


Objective
3
Task:
6
6/24/02
Page 40 of 58


Objective
3
Data Management and Delivery

Task
7
Data / Information Requests

Receive and respond to requests for data and information, source materials, and custom products.  Response to requests will be

honored within the limits of available resources, with priority given to information requests having direct relevance to the Fish and

Wildlife Program.  Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural

resource management activities.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Respond to requests for data and queries of the 
1. We received one month of funding for our data manager from USFWS to

IDFG/StreamNet Fish Information System. These requests 
update our bull trout data in the FIS with local data sets from IDFG Salmon and

come from a variety of sources, federal agencies, state 
Clearwater offices. The data were to be used in development of recovery plans

agencies, and private consultants. All data requests will be 
and identification of critical habitat. We provided the data to USFWS in a combined

logged for reporting.
Access database and ArcView project that allowed mapping the data.

2. We filled 15 data requests that came directly to our office. The requests consisted

of 10 species lists, 3 sets of shapefiles of streams, wetlands, and fish distribution,

and 2 technical assistance (fish species status list, river mileage calculations).


MFWP
1
Receive and respond to requests for data, source materials, 
We filled 20 requests from the Fisheries Division, most from BPA funded 

and custom products.  Respond to requests within the limits 
project in Kalispell.

of available resources, with priority given to information 

requests having direct relevance to the F&WP.


ODFW
1
As requested, consistent with other deliverables in this 
1.  Jon responded to two NMFS requests for fish distribution data. One was for 24K

contract, receive and respond to requests for data, source 
Coho data on the coast and the other was for Mid-Columbia River steelhead data.

materials, technical training, and custom products.
He also responded to an internal ODFW request for westslope cutthroat trout

data.  Jon filled requests for Umpqua 24K streams data, "tributary-to" data for all

100K streams in Oregon, and for an Oregon Salmon Distribution poster.   In 

addition he provided his OFWIM Salmon Distribution Data Standards PowerPoint

presentation to the Virginia Dept. of Game and Inland Fisheries.

2.  A total of 19 data, 3 document, 1 map, and 8 'other' requests were answered

during this quarter. A detailed list by requester and request type can be made

available upon request.  Library-specific document requests are summarized under

Objective 4, Task, 3, Component 2.  Also, 2,423 data downloads were made from 

the ODFW FTP site during this quarter.


Region
1
Respond within one day whenever possible to users who 
Regional staff responded to 55 requests for information or help during the quarter.

request information or assistance.  Requests may be for help 
Twenty five of these requests were GIS or map-related.

in navigating the StreamNet web site to find desired 

information, help in learning to use the on-line data query 

system, help in finding information not contained in 

StreamNet, assistance finding GIS layers, providing unique or 

customized data, or a variety of other types of requests.


Objective
3
Task:
7
6/24/02
Page 41 of 58

WDFW
1
Generate maps, data reports, and electronic copies of data 
All staff responded to data requests and documented them in a detail database

sets as requested.  Provide PRIORITY data support for 
available on request.  Over two dozen major requests were handled this

subbasin assessments and other new elements of the NWPPC 
quarter, including dataset dumps for gamefish stocking, anadromous fish

Fish & Wildlife Program, within existing resources.
releases, spawner survey and other fish counts, fish distribution data (particularly

bull trout), and age data.  Maps of fish distribution/use continue to be popular,

along with lake maps (where available).  A new development this quarter was

an increase in requests for ArcView-related products, such as shapefiles for both 

map base layers and fish data layers, and custom ArcView maps (our first ever).


Objective
4
Library / Reference Services

Provide professional library services to the Columbia Basin's fish and wildlife decision-makers, planners, managers, and researchers by acquiring and cataloging StreamNet source documents and other related material; and by providing open and efficient access to these materials


Objective
4
Library / Reference Services

Task
1
Collection Development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document

data sources, Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies,

interested parties, and other libraries.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Coordinate source material submissions for data compiled by 
The Library received and cataloged a shipment of materials from 

participants.
California.


CRITFC
2
Develop collection of materials related to the Columbia 
The StreamNet Library added approximately 650 new records to the 

Basin, including reports from other Fish and Wildlife 
library collection.

Program projects, other agency documents as they relate to 

the Basin, and other published and unpublished materials as 

requested by clients.


CRITFC
3
Maintain and develop a collection of journals related to 
We renewed subscriptions to the usual journals, and also renewed 

fisheries and aquatic sciences as well as other related scientific
memberships to several societies.  The library received over 190 items 

topics.
through duplicate exchange to fill in gaps in serial collections.


CRITFC
4
Format the library reference table of StreamNet documents 
We began working with Bill Kinney on updates to reference tables and 

for inclusion in the StreamNet database.  New updates will be 
formats for library records.

sent to the regional database monthly after that.


Objective
4
Task:
1
6/24/02
Page 42 of 58

MFWP
1
Update the StreamNet library with references and publications
No updates were requested.

from the Fisheries Division Library on an annual basis.


MFWP
2
Collect and catalog supporting references to document the sources
Work is ongoing.  We still need to work with the FWP library to 

of the distribution information and other data types developed
incorporate all fishery papers, not just internal documents.

under Objectives 1 and 2, and to connect the data to references.

Submit updated references to the StreamNet Library.


ODFW
1
Update library bibliography of ODFW, Fish Commission, and 
Gloria continued to enter reports into the Library Bibliography, including 

Game Commission reports with historic and current publications.
26 electronic reports.


ODFW
2
Provide originals/copies of all documents and reports 
1.  Shannon finalized and submitted a Library submission to StreamNet in 

referenced in the compilation of new StreamNet data 
early October.

holdings, but not already housed in the StreamNet Library.
2.  Bill and Shannon worked on creating a Reference Submission database 

to enhance user productivity when submitting new or updated references 

to StreamNet. They also created an automated Library Submission process,

that creates the library reference submission in a report which can be 

printed and sent to StreamNet. This system results in an easier and faster 

submission process. The database also allows for a lot fewer errors to be 

made in the reporting process.

3.  Shannon did a reference table comparison between Oregon's reference 

table, StreamNet reference table, and the StreamNet library set. She 

identified some missing references in both the StreamNet table and 

StreamNet library table, and sent Bill Kinney reference information he 

could use to update the StreamNet table. She identified the missing 

reference data from the StreamNet library as North Coast distribution 

documentation and some barrier materials. These references will be 

submitted, or possibly resubmit, to the library.


ODFW
3
Organize and submit to the StreamNet library all references 
A Library submission was made to StreamNet in early October.

related to the data developed under Objectives 1 and 2.


Region
1
Work with the StreamNet Library to search the library 
Gary Christopherson, former StreamNet employee, made available a box 

holdings for non-durable electronic reference materials 
of books and reports that may be useful to the StreamNet Library.  These 

(mainly floppy disks).  Archive any files found on CD.  Print 
materials were obtained by PSMFC staff and sent to the StreamNet 

hard copies if appropriate.
Library for processing.


WDFW
1
Engage in discussions to finalize procedures to submit spatial 
Sikora sent a replacement reference for the Hatchery Facility Database 

data references.  Continue to collect documents used as source
and researched the hatchery returns references identified as missing in Bill 

materials for any data in Objectives 1 and 2. Documents will 
Kinney's email.

be assigned reference numbers and forwarded to the 

StreamNet library as per established SN guidelines.


Objective
4
Task:
1
6/24/02
Page 43 of 58

Objective
4
Library / Reference Services

Task
2
Provide Access to Collection

Provide user access to the materials described in Task 4.1 by providing facilities for storage of paper and electronic copies of documents,

an online catalog of all documents in collections, and staff to answer location questions and respond to requests.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Provide and maintain an appropriate facility for the storage 
The lease with Ashforth-Pacific, Inc. for library space was continued.  We

and public use of the StreamNet Library collections.
also continued work from last year on space expansion plans.


CRITFC
2
Catalog and organize the materials for ease of use by clients 
We continued integration of all materials into one subject oriented 

and staff.
collection.


CRITFC
3
Provide access to the catalog of materials via the Internet 
The catalog was made available through the Internet.  We upgraded the 

and update the online catalog on at least a monthly basis.
search and record display pages.  The catalog was updated monthly.


CRITFC
4
Develop and execute a plan to place electronic documents in 
We began developing a plan for virtual library materials.  We also added 

the catalog and on the library website.
electronic access to several StreamNet documents.


CRITFC
5
Develop and keep schedule of open times and reference desk 
Scheduled reference desk hours and open times were posted on the library 

staff hours.
website.


Objective
4
Library / Reference Services

Task
3
Library Services

Manage the StreamNet Library and provide library services to the StreamNet user community, Fish and Wildlife Program, and the

general public.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Provide information and reference services to library clients
We answered over 25 requests for information from clients.


CRITFC
2
Provide information about services and hours to library 
We kept webpages updated with information about hours and holidays.

clients via print and Internet


CRITFC
3
Provide interlibrary borrowing services for library patrons to 
We answered over 160 requests for materials from clients for materials 

access materials not yet owned by the StreamNet Library.
not owned by the StreamNet Library.


CRITFC
4
Provide access to hardcopy and electronic files of draft and 
The 1990 subbasin plans are now in residence on the library server and 

final documents related to subbasin planning and the NPPC 
continue to have a separate section in the library website.

amendment process.


Objective
4
Task:
3
6/24/02
Page 44 of 58

ODFW
1
Enhance, maintain, and update ODFW Library software and 
Bill spent time working with Gloria to get her new laptop set up and to 

procedures to ensure adequate tracking of information 
transfer information from her old computer to her new one. This included

requests, key word searches, and easy comparison to the 
 the bibliographic software.

StreamNet Library holdings.


ODFW
2
Respond to requests for ODFW documents and other source 
Provided 107 documents pertaining to Klamath Basin for the Dept of 

materials through the ODFW Library.
Justice to make copies. In addition, Gloria provided 502 hardcopy 

documents and 14 electronic documents to 48 individual users (12 

additional users were referred to other sources) during the quarter.


Objective
4
Library / Reference Services

Task
4
Inter-library Coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other collections

that will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Provide interlibrary lending services for other libraries to 
We provided over 50 items to other libraries.

access the library's unique collection


CRITFC
2
Maintenance of memberships in appropriate library and 
Memberships in library organizations were renewed.  We continued 

subject-related associations.  Ex. IAMSLIC, NRIC, OFWIM, 
serving as webmaster for SLA-Oregon Chapter.  We presented a technical 

etc.
paper and workshop at the OFWIM annual conference.


CRITFC
4
Coordinate with other StreamNet libraries, library clients and 
We provided information to clients referred by Gloria Bourne at the 

other libraries to improve service to clients and limit 
ODFW StreamNet Library.

duplication of effort.


CRITFC
5
Work with subbasin planning groups and TRTs to identify 
The Council's subbasin planning process has not yet begun, so no work was

modifications and new uses to make information related to 
 accomplished on this specific task.

these processes easier to retrieve


ODFW
1
Provide an index of Oregon Fish Commission, Oregon Game 
Gloria provided 7 documents to the StreamNet Library which fill gaps in 

Commission, and Oregon Wildlife Commission processed 
their Oregon Game Commission report holdings.

reports to the StreamNet Library for the purpose of 

identifying documents that are not currently within library 

holdings.


ODFW
2
Coordinate with the Oregon State Library system to enhance 
Gloria set up 3 more ODFW employees with State Library SmartOrGov 

access to published periodicals, journals, and other documents 
services.

for StreamNet users.


Objective
4
Task:
4
6/24/02
Page 45 of 58

Objective
5
Services to Fish and Wildlife Program Activities

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife Program projects


Objective
5
Services to Fish and Wildlife Program Activities

Task
1
Data and services to support the Subbasin Planning effort

Within existing data categories and staffing levels and as workloads permit, assist Subbasin Planning efforts by 1) providing data in

formats that fit planner needs, 2) working with planners to locate data within the StreamNet database and contributing projects'

databases, and 3) advising and assisting planners on data management issues.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Provide described services to CRITFC staff working on 
The Council's subbasin planning process has not yet begun.  References 

subbasin planning and NMFS' TRT groups
were provided as requested by participant on the TRT.


IDFG
1
Provide data and related assistance to subbasin planning 
1.  We provided queries of the FIS to biologists developing subbasin summaries

efforts in Idaho. IDFG has the lead role in a number of 
for the Palouse, Salmon, Boise-Payette-Wesier, Upper Middle Snake, Upper

subbasins and we will provide support services, including 
Snake Headwaters, and Closed Basins subbasins. The data consisted of presence

tabular reports and GIS services to these subbasins.
absence tied to LLID and abundance measure where available.

1.  IDFG had the lead role in preparation of subbasin summaries for the  

Boiise-Payette-Weiser, Upper Middle Snake, Closed Basins, and Upper Snake

Headwaters subbasins.  Using funding supplied by subbasin planning, IDFG

StreamNet staff used FIS data and StreamNet equipment to produce a variety of

maps that were included in the summaries. Map types included: location, land

use, land cover, vegetation, climate, stream gauges, dams, lithology, managed

areas, aquifers, ecoregions, fish distribution, rare plants and animals, protected

areas, and 303(d) listed streams.

MFWP
1
Work with Montana's CBFWA representative involved with 
No requests are outstanding.

subbasin planning and provide data, map products and 

assistance as needed.


ODFW
1
Participate in Subbasin Planning meetings and provide data, 
1.  Cedric attended the initial System-wide Provincial Review meeting held

advice, and related assistance to subbasin planning efforts in 
 in Portland.

Oregon (within existing resources and as workloads permit)
2.  Cedric contacted Tony Nigro regarding ODFW's strategy for responding

to the system-wide provincial review. He informed me that Ron Boyce was

still leading this effort, but that nothing had been done thus far.

Objective
5
Task:
1
6/24/02
Page 46 of 58

Region
1
Generate customized maps and information for subbasin 
Regional staff developed a set of subbasin maps for the subbasin planning 

planners from StreamNet data or other data provided by the 
component of the NW Power Planning Council, to be used on their web 

planners, as long as this work can be accomplished within 
site.  These included low resolution and high resolution maps of all 

existing resources.
subbasins and provinces for printing and/or online selection, and a custom 

low-resolution base map of each subbasin for use on their individual 

subbasin pages.


WDFW
1
Participate in Subbasin planning meetings and provide data 
1.  Smith worked to update the Columbia River Subbasin reports that 

and advice as needed.
WDFW compiled long ago for StreamNet, yet abandoned when StreamNet

started focusing on database submissions.  Water uses, historical releases, 

presence/absence and any relevant information are being added to these 

reports to update and describe the basin better.  Woodard worked with the 

fish data compilation for these reports.  Chum and Chinook data for 

tributaries below Bonneville Dam were delivered to Ron Roler along with 

past reports on these tributaries.  Ongoing consultation of historical data 

on these tributaries continues and data is delivered or manipulated as needed.

2.  Woodard downloaded ArcExplorer from the Internet to learn how to 

create maps for the region/project and lay presence/absence data on top 

of specific layers.  GPS units were used to gather beginning and ending 

points for index areas on streams, and points where Chinook, Coho and 

Chum had spawned or were observed in the Subbasin.  Woodard took this 

data and loaded it into ArcExplorer and ArcView to determine how to 

more efficiently collect and store such information and be able to deliver 

this to StreamNet.


Objective
5
Services to Fish and Wildlife Program Activities

Task
2
Support monitoring and evaluation efforts

Assist in the development of products that contribute to the monitoring and evaluating (M&E) of Fish and Wildlife Program 

effectiveness.  Specific areas of involvement will include:  participation in Program-related monitoring and evaluation work 

groups; periodic re-evaluation of the StreamNet data plan to ensure consistency with M&E needs; and design of databases 

and formats to house and disseminate M&E information to the degree possible under the existing contract.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Work with NMFS, NWPPC and subbasin planning groups to 
We co-authored summary reports on M&E needs and plans developed as 

identify M&E needs and plans
part of the Council's Mainstem and System Wide Provincial Review.  

These summaries will be the basis for future project selection and funding 

for the next three fiscal years under the Council's Fish and Wildlife 

Program.


Objective
5
Task:
2
6/24/02
Page 47 of 58

Objective
5
Services to Fish and Wildlife Program Activities

Task
3
Support for and participation in regional data management initiatives

Work with regional entities to promote and implement sound data management programs that ensure efficient organization,

management and delivery of pertinent fish and wildlife related information within the Columbia Basin.  Efforts may include

determination of regional data needs, identification of obstacles and challenges to effective regional data management, and 

development of recommendations and will take place in a collaborative atmosphere.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

ODFW
1
Participate in discussions and offer solutions related to 
Jon met with BPA Fish and Wildlife Program staff to view an ArcIMS 

Columbia River Basin database management and information 
application that they have developed to serve GIS data in support of 

distribution issues, as needed.
subbasin planning. Their application is essentially "out of the box" 

ArcIMS for the purpose of enabling viewing and download of GIS data.


Objective
5
Services to Fish and Wildlife Program Activities

Task
4
Archive function for regional data sets, as requested

Work with regional entities to aid in the capture and distribution of data generated through Fish and Wildlife Program activities

and to help determine the most appropriate means of storing and disseminating them.  Where data do not fit in existing StreamNet

data sets, develop archive functions to at a minimum make data available 'as is', regardless of their current form.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

All
1-2

No work was performed on this task by any of the projects this quarter.

Objective
5
Services to Fish and Wildlife Program Activities


Task
5
Data and services as requested by other FWP participants

In consultation with CBFWA, the Council, and BPA, StreamNet will provide technical assistance and data services to Program projects as

requested, to the degree possible under the current contract.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Provide technical assistance to fisheries projects in IDFG. 
1. IDFG/StreamNet has developed a close relationship with the FWP funded Idaho

Under current funding from both the F&WP program and 
Supplementation Studies. We worked with ISS to continue development of a 

IDFG, we are very limited in our ability to provide this 
spawning ground database and interface for redd count and carcass count data.  We

assistance. Assistance will generally be focused where there is 
also continued to develop the juvenile trapping system.  Both systems were used on 

some mutual benefit to both StreamNet and the other project.
a prototype basis by ISS this past field season. They found them very useful and we 


have worked with them to fix bugs and add enhancements.  Both system allow data 

entry by field biologists and data maintenance by the project coordinator.  Data are 

then electronically transferred to the FIS and made available to StreamNet.


Objective
5
Task:
5
6/24/02
Page 48 of 58

2. We also worked with another IDFG project, a BLM Challenge Cost Share project

to compile historic data from IDFG regional offices.  In the past we developed a 

database and interface, plus the Fish Tools ArcView application for their use. 

During this quarter, we monitored and administered the database and interfaces for

the project. These data come directly into the FIS and are available to StreamNet.

3. Two other systems that IDFG/StreamNet has developed in the past for IDFG are

a collecting permit system and fish reference system. We provided administrative

and technical support to the Fisheries Bureau for both systems as they continuously

entered data into the FIS.

4. IDFG/StreamNet staff worked with the Upper Snake River Stock Assessment

Program to ensure the compatibility of their resident fish data for the FIS and

eventually StreamNet. We also worked with the IDFG Salmon regional office

to incorporate LLID and GPS coordinates into their stream survey database.  This

will facilitate the eventual incorporation of their data into the FIS and StreamNet.

ODFW
1
In consultation with CBFWA, the Council, and BPA, Oregon 
1.  Cedric accompanied Leah Gorman to Seattle to demonstrate the TRT Database

StreamNet staff will provide technical assistance and data 
to NMFS staff, and to pursue funding for and answer questions about future efforts.

services to Program projects as requested, to the degree 
2.  Cedric coordinated with PSMFC, NMFS, and NWPPC staff in an effort to hire

possible under the current contract.
Stacy Carpenter to replace Leah Gorman on the Willamette-Lower Columbia TRT

Viable Salmon Population Project.

3.  Bill prepared the VSP Database backend for delivery to NMFS, deleting all test

information and populating the database with real data.  Final adjustments were 

made to the database in the User Interface and database management areas.  The 

database was delivered in early December.


Region
1
Respond to requests to StreamNet from F&WP participants
During the quarter we completed compilation of data on adipose marking of

for data, maps, GIS products or general assistance. Provide
hatchery fish as requested by Power Planning Council staff.  A revised report 

assistance, including custom map work where feasible.  Direct
with revised maps was prepared and presented to the Council at their monthly

users to other resources if requests exceed project capabilities.
meeting.  


Objective
5
Task:
5
6/24/02
Page 49 of 58

Objective
5
Services to Fish and Wildlife Program Activities

Task
6
Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas dataset, b) archive the official version as a historic

record, and c) in consultation with the Council, respond to requests for information concerning Protected Areas

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

MFWP
1
Exchange Montana's Protected Area database, which has been
Montana's Protected Area database, converted to LLID, was exchanged to

 converted to LLID stream routing.
 the StreamNet database.  A conversion was done so that Regional Staff 

didn't have to do anything to the coverage.


Region
1
Maintain the Protected Areas database within the StreamNet 
The Protected Areas database was maintained.  In addition to routinely making

database
this database available on the StreamNet website, we initiated a project to

convert these data from the 1:250K River Reach referencing system to the

1:100K LLID system (see Objective 3, Task 3, Job 5).


Objective
6
Project Management / Coordination

Provide effective leadership that ensures the production of high quality products targeted at critical applications and the development of these products in a timely, cost-effective manner.


Objective
6
Project Management / Coordination

Task
1
Manage project activities

Administer all aspects of the project at the regional and sub-contractor levels, including oversight of budget, personnel, work

statement preparation and implementation, coordination among participating agencies, active participation in steering committee

work, and project reporting.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Attend and participate in Steering Committee meetings
Phil Roger participated in all Steering Committee discussions.  

Presentations were given on the status of regional activities related to 

information management and on a prototype genetics catalog application.


CRITFC
2
Effectively administer the CRITFC StreamNet project
Normal project management was provided.  Phil oversaw transition 

between fiscal year contracts, including final budget adjustments and new 

proposal development and implementation. Staff evaluations were completed.


Objective
6
Task:
1
6/24/02
Page 50 of 58

FWS
1
Represent FWS in Steering Committee meetings.  Produce 
Steve attended and participated in the Steering Committee meeting.

quarterly reports w/in 30 days of quarter end.  Produce FWS 

component of FY2001 final report.  Create FWS StreamNet 

budget & statement of work for FY2003.  Contribute FWS 

portion of Project Renewal documents.


IDFG
1
Prepare budgets, work statements, and progress reports
The IDFG StreamNet project coordinator prepared the FFY 2002 budget and

statement of work for IDFG/StreamNet. He also prepared quarterly reports.


IDFG
2
Provide project management and staff supervision for IDFG 
The IDFG StreamNet project coordinator provided personnel supervision for not

StreamNet.
only the IDFG/StreamNet staff, but additional staff in IFWIS. He also managed

work flow, providing a special emphasis to leverage StreamNet as much as

possible with other projects that were assigned or made available.


IDFG
3
Participate in Steering Committee activities, including 
The IDFG StreamNet project coordinator was an active participant in 

Steering Committee meetings, project direction, and data 
steering committee meetings and DEF development.

exchange format development.


IDFG
4
Participate in and provide for IDFG StreamNet staff 
1. IFWIS staff attended training on Intro. to VB for ArcGIS and Intro. to ArcGIS.

appropriate professional and technical development. This 
Costs were covered with non-StreamNet funds, but the training benefits StreamNet

includes technical training and participation in professional 
because all staff contribute to StreamNet objectives.

organizations and conferences.
2. The IDFG StreamNet project coordinator was the chairman of the 2001

Northwest GIS Users Group Conference in Sun Valley, Idaho on October 8-12,

2001. He became the user group president at the conclusion of the conference.  The

conference had approximately 250 attendees that were GIS professionals from

across the Pacific Northwest. The conference provided training, a vendor show,

plenary session and concurrent sessions.

MFWP
1
Provide normal supervision of Montana StreamNet staff and 
1.  The annual Statement of Work for Montana was completed and sent to

project. Produce quarterly reports within 1 month after the 
regional staff.  

end of each quarter. Produce final report within2 months of
2.  We had a full staff meeting in Kalispell in December and laid out work 

the end of the contract period.  Participate in Steering
for the fiscal year.  

Committee meetings.  Collaborate on developing a final
3.  We attended the 2 day Steering Committee meeting in Seattle in October.

detailed Statement of Work for FY02.
4.  We completed Performance Agreements for all staff except one.


Objective
6
Task:
1
6/24/02
Page 51 of 58

ODFW
1
Administer all aspects of the project for Oregon, including 
1.  Bill and Cedric attended the StreamNet Steering Committee meeting in

budget oversight, personnel, work statement preparation, 
SeaTac on Oct. 25 - 26.

staff work plan preparation, project implementation and 
2.  Reports and SOW:

coordination, reporting, and participation with the Steering 
Oregon finalized and submitted the 2001-3 Quarterly Report for StreamNet.

Committee and technical issue working groups.
Most staff submitted their StreamNet fourth quarter report and request log.

Cedric reviewed and commented on StreamNet's draft 2001-2 Quarterly Report.

Cedric completed development of the Oregon StreamNet 2002 Statement Of Work

and budget, and submitted it to Bruce Schmidt. Several Oregon staff provided input

regarding potential work components and budget considerations, including

Columbia River Management staff.

Cedric completed the final review of the overall StreamNet 2002 SOW 

and submitted comments to regional staff.

3.  Training:

Shannon attended beginning and advanced PowerPoint workshops. She created a 

disk of information to use in the class to make a presentation.

Shannon worked on becoming more familiar with the grant writing process by

reading literature on the subject. 

Shannon attended a SAS workshop at the OSU Forestry BLDG. 

Cedric, Jon, Jennifer, Bill, and Shannon attended the Organization of Fish and 

Wildlife Information Managers Annual Conference in Portland, titled "Data 

Standards from A-Z".

Jon attended the morning portion of an all day ArcView 8.1 seminar. It served as a

valuable clarification of how the various pieces of the current software puzzle all

fit together, and provided good insights to the new suite of editing tools.


4.  Library:

We finalized a memo for Dave McAllister's signature describing the services 

provided by Gloria and the Library and soliciting funds to keep the Library

operational through the biennium and beyond.

Shannon worked on applications to procure Library renovation grants, and spent

time at the Portland library identifying Library funding sources in the grant section

and by using 'The Funding Center' CD-ROM. She drafted and submitted four 

Library funding proposals.

5.  Hardware/Software/Equipment:

We contacted Bill Kinney regarding the ordering of a new printer for the office and

a laptop.  Bill agreed to purchase the Lexmark printer after we discussed issues

about it.  He also ordered the Dell model notebook we spec'd out.

Susan and Cedric investigated the costs of hardware needed to conduct video

conferencing with remote staffers and for future StreamNet meetings.

6.  Personnel:

We finalized the interview schedule and conducted interviews for our ISS-4 GIS

Analyst position.  We are now awaiting permission from DAS to fill the position.


Objective
6
Task:
1
6/24/02
Page 52 of 58

Region
1
Project Administration:  Perform ongoing administration of 
1.  Routine project administration continued.  

the StreamNet project, to include budget development and 
2.  The project proposal for FY-02 was submitted, but approval was delayed.

tracking, contract monitoring, personnel functions, 
The initial proposal was developed to provide full funding for all core staff 

inventory control, etc.
members, resulting in an increase in the requested budget above the basic COLA.

StreamNet was included in a CBFWA list of projects that needed increased budgets,

but no decision was made on our request, and we started the year on a level funding

trajectory until the Council has time to review the details of our full budget request.

3.  Project staffing at the regional level at PSMFC was brought to the full level at

the end of FY-01 with the hiring of Greg Wilke as the project programmer.  This

significantly increased project capability by substituting a permanent staff person

for the higher salaried, part time contract programmer used previously.  This change

eliminated delays caused by competing work assignments for the contract 

programmer and increased responsiveness to project needs.  Initial activities this

quarter included new employee orientation and instruction on the StreamNet query

system.  It is important to note, however, that all staff positions are now filled, but

three positions (programmer, GIS specialist and fish biologist) are supported for 

only 9  months each by the StreamNet contract.  These individuals need to spend

1/4 of the year working on other, non StreamNet, contracts.

Region
2
Reporting:  Submit quarterly progress reports to BPA within 
A data entry form was developed for input from the cooperating projects to enter

one month of the end of each quarter and submit an annual 
data for the FY-01 Annual Report.  This work was a lower priority than work to

report within two months of the end of the fiscal year.
finish the FY-02 project proposal and gain approval of the budget.  Thus, input

into the annual report was delayed into the next quarter.


Region
3
Maintain effective relationship with the StreamNet Steering 
The fall Steering Committee meeting was held near SeaTac on Oct. 25-26, 2002,

Committee.  Organize and conduct quarterly Steering 
hosted by WDFW.  Key elements of the meeting included: Demonstration of the

Committee meetings to facilitate project oversight and 
IDFG Fisheries Information System, which is an internal agency database 

setting direction/goals.  Coordinate regional project activities 
developed by StreamNet used to capture and manage data from agency biologists; 

with Steering Committee involvement and direction.
Report on the success of the Willamette VSP data project by ODFW; Work on

developing a common approach for fish distribution data; Review and discussion

of 2002 work statement in light of delay in budget approval; and, Planning for the

Mainstem/Systemwide Province Review.


WDFW
1
The WDFW StreamNet state coordinator will participate in 
1.  O'Connor, Sikora, Lensegrav and Woodard planned and hosted the Oct. 25-26

all Steering Committee and StreamNet Project management 
Steering Committee meeting in Burien, WA (near SeaTac).  Staff provided input

activities, including meetings and follow-up work assignments
to the WDFW work update, delivered by O'Connor/Sikora at the meeting. Sikora

(progress reports, Statements of Work, budgets).
revisited with Woodard on how to re-organize his reports of work accomplished.

2.  O'Connor and Sikora prepared the budget and work plan for FY2002 and made

timely submittals of the FY2001 Q4 Report, draft FY2001 Annual Report (to be

finalized next quarter), justification for FY2002 COLAs, and responses to requests

to review/modify the new work plan template eventually adopted for StreamNet in 

FY2002.


Objective
6
Task:
1
6/24/02
Page 53 of 58

WDFW
2
The state coordinator and the state data manager will jointly 
1.  All staff were asked to clean the WDFW server again due to space issues and

manage all aspects of StreamNet in WDFW, including budget,
Jeff Parkhurst tuned-up Sikora PC's.  Oddly, she's experiencing more problems 

personnel, work scheduling, and product delivery.
since the tune-up yet they could be due to the new re-writeable CD or abCD

software that was added near the same time.  Lensegrav loaded software on the

new laptop PC.  O'Connor and Sikora notified IS staff of DOE's virus declaration

for a *.exe file Sikora passed to them.  The warning proved to be only overly

cautious language. Lensegrav established a Virtual Private Network (VPN) account

and the necessary software for working at home 1 day a week.

2.  Lensegrav ordered Advanced File Organizer (AFO) software so staff could 

easily document files and he attended a two day class on technical writing 

(Technical Writing: Tricks of the Trade).  Lensegrav also researched the BC

Fisheries website and documented his findings.  Sikora has yet to check the website

herself or review this document. 

3.  All staff attended the WDFW Director's Roundtable meetings.  Sikora attended

O'Connor's October 12 meeting to brainstorm ideas for a unit work plan. Following

the meeting, Sikora talked with Jeff Parkhurst on the procedures to establish data on

the WDFW website so we could also advertise when we need help with 

information.  Sikora reviewed O'Connor's draft work plan and instructions for

Burns to mine information from the Stream, Lakes and Fisheries Database.  This

quarter we received a noteworthy increase in requests to tutor other WDFW staff

in how to operate software or run database routines.

4.  O'Connor and Sikora performed standard work planning and time management

tasks for supervised StreamNet staff.


Objective
6
Project Management / Coordination

Task
2
Participate in Fish and Wildlife Program development activities

Work with regional entities to assist in the area of data management as requested to support development of Fish and Wildlife Program

projects and programs.  Organize, facilitate, and/or participate in appropriate coordination meetings with BPA, CBFWA, the Council, ESA

officials, ISAB/ISRP, and/or staff and management of participating organizations to identify ways StreamNet can effectively contribute to

the Fish and Wildlife Program (FWP) and facilitate  capture and dissemination of data.  Participate in advisory groups, task forces, and

other groups whose purpose is enhancing the effectiveness of the Fish and Wildlife Program and its data development activities.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Work with NWPPC and related agency staffs to improve 
Phil Roger worked with Council staff and contractors to include data management

data management services to the region
functions in draft work statements for subbasin planning.  He worked with the

Oregon Coordinating Group on similar issues but focusing on division of 

responsibilities between a state technical assistance team and local subbasin groups.

He kept Steering Committee apprised of developments and status.


Region
1
Work with regional entities to contribute data management 
PSMFC assisted ODFW personnel (non-StreamNet) working on their 24K

expertise with development of activities within the scope of 
hydrography project with how to submit references to the StreamNet library.

the Fish and Wildlife Program.


Objective
6
Task:
2
6/24/02
Page 54 of 58

Objective
6
Project Management / Coordination

Task
3
Coordinate with other related activities

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities beyond

the Council's Fish and Wildlife Program to identify means for collaborative data collection, storage, and dissemination.

Collaborative data activities will include tribal fishery programs within the Columbia Basin, federal land managers’ fishery

programs, state fish and wildlife agencies, and, with respect to water use and stream development, state water resource

management and environmental quality agencies.  Collaboration with coast-wide and private data collection/compilation efforts

will be pursued when this supports overall project goals.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

IDFG
1
Coordinate and collaborate with other organizations, 
We continue to focus our efforts at developing an efficient flow of data 

including federal, tribal, state, and local governments and 
from IDFG by providing data management tools that match StreamNet 

private organizations. Such coordination and collaboration 
data standards. Some of those projects, in particular Idaho 

will be selected and conducted in such a manner as to provide 
Supplementation Studies, includes federal and tribal biologists. They have 

benefit to IDFG and StreamNet database systems or to 
had an opportunity to listen to what IDFG biologists say about our tools. 

distribute StreamNet data.
In the future, we will be trying to expand our support of ISS to include 

these other agencies and therefore capture all ISS data.


MFWP
1
Maintain communication between state and regional entities
Staff attended a meeting with USFS and BLM data managers in December 

to discuss programs and how we could better coordinate data collection 

and dissemination.


ODFW
1
Establish / maintain working relationships with data 
1.  Jon answered barrier/dam questions for Mindi Sheer at NOAA.

collection projects within and outside ODFW to promote 
2.  Cedric attended a meeting in Portland lead by the REO to discuss their 

efficient and beneficial data sharing.
restoration data development and compilation process.

3.  Cedric traveled to Bend to attend Susan's FishScreen Database Q&A 

session w/Fish Screen and Passage Program staff. He also met with the 

office manager of the Bend Annex to secure office space for Susan.

4.  Shannon and Cedric attended a presentation at OSU given by Kelly 

Moore and Hiram Li in which they compared and contrasted the Oregon 

Plan and the Washington Plan.

5.  Jon acquired a draft coverage of the Northcoast Salmon Abundance and

Diversity watershed data that Andy Talabere has been developing.  This 

was done with the intention of including it in a discussion with ODFW and

StreamNet staff to talk about potential applications of GIS to the 

problems that field biologists are working to solve.


Objective
6
Task:
3
6/24/02
Page 55 of 58

Region
1
In order to broaden the scope and utility of the StreamNet 
1.  PSMFC and Xerces Society staff updated a proposal for creation of a 

database, develop appropriate proposals for data 
regional macroinvertebrates database.  The proposal was submitted to 

development activities that would compliment the main 
EPA for funding.

StreamNet data holdings.  Ensure proposed work is not 
2.  Oregon DEQ collects fish sightings information during their biological 

currently conducted by other entities.  (Examples may 
monitoring work.  The ODEQ lead, Rick Hafele, was put in contact with 

include traditional StreamNet data types outside of the 
Cedric Cooney so that ODFW/StreamNet could obtain the data collected 

Columbia River basin, macroinvertebrates, water temperature,
by ODEQ.

and habitat restoration.)  Conduct of such work will be 

dependent on availability of additional resources.  Once 

awarded, efforts will conform to the approved contract.  Such

work will be coordinated with this work plan so that 

activities under this task do not impede accomplishment of 

the remainder of the work plan.  This task is necessitated by 

the fact that project staff have time available that is not 

covered by the BPA contract.


Objective
6
Project Management / Coordination

Task
4
Prepare and present public information related to the StreamNet Project.

As needed, produce public information materials and participate in various meetings and forums to explain the project's capabilities

and purpose and to generate support and additional data sources.  Activities may include brochures, demonstrations, posters and talks.

Project
Job
Planned work elements                                                                                    
Accomplishments, First Quarter 2002





 

CRITFC
1
Prepare and present demonstrations and descriptions of the 
Lenora Oftedahl, StreamNet Librarian, presented a paper and conducted a 

library services available through StreamNet
workshop at the OFWIM Annual Conference.


IDFG
1
Where appropriate, participate in public or private meetings 
As part of our collaboration with ISS, we participated in cooperators 

and forums to represent StreamNet and IDFG. Produce 
meetings.

reports, maps, or other materials in support of or for 

dissemination of StreamNet information.


ODFW
1
Produce public informational documents on StreamNet data 
1.  Jon investigated differences between 1995-97 distribution data and 1998-

activities for natural resource oriented publications, give oral 
2000 distribution data, and prepared graphics highlighting key differences

presentations to relevant user groups, and participate in 
between the datasets in preparation for his Organization of Fish and Wildlife

various meetings and forums.
Information Managers Annual Conference. He gave a trial presentation at an

NRIMP staff meeting and incorporated changes to the presentation based

on feedback from the NRIMP team. The presentation was given at the 

conference during the Data Management and Delivery Session.

2.  Shannon developed a PowerPoint presentation to explain the NRIMP 

Program for a brown bag lunch lecture.


Objective
6
Task:
4
6/24/02
Page 56 of 58


3.  Shannon completed a draft 'Inside Tracks' article highlighting the function

and abilities of the NRIMP program. She also updated a draft article describing

the Incidental Fish Observation data system, and another comparing and contrasting

'Spreadsheet vs. Database' functions.

4.  Shannon initiated and completed a PowerPoint presentation on the 

Carcass Placement database.

5.  In an effort to help Bruce Schmidt prepare a presentation for a Steelhead

Workshop in the Spring, NRIMP staff solicited ideas for how GIS can help

field biologist from ODFW biological staff. Staff also participated in a meeting in

Portland to further identify ways that GIS can aid steelhead biologists.


Region
1
Prepare and deliver presentations to scientific and 
The Program Manager and Regional Fisheries Biologist prepared and delivered

professional meetings to demonstrate project capabilities and 
presentations at the annual Organization of Fish and Wildlife Information

accomplishments and to solicit additional data and 
Managers meeting.  These talks addressed real-world needs in data compatibility

involvement or coordination with the project..  Expected 
between different users.  Topics presented were:  1)  Use of region-wide data

results would be enhanced visibility for the project, increased 
exchange formats to organize dissimilar data  2) Long term fisheries monitoring:

participation and data flow from agencies, improved 
using standardized data sets: How well is it working?  and  3)  Obstacles to

coordination, and avoided duplication of effort.
standardization of field sampling methodology. Or: Why is it so hard to get

everyone to do it the same way?


WDFW
1
Participate as opportunities arise to highlight StreamNet 
O'Connor delivered a presentation "Scrambling for Data Standards in 

programs & data. Report key contacts and results to Regional
Habitat Restoration Projects" at the Annual Meeting of the Organization 

Project Manager to keep Manager apprised on opportunities 
of Fish and Wildlife Information managers (November; Portland, OR).

pursued in Washington state.

Supplemental Information:  Work accomplished outside the specific work elements in the Work Statement
The following work was accomplished in addition to or beyond the specific tasks described in the FY 01 Statement of Work.  Although these tasks were not specifically listed in the work statement, they were opportunistic in nature and contributed directly to StreamNet project goals.

Project

Accomplishments, First Quarter 2002                                                                    

CRITFC

Most of the "other" activities are related to tasks in the existing work statement and have been mentioned as accomplishments under those tasks.  There are two general areas of activity that might be considered here, however.  1)  The first is the growing reputation and credibility of the StreamNet Library for providing services and resources for fisheries projects not specifically described in the StreamNet work statement.  For instance, the Library has been asked on two occasions to create custom CD's of reference reports on protocols for habitat monitoring and, again, on the status of coastal cutthroat trout.  These have been relatively small projects which can be handled within the present budget, but we anticipate this type of request will grow.  2)  The second is that the Steering Committee member is routinely asked to participate in regional planning and evaluation groups.  These include, for instance, participation in the Regional Assessment Advisory Committee, Regional Data Management project, Subbasin Planning, monitoring and evaluation discussions, etc.  This broad scale understanding of regional needs and plans is reported regularly to the Steering Committee and helps keep the project relevant to regional needs.


Supplemental Information
6/24/02
Page 57 of 58

Region

In continuation of coordination work begun in previous years under other funding, PSMFC staff assisted Oregon Department of Environmental Quality with final corrections to their macroinvertebrates database.  We pointed out 22 sampling sites that needed to be corrected.  We also worked with ODEQ to create an updated database for their agency.  This new database should be better integrated into the ODEQ LASAR database, and thus fit their needs better while allowing for easy data sharing at a regional level in the future.  Also related to macroinvertebrate work, the Regional Fisheries Biologist gave a presentation at the annual meeting of the Northwest Biological Assessment Workgroup, held this year in Cannon Beach, Oregon.  This presentation was designed to introduce the idea of a regional macroinvertebrates database to the Northwest's macroinvertebrates community.  We hope that this effort will result in outside funding to continue the regional macroinvertebrates database work that we have been pursuing.

WDFW
1.  The WDFW Habitat Program is reviewing the future of its SSHIAP Project, and is considering a request from O’Connor to integrate and truth the various collections of barriers data we have.  Such work would greatly enhance the quality of Washington state migration barriers data, and would give us the product we need to be able to effectively exchange high-quality barriers data with StreamNet. 




2.  The Resident Fish Joint Stock Assessment Project in Northeast Washington is struggling to deal with the different field sampling data formats used by the four project participants.  An RFP was drafted to seek a consultant to help integrate the data (both fish sampling and habitat sampling) into a single common database.  O’Connor is involved in guiding the RFP, selection, and data format creation process. We hope to see a format adopted that will support simple conversion to the appropriate StreamNet exchange formats.


3.  The WDFW Fish Program recently authorized creation of a one-year project to fund 2.5 FTE in order to build basic fish data GIS capability in the agency (partnered with current contract funding).  A series of priority tasks were assigned, including moving SaSI (salmon stock identification and status) data onto the Web using 24K hydrography. If we succeed in meeting these goals, prospects for future WDFW support for basic fish GIS data will improve considerably.  In addition, O’Connor is scheduled to travel across the state to visit the six Regional WDFW offices this spring to interview field staff about their basic data needs, both tabular and spatial.  Results of this survey will build the first-ever WDFW Fish Data Plan, which will provide strategic guidance for both WDFW-funded efforts and partner efforts such as StreamNet.

Supplemental Information
6/24/02
Page 58 of 58



� EMBED Word.Document.8 \s ���








_1079873581.doc
[image: image1.png]






