[image: image2.wmf]  
[image: image1.wmf]
StreamNet Project
BPA Project No.  198810804

Fiscal Year 2002
Fourth Quarter Progress Report
July 1, 2002 through September 30, 2002

Bruce Schmidt
Pacific States Marine Fisheries Commission

Cooperators
Phil Roger, Columbia River Intertribal Fish Commission
Bart Butterfield, Idaho Department of Fish and Game

Janet Hess-Herbert, Montana Fish Wildlife and Parks

Cedric Cooney, Oregon Department of Fish and Wildlife

Steve Pastor, U.S.  Fish and Wildlife Service

Dick O'Connor, Washington Department of Fish and Wildlife

October 31, 2002


                                            Table of Contents                                             Pg.

Introduction………………………………………………………………
 2


Objective 1.  Data Development and Update, Priority Data Sets…….
 7


Objective 2.  Data Development and Update, Other Data Sets………

17

Objective 3.  Data Management and Delivery…………………………

24


Objective 4.  Library / Reference Services…………………………….

39


Objective 5.  Services to Fish and Wildlife Program Activities………

43


Objective 6.  Project Management and Coordination…………….…..

47


Supplemental Information: Work accomplished outside the S.O.W...

55

Introduction
StreamNet is a cooperative, multi-agency data compilation and data management project authorized by the Northwest Power Planning Council’s Fish and Wildlife Program (FWP) and is funded primarily by the Bonneville Power Administration.  The project is administered by the Pacific States Marine Fisheries Commission.  Three fourths of the project consists of sub-projects within the state fish and wildlife agencies, Columbia River Intertribal Fish Commission and the US Fish and Wildlife Service to develop databases within the respective agencies and facilitate data transfer regionally. 

The StreamNet Project compiles, manages and distributes information related to fish resources in the Columbia River basin, with additional information available for the rest of the Pacific Northwest.  The state, tribal and federal fish and wildlife agencies collect and utilize data related to the region’s fish and wildlife resources to meet their own mandates.  A subset of these data, primarily the annually collected types of information that are routinely used to monitor trends within fisheries and populations and provide management information, are compiled by StreamNet into regionally standardized formats and publicly distributed.  In this manner, data common to fisheries management but collected and stored in multiple formats by the individual agencies are standardized and made uniformly available basin wide.  StreamNet also ties all data to the regional 1:100,000 scale routed hydrography (GIS stream network) so that different kinds of data can be compared on a geographic basis and mapped.  The project utilizes the Internet as its primary means of data distribution, but also provides custom data services to FWP participants.  The StreamNet web site provides access to information in a queriable database and also provides maps, individual data sets not contained in the queriable database, and library references.  All data in the StreamNet database are referenced to source documents that are housed in the StreamNet Library.


Introduction


StreamNet Fourth Quarter Performance Report, FY 2002
Page 2 of 56
Work priorities for FY 2002 include updating existing long term data sets, managing the data and infrastructure necessary to maintain and deliver data, maintaining the StreamNet Library, providing data services to regional entities associated with the Fish and Wildlife Program, and project administration.  This year the distinction between anadromous and resident fish data in the data development objectives was dropped, and the annual statement of work was reorganized to reflect that change in approach.  This year, the agencies indicate in each individual job whether the work is directed toward anadromous or resident species for each particular data type.  This change is a change in organization, not project direction.  The majority of work remains focused on anadromous species due to the sport and economic value of these species and because of associated Endangered Species Act aspects.  However, efforts are also underway to develop increased information on resident species distribution, and increased effort is directed toward identifying resident species information that may be developed by other projects funded through the FWP and obtaining those data for archiving so that they are more widely available.

This report documents accomplishments made by the project and its cooperators during the fourth quarter of Fiscal Year (FY) 2002.  Since the cooperating agencies work on different jobs throughout the year, and not all agencies address the same jobs in their respective portions of the Work Statement, the work accomplished in this quarter varies by cooperator.  Tasks and jobs that did not have any work addressed during the quarter are not included in this report.

Activities in the fourth quarter of FY 2002 included routine development, maintenance and posting of various data sets, as well as routine administrative activities to continue project function.  Key highlights of activities by each of the project participants this quarter are presented below:

Columbia River Intertribal Fish Commission (CRITFC)

1.  Problems with the existing harvest data were identified previously.  In the fourth quarter we developed prototype alternative harvest information to replace the existing data sets.  These are now being checked and modified.

2.  The bulk of fourth quarter activities focused on providing and extending routine Library services.  Significant amounts of material were 

exchanged with other libraries which filled in voids (principally in journals and unpublished technical reports) in the existing collection.  Requests for information concerning anadromous fish recovery planning under the ESA and subbasin planning were filled in the fourth quarter.  A new lease agreement was completed to obtain additional Library space, which will provide adequate room to incorporate material used for the Council's subbasin planning efforts.

3.  Significant time was spent by StreamNet staff (through other funding sources) working with Council and agency staff to organize subbasin planning efforts.  These discussions included a number of data management issues and there is growing regional acceptance of the  StreamNet system as an integral component of subbasin planning.  A draft contract with the NWPPC was prepared to allow the Library to digitize the reference material needed for and developed during subbasin planning.  This is both a complement to work accomplished by the project and a challenge to incorporate more regional services in the future.


Introduction


StreamNet Fourth Quarter Performance Report, FY 2002
Page 3 of 56
U. S. Fish and Wildlife Service (FWS)

The Fish and Wildlife Service, the smallest component of the StreamNet project, accomplished routine tasks, including production of the FWS portion of the Third Quarter Report and participating in the quarterly Steering Committee meeting.

Idaho Department of Fish and Game (IDFG)

1.  After completing a thorough review and update of the entire IDFG hatchery return and age composition database, we submitted 1998 - 2000 hatchery return and hatchery facility data to StreamNet.  The data were imported into the StreamNet web site and are available to the public.

2.  A thorough review and update of the entire IDFG redd count data set was completed.  Errors were corrected and additional data were found and entered.  A review of the trend definitions that the data are rolled up into for StreamNet still needs to be done.  The 1998 - 2000 data will be submitted based on the current trend definitions and then the definitions will be reviewed for a later complete update.

3.  Internal capabilities to build and manage a comprehensive fish information system made a major step forward with the installation and configuration of two new servers and related equipment and upgrading to a Windows 2000 network.  The equipment was purchased with IDFG funds, not StreamNet, but will serve as the infrastructure and framework for the Idaho Fish and Wildlife Information System, which will hold the StreamNet databases and tools.

4.  GIS data and tools were installed in two more IDFG regional offices.  This provides people with the tools and data for standardizing their data on StreamNet compatible codes.

Montana Fish, Wildlife and Parks (MFWP)

Work on Objective 1 continued smoothly; genetic data and the corresponding distribution data have been updated and the data are current through 2001.  Participating in the Montana Westslope Assessment process will greatly update the westslope cutthroat trout and barrier data.  StreamNet staff have been closely involved with the development of the products for the assessment.  StreamNet staff will participate at each meeting and all data collected will reside in MFISH.  The only date not met will be for the barriers data due to the amount of information that will be collected during the Westslope Assessment.  A decision was made to contract the 1/2 time fisheries data management duties that were lost when Steve Carson became the data manager for a new wildlife data system for nongame occurrence and habitat survey data.  A contract with the Montana Natural Heritage Program will be used with a 1/2 GIS position that they are filling.  The position will be located in Helena.  A presentation about StreamNet in Montana was given at the NWPPC August meeting and was well received.  The project leader attended the August SC meeting and had a follow-up assignment to create a first draft of a DEF Review Process; the draft was completed, review comments received and a second draft will be discussed at the October SC meeting.  A considerable amount of time was spent on reviewing the other data management projects prior to the CBFWA review in September.


Introduction


StreamNet Fourth Quarter Performance Report, FY 2002
Page 4 of 56
Oregon Department of Fish and Wildlife (ODFW)

1.  Oregon submitted a great deal of information to StreamNet during the fourth quarter, including distribution, barriers, dams, fish barriers, hatchery facilities, numerous abundance trends, and an independent data set of Oregon’s carcass placement efforts.

2. Using funding provided by the Governor’s Natural Resources Office and Oregon Watershed Enhancement Board, we continued to update 1:100,000scale fish habitat distribution data in the entire anadromous zone of Oregon, and also to develop fish habitat distribution data at the 1:24,000 scale for this same area.  Conversion of all the hardcopy information into electronic format was completed during this quarter, and lead to the improvement of the locational accuracy of many of StreamNet’s data sets including barriers, fish barrier information, dams, and distribution.  This effort will continue through the end of the calendar year, and should continue to greatly improve the accuracy of many StreamNet data sets from Oregon.

3.  Oregon staff spent a considerable amount of time developing Oregon's portion of the ISRP response from StreamNet, including a description of Oregon's QA/QC procedures for redd count data, and a task by task breakout of our budget request for FY-2003. We also reviewed and commented on StreamNet’s response to specific ISRP questions.

4.  In response to a request from Oregon’s CBFWA representative, Oregon collaborated with other StreamNet Steering Committee members to review five of the six data management projects in the Systemwide Province (excluding StreamNet).  Staff also represented ODFW during the CBFWA Provincial Review process.

5.  Staff participated regularly during the quarter in Oregon Subbasin Planning Group meetings, and provided feedback on data related topics as needed.

6.  Two proposed data exchange formats for fish screen and hatchery fraction information were submitted to StreamNet for review and adoption.

7.  We accomplished normal project activities, including completion of quarterly reports, attendance and participation in the StreamNet Steering Committee meetings, and responding to direct requests for information.

Washington Department of Fish and Wildlife (WDFW)

1.  Our salmon natural spawner data update was a huge milestone.  Before this submittal, our most recent update for this data type occurred in 1998 for steelhead data.  Consistent updates were hindered by losing essential knowledgeable staff, the complexities of the data type, the labor in gathering the pieces that are scattered throughout the agency and the press of too many other StreamNet priorities.  

2.  Our work with ArcView projects and our investments to use GPS tools are enabling us to resolve many of the pressing location related problems.


Introduction


StreamNet Fourth Quarter Performance Report, FY 2002
Page 5 of 56
Pacific States Marine Fisheries Commission (PSMFC, or ‘the Region’)

Regional efforts centered around routine project operations, including loading and quality assuring data submitted by the cooperators, software upgrades and project administration.  Key accomplishments the fourth quarter included:

1.  Replacement of the Regional GIS Specialist.  The previous GIS Specialist provided enough lead time that we were able to interview and hire a replacement in time to allow a period of overlap to facilitate the new specialist learning how the project functions.

2.  Significant effort was required to respond to reviewers comments as part of the Mainstem and Systemwide project review and approval process being used this year.

3.  A newsletter was distributed to highlight new features and data contained in the StreamNet web site.  The newsletter is intended to be an ongoing feature to periodically highlight changes and enhanced services and capabilities.  Over 850 people had signed up to receive future update newsletters by the end of the quarter.

4.  In response to user requests we instituted a new capability to retrieve data by Trend Number.  This allows users to come back and retrieve updated data without having to repeat the query process.  The one caveat is that Trend Numbers are internal tracking numbers and do occasionally change.

5.  StreamNet has participated actively in the Columbia Basin Cooperative Information System (CBCIS) project being conducted for the Power Planning Council by Science Applications International Corporation (SAIC).  The project is attempting to conduct a data needs and data availability inventory in preparation for recommending an approach to basin wide data management.


Introduction


StreamNet Fourth Quarter Performance Report, FY 2002
Page 6 of 56
Objective
1
Data Development and Updates, Priority Data sets

Support the need for region wide fisheries data for research, monitoring, modeling, and management through acquisition and regional standardization of new information and updates to previous information for priority fishery data types.  These priority data types will be addressed by all data providing agencies, or for specific data types by a single cooperating agency on behalf of the entire project.  This Objective addresses both anadromous and resident fish species, although priorities may differ.

Objective
1
Data Development and Updates, Priority Data sets
Task
1
Distribution and life history (use type)

Document the occurrence, distribution and life history characteristics of native fish species, both resident and anadromous.  Project participants have placed a high priority on updating these data during the fiscal year, utilizing newly re-defined use types.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






IDFG
1
Compile available IDFG data on fish distribution into the 
Data continued to be entered by IDFG staff into the IDFG/StreamNet-developed

IDFG/StreamNet Fish Information System. These data will 
Fish Information System.  Data included collection permit reports and stream

come primarily from Collecting Permit reports and IDFG files
survey data.  These data will be used to update the StreamNet generalized fish

being digitized via a BLM Challenge Cost Share grant. Both of
distribution data.

these data entry efforts are independent of StreamNet. Other 

data will be collected from incidental observations in other 

tasks. Convert these data into StreamNet data exchange 

format and send to PSMFC as they become available.

MFWP
1
Complete Distribution and Use Types data set from data 
The edits and additions are ongoing.

collected from biologists, documents and reports during 

1999-2000 using LLID stream routes.  Exchange the data to 

the StreamNet database in the approved DEF format.

MFWP
2
Visit MFWP biologists in 2002 to collect 2000-2001 fish 
The edits and additions are ongoing.

distribution and supporting survey data and references.  Obtain

data from federal biologists using our developed interface.  

Input all this information into the MRIS tables.


Objective
1
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 7 of 56
ODFW
1
Update, maintain, correct and exchange anadromous and 
1. The GIS Analyst further processed Malheur and Wallowa Whitman N.F.

resident fish distribution information (DistUse and 
O. mykiss data for potential inclusion into our Distribution database.  The

DistPresence tables).  Efforts will focus particularly in the 
24K Project GIS Coordinator contacted Ralph Browning (Forest Fish 

Upper portion of the basin (NE Region, upstream of the Hood
Biologist) of the Wallowa-Whitman National Forest to verify whether the

River basin).
data are appropriate to include in our database as documentation.  He 

thought not, and deferred to the opinions of the WWNF District biologists,

which we have captured on our hardcopy maps and mylars during our24K

Project effort. The WWNF digital data will NOT be incorporated as 

documentation, but will remain professional opinion-based distribution.


2. The GIS Analyst identified and resolved additional QA issues within the 

Distribution database. He then reformatted Oregon’s data into StreamNet 

Generalized Fish Distribution table format and submitted the anadromous 

species to PSMFC.  He also submitted a limited set of distribution data 

records in the Upper Willamette Basin for resident rainbow trout to 

StreamNet.  In addition, we developed a substantial number of distribution 

data records for resident rainbow / redband within the Columbia Basin, but 

are not submitting the data at this time due to the fact that it is not 

comprehensive in nature

3. The 24K Project GIS Coordinator finished updating the federal ESA 

status for all 100K distribution records.  Problems associated with 

identifying gene conservation group boundaries for state designations 

slowed the process, but it's was recommended that we follow the federal 

boundaries to populate the state item.  After receiving feedback from 

ODFW Fish Division staff regarding the Oregon State ESA listing status, 

she began populating the OR_ESA field in the 100K Fish Distribution database.

4. The GIS Analyst appended 916 fish presence survey records to the 

Full_Doc Documentation table.  He also processed another 1740 records 

which will have their spatial locations based on coordinates rather than 

LLIDs and measures since they are associated with streams not found in 

the 1:100,000 scale streams layer. 

5. The GIS Analyst completed DRAFT criteria for adding resident fish data

to the Distribution database.  He also resolved UseType discrepancies 

between Idaho and Oregon for Summer Steelhead in the Snake River.

6. Oregon’s GIS Analyst synchronized the Distribution design master with 

existing replicas, and resolved various data conflicts.  He also identified and

fixed several records that had EndMeas values greater than the total 

stream length.


Objective
1
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 8 of 56
ODFW
2
Update (and modify if needed) the Fish Presence Survey 
1. The GIS Analyst addressed numerous issues related to fish observation 

database which helps populate the DistPresence table.  These 
data and how to translate them into linear distribution format.  Staff 

data will update the distribution data developed under Task 
worked together to develop protocols of "translation" that make only the 

1.1.
safest assumptions to derive these data.  Based on decisions made, we 

corrected existing resident O. mykiss event data to match finalized 

protocols.

2. The GIS Analyst initiated Documentation Q/A in relation to distribution

 data and as a result identified hundreds of coho records where 

documentation falls upstream of the distribution (27 records where the 

difference was greater than 2 miles).  We developed a methodology for 

resolving these discrepancies in a comprehensive manner.

3. Staff determined minimum and maximum UTM coordinates for setting 

validation rules within the Fish Presence Survey database, and after 

cleaning up a few lingering Fish Presence Survey records that still had bad 

or inconsistent coding, we progressed down the path of creating 

documentation data based on these survey records.

ODFW
3
Update (and modify if needed) the Incidental Fish Observation
The Project Leader entered a newly submitted IFO form from Jeff Neal in 

database, which captures incidental species observations not 
the John Day.  This record adds distribution to a stream that had 

routinely reported in agency documents, which helps populate 
previously been designated as non-fish bearing.  There are several more 

the DistPresence table.  These data will update the distribution
new forms to be entered that have come in over the past few months.

data developed under Task 1.1.

WDFW
1
Incorporate field updates for Washington fish distribution and 
1.  WDFW is actively collecting new data on fish species distribution by 

use data (when provided) into WDFW's GIS database, with 
conducting mapping parties in various regions of the state.   We provided a

emphasis on bull trout and other sensitive salmonids this year. 
custom map of the existing Cutthroat distribution that's already been 

Update tabular files via export from the GIS database. Convert
documented in SW Washington and WDFW StreamNet staff contributed 

spatial and tabular data to new StreamNet exchange formats 
distribution knowledge at the Region 5 mapping party.

and submit to PSMFC.
2.  WDFW StreamNet staff continually conferred on technical issues and 

needs for WDFW's re-organization of the old and new distribution data.

3. Tabular/ GIS Compiler Gil Lensegrav assisted Fish GIS Manager Martin 

Hudson by using an ARC/INFO interface to align 100K StreamNet fish 

distribution end points with the SaSI end points in order to link the new 

2002 SaSI attributes to the fish distribution tables. In addition, these 

adjusted points were "snapped" to WDFW's 24K hydro layer to form the 

basis of the new (higher resolution) fish distribution layer that is being 

created this year in WDFW.


Objective
1
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 9 of 56
Objective
1
Data Development and Updates, Priority Data sets
Task
2
Adult abundance in the wild

Develop and maintain information on adult abundance for native fish species, resident and anadromous, including 

escapement, redd counts, peak spawner counts, trap counts and dam and weir counts.  Also included in this data category are 

data gathered during spawning ground surveys regarding straying of hatchery fish onto spawning areas, i.e., 

marked/unmarked ratio.  Priority is given to updating these data through 2000.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






IDFG
1
Submit 1998, 1999, and 2000 field season redd count data.
1.  We completed our review of the entire IDFG/StreamNet redd count 

database.  This did not include a review of trends.

2.  We started to roll up our redd count data to existing StreamNet trends.  

This was started right at the end of the fiscal year and we did not complete

the submission to PSMFC.  Completing this task will be our first job in 

October and we should submit the 1998 - 2000 data within the first few 

weeks.

IDFG
2
Compile year 2001 field season redd count data and submit to 
2001 redd count data continued to trickle in.  We continued to enter the 

PSMFC.
data as they became available.

MFWP
1
Complete input of 1999-2000 data, including trend, count and
Work continued on this ongoing job.

references; exchange to StreamNet.

MFWP
2
Collect all 2000-2001 survey data during field office visits.
Work continued on this ongoing job.

MFWP
3
Input 2000-2001 data into MRIS, including trend, count and 
Work continued on this ongoing job.

references. Provide data in data exchange format to regional 

StreamNet staff if completed.

ODFW
1
Update existing abundance and indices trends (escapement, 
1. The Database Analyst reviewed StreamNet Library documents and 60K 

redd counts, trap counts, peak/other spawning counts, etc.) 
trends with the goal of transferring ownership of the information to 

where data collection continues for anadromous and resident 
NRIMP (ODFW Natural Resources Information Management Program, 

species through 2000 and modify as needed to adhere to any 
which includes Oregon StreamNet).  She found that most "references" are 

new data exchange standards.  Three data submissions are 
very poor; mainly just sheets of data, and occasionally the data didn’t 

planned.
appear to be within the reference at all.

2. The Database Analyst continued updating Abundance Trends to 2000, 

completing all the trends from the Columbia Basin.  She also continued 

efforts to examine Hatchery Return 60K trends with the help of the 

Database Manager.  Staff updated location information for many trends 


based on newly entered EscData.


Objective
1
Task:
2
StreamNet Fourth Quarter Performance Report, FY 2002
Page 10 of 56

3.  The Database Analyst corrected errors identified during QA/QC activities.

She reviewed the Trend Database for null values in the CountPerMile field

where the TrendType was any "Count" Per mile variation.  She used references

to verify if a count was present, and calculated a value if there was none provided.  

She also compared StreamNet’s tables with ODFW's EscData and Trend tables.

This included approximately 900 Trend records and 3300 EscData records.

Following this work, a Trend data submission was made in late September.

WDFW
1
Research, compile, convert and submit natural spawner data 
1.  The Region 5 WDFW StreamNet Compiler and Data Manager updated and

updates (returns and/or redd counts) through 2000 (and 2001 
manipulated data preparatory for a StreamNet submission, including but not limited

as available) for available species (Columbia River and Puget 
to stock code updates and an assessment of the 60K PSFMC trends.  The data was

Sound).
submitted to the WDFW StreamNet Data Manager in aid of a StreamNet 

submission of salmon natural spawner data that would bring StreamNet data current

through 2000 data.  After review and further manipulation, the bulk of the data was

submitted to StreamNet, yet, some records were rejected for various issues and a

strategy for follow-up resolution was drafted.  All staff contributed to this important

submission with complex location coding needs.  

2.  Following the StreamNet submission, staff made changes to the database system

to improve future submissions, began researching the rejected records, augmented

documentation for the QA/QC process and continued to assess 60K PSMFC trends.

Staff also received a Entiat River data report and entered the redd count data into 

the Escapement database.

3.  The Region 5 WDFW StreamNet Data Manager spent considerable time in 

August and September reviewing sampling procedures for stream surveys on the

Columbia River.  Historical stream surveys on the Columbia River have been 

recorded on stream survey cards by river, index and date.  These cards are in the 

process of being converted to an electronic format using new technology.  GPS

locations will be used to catalogue index areas on surveyed rivers and streams.  

Indexes will then be converted from a named place to reflect from X river mile to

Y river mile.  River mile was chosen (instead of BegFt, EndFt) since the biologists

prefer river mile and the data can easily be converted to StreamNet's format.

4.  Separate from the salmon data work and submission, we began work to resolve

the 60K steelhead trends.

5.  Per request, one staff member assisted on a Green River Chinook salmon mark  /

recapture field project.


Objective
1
Task:
2
StreamNet Fourth Quarter Performance Report, FY 2002
Page 11 of 56
Objective
1
Data Development and Updates, Priority Data sets
Task
3
Hatchery releases

Develop and maintain information on the release of hatchery reared fish.  Priority is given to updating anadromous release 

records using RMIS data for anadromous species through 2000.  Release data for resident species are currently low priority 

and will require specific resources in the future.  Efforts this year will focus on creating cross references between PSC 

release codes and LLID stream location identifiers.  We will explore means of providing data on specific release locations 

rather than more general PSC codes.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






FWS
1
For anadromous hatchery releases, compile FWS hatchery 
The FWS Project Leader  did an initial transformation of 2002 release data into the 

release data, w/ added CWT information.  Transform data to 
new PSC format 4.0.

format 032.  Submit 2001 hatchery release data to PSMFC via

USFWS WWFRO.

ODFW
1
Acquire specific release location information for select 
1.  The Database Manager started work on implementing Hatchery Release 

releases in the Willamette, Lower Columbia, or Sandy basins
functionality into the query system created last year for Hatchery Return 

as available.
information.  He downloaded vocabulary lists for the Fish Liberation and 

Coded Wire Tag tables from the HMIS system, and worked on creating 

queries that will relate these two tables, as they are two unrelated entities 

within the HMIS system.

2.  The Database Manager sent a sample hatchery release data set to the  

Regional Database Manager to see if the data satisfied regional needs.  In the 

end 17 Trends were created along with 314 detail records; all from one hatchery, 

for one species, in one brood-year.  The Regional Database Manager brought up 

some issues that were overlooked and so the data were reworked and sent back to 

PSMFC for further review.  In the end, he recompiled the hatchery release data 

from Stayton Pond.  15 Trends were created along with 285 detail records; all 

were submitted to StreamNet.

ODFW
2
Investigate if Hatchery Release data can be acquired in an 
The Database Manager/Developer identified 18 distinct water codes and 

unrolled format prior to it being submitted to RMIS.
descriptions for the hatchery release test data.  Our Database Analyst 

converted those water codes to LLIDs and BegFt measurements.  At that 

point, actual count numbers for the HatchRel table were created using 

ratios derived from the RMIS system.  This rolled hatchery release test 

data set was delivered to PSMFC.  This data set totaled 17 Trends, with 

314 detail records, which was for one hatchery, one species, for one 

brood-year.  The Regional Database Manager brought up some issues that 

had been overlooked and so the data were reworked and resubmitted to PSMFC.


Objective
1
Task:
3
StreamNet Fourth Quarter Performance Report, FY 2002
Page 12 of 56
Region
3
Assist agencies to replace certain Hatchery Release records 
The Data Manager received a test record set of about 285 records in 

with records having specific locations and times rather than 
Pacific Salmon Commission (PSC) data exchange format prior to being 

general "supercodes" originating from the PSC data exchange 
rolled up by coded-wire tags.  This sample set will be reviewed and 

requirement that all releases of coded-wire tagged fish must be 
evaluated to determine if this method of loading Hatchery Release data 

rolled into a single release record per tag code.  This task 
into StreamNet resolves many of the PSC location code to LLID 

requires that CWT data be resubmitted from agencies in either 
conversion problems.

StreamNet data exchange format or a modified PSC data 

exchange format.  The new formats will avoid pooling releases

by tag code; thus allowing more detailed release location and 

timing information.

WDFW
1
For anadromous species, research, compile, convert and 
Hatchery releases continue to be a highly requested data category and until 

submit existing WDFW anadromous release data as detailed, 
we make a submission to StreamNet we continue to handle any requests 

"unrolled" records directly to StreamNet (instead of via 
that come to our WDFW StreamNet staff.

RMIS).  As warranted, organize procedures to ease future 

updates.

WDFW
3
WDFW resident data is fractured in several collections by 
We continued to assign StreamNet's location codes (LLIDs, etc) for any 

year.  Research, compile, convert and submit data for any 
records pertinent to a direct data request.

years we have finalized at a given time, until all collections are

submitted.  (Progress with this data set relies upon 

improvements to our Lakes spatial layer first).

Objective
1
Data Development and Updates, Priority Data sets
Task
4
Hatchery returns

Develop and maintain information on the return, disposition and straying of adult fish returning to hatcheries, including 

information on coded wire tags.  This is an anadromous related task only.  Priority will be placed on updating total return and

egg take data through 2000.  Development of disposition data is lower priority and would require additional resources.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






FWS
1
Compile FWS hatchery return data for FWS hatcheries and 
Pastor worked with regional GIS specialist David Graves to produce maps 

submit to the regional database
which will facilitate the display of hatchery recovery information.

IDFG
1
Submit 1998, 1999, and 2000 return season hatchery return 
We delivered the 1998 - 2000 hatchery return data to PSMFC.

data.

IDFG
2
Compile year 2001 return season hatchery return data and 
2001 hatchery return data were entered into the database as they become 

submit to PSMFC.
available.


Objective
1
Task:
4
StreamNet Fourth Quarter Performance Report, FY 2002
Page 13 of 56
ODFW
1
Compile data on returns to ODFW hatchery facilities (updated
1.  The Database Analyst designed a form to allow easier viewing and 

through 2000 returns where possible).
reviewing of Hatchery Return data.  This new form is being used in our 

process to transfer historic PSMFC Hatch Return records to Oregon’s 

responsibility.

2.  The Database Manager/Developer downloaded Hatchery Return 

information from the HMIS system using the Insyte Query System seeking

to identify new records.  He also downloaded the Vocabulary lists and 

sample data to ensure no internal data structures had changed.  Following 

this, he downloaded all the raw hatchery returns data and started processing

it to perform comparison checks against last year's data.  Fifty-four new 

trend were created, along with 448 detail records.  These data were 

submitted to StreamNet.
Objective
1
Data Development and Updates, Priority Data sets
Task
5
Dams and Fish Passage Facilities

Develop and maintain information on dam facilities.  Enhance the existing StreamNet dams data set by updating relevant 

data from the Pacific Northwest Hydropower Database and Analysis System (NWHS) and the National Inventory of Dams.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






MFWP
1
Complete the creation of a Montana dams spatial coverage 
We made minor spatial edits to the Dams and Passage Facilities database.

and associated data in the StreamNet exchange format.  Layer 

and data are being created using the NWHS and the National 

Inventory of Dams.  Tasks to date include combining the data 

from the two sources; manual checking needs to be done 

before the final product is completed.  Exchange the Dams 

data set to the StreamNet database.

ODFW
1
Update, maintain, correct and exchange dam information (as 
1.  Staff performed extensive QA/QC on the barrier/dam database, as well as

part of the Barrier database).
added lat/long coordinates to five 24K dams and removed three other dam

records because they were erroneously created during recent system tests.

2.  The  Assistant Database Manager submitted dam data to StreamNet.  

The data submission included 1,283 dam records, which is 98% of the total

number of dam records in the ODFW database, 1,022 DamXDamPurpose 

records, and 987 DamXDamType records.

3.  The GIS Analyst created coverages of status level 1 dam data in order to

work in the direction of posting these data to the FTP site and make 

them available publicly.  He also documented online files and data 

processing procedures.


Objective
1
Task:
5
StreamNet Fourth Quarter Performance Report, FY 2002
Page 14 of 56
Region
1
Assist data contributing agencies in development of data, 
We received a draft DEF for Screening and Fish Passage data from ODFW;

including formatting, coding, data entry, error checking, and 
this will be reviewed for inclusion into StreamNet during the next project 

submitting to the regional database.
quarter.

WDFW
1
StreamNet currently carries Washington dam information that
Staff continued to research and update the dams data file.  We are 

wasn't officially exchanged by WDFW.  We will compare 
augmenting the database with data from WDFW's SSHEAR GIS data sets in 

StreamNet's existing Washington dams data with WDFW's 
preparation for future data exchange.  We also analyzed a "Power Dam 

internal dam layer and any other dam data resource (i.e. DOE's
Investigations" publication for additional data to add to dams database & 

dams), adjust the WDFW layer accordingly and submit to 
shapefile.   More work is pending.

StreamNet.

Objective
1
Data Development and Updates, Priority Data sets
Task
6
Hatchery Facilities

Develop and maintain information on anadromous and resident hatchery facilities, including information on location, 

design, management and authorization.  Information will be updated through 2001 for required fields.  We will review the 

optional (non-required) fields in the DEF.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






IDFG
1
Submit hatchery facilities table in data exchange format to 
We updated the coordinates for Idaho hatchery locations and submitted 

PSMFC.
the hatchery facility data to PSMFC.

MFWP
1
Update the StreamNet hatchery database with Montana's 
This job has been completed already.  The next anticipated update is 

public and private facilities.  Exchange with StreamNet upon 
February, 2003.

completion.

ODFW
1
Incorporate temporary facilities that correspond to hatchery 
There were no temporary facilities that needed to be added to the 

return data but are not yet in the data set.
Hatchery Facilities data set this year.  All hatchery return data we 

encountered could be linked to a facility already in the data set.

ODFW
2
Maintain hatchery facility records and update location 
1. The Assistant Database Manager reviewed our hatchery facility records 

information as available.
and noted a few improvements that could be made to the data entry 

screen.  She also added the seven new hatchery facility records and updated

all of the hatchery facility records in the database with the 

additions/changes suggested by our GIS Analyst. Lastly, she entered new 

hatchery facility elevation data, which was provided by Mark Lewis from 

ODFW.

2. Oregon submitted 84 updated or new hatchery facility records to 

StreamNet.


Objective
1
Task:
6
StreamNet Fourth Quarter Performance Report, FY 2002
Page 15 of 56
WDFW
1
In an on-going effort, digitize hatchery facility sites and 
1.  Eric Lowrance of BPA contacted WDFW staff to get accurate hatchery

correct existing site locations as more site information is 
facility data after consulting the StreamNet's website and finding it lacking

learned.  Complete, convert, and submit  Washington state 
in location accuracy and site availability .  The WDFW StreamNet Data 

hatchery facility data (including federal and tribal facilities as 
Manager maintains the agency's most accurate and comprehensive data set 

available), focusing on the location related fields per the 
and StreamNet has the most current update.  She attempted discussion with

2001.1 format and facilities needed to support hatchery 
Eric but they haven't identified the specific issues yet.  

release and returns data.  As time permits, update other 
2.  WDFW hired a contractor to develop an ARCIMS application to post 

hatchery facility related fields (including the water source 
on the agency's website.  Among other things this application allows visual

table).
display of hatchery facility sites.  We provided the contractor with hatchery

facility data as requested and continue to work with them on their needs.

Objective
1
Data Development and Updates, Priority Data sets
Task
7
Harvest

Develop and maintain information on sport and commercial harvest.  Higher priority is assigned to anadromous species.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
2
Correct and update ocean and mainstem Columbia River 
Ocean harvest data were assembled from Pacific Salmon Commission and 

harvest data as agreed to by Steering Committee
Pacific Marine Fisheries Commission reports. The following sets of 

reports are being tested: 1) written descriptions and a map of coast-wide 

catch summary areas, 2) Total chinook and coho catch for 6 standard 

ocean areas, 3) Aggregate Columbia River mainstem commercial, sport, 

and ceremonial and subsistence catches for 3 reporting areas, and 4) 

stock-specific catches for Pacific Salmon Commission Columbia River 

indicator stocks by catch area.

ODFW
1
Compile and exchange updated and/or new tributary sport 
The Project Leader acquired sport harvest data through 1999 from Mark 

harvest data.
Lewis, ODFW   Ten harvest records were submitted to StreamNet based on

these data.  The remainder of the information will be submitted during the

first quarter of FY-03.

WDFW
1
As funding and time permits, compile freshwater harvest for 
We spent a couple of weeks in September working on the CWT/Snout 

key Columbia Basin salmonid stocks for both anadromous and 
sport summary reports for the Columbia River.  This data was sent to the 

resident data , using existing WDFW data sets (i.e. Angler Fish
WDFW CWT Analyst (Susan Markey) for final processing.

Database) and other sources.  Standardize the data (to stock if

possible), convert and submit it to PSMFC.


Objective
1
Task:
7
StreamNet Fourth Quarter Performance Report, FY 2002
Page 16 of 56
Objective
2
Data Development and Updates, Other Data sets

Support the need for region wide fisheries data for research, monitoring, modeling and management 

through acquisition of new information and updates to previous information for data sets of medium 


or lower priority as time and funding allow.  This objective includes anadromous and resident species.

Objective
2
Data Development and Updates, Other Data sets
Task
1
Habitat Restoration/Improvement Projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations 

within the Columbia Basin and compile and maintain them in standardized, consistent formats.  This data category is still 

being organized, but interest in this information is growing.  Existing data sets will be maintained and enhanced as practical. 

Additional sources of this information will be explored.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






MFWP
1
Continue to collect, centralize and maintain all stream 
Work continued on this ongoing job.

restoration projects for Montana using the "Future Fisheries 

Interface" which StreamNet staff maintains and the Fisheries 

Division inputs data.  Exchange data to the Region twice 

during the year.

ODFW
1
Maintain, correct and exchange existing restoration project 
There were no requests to update or correct existing records this quarter.

information.

Objective
2
Data Development and Updates, Other Data sets
Task
2
Barriers and diversion/screening

Develop and maintain data sets for barriers to fish migration and diversion structures with information on screening status.  

This category is still being organized.  Existing data on adult barriers will be maintained and updated as practical.  Other 

sources of data will be explored.  Work on juvenile barriers, culverts and diversion screening may require additional 

resources.  The primary emphasis is on anadromous species except in non-anadromous areas.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






MFWP
1
Continue to collect barrier location, species affected and other
The data exchange was delayed because new barriers data is forthcoming as 

fields on stream barriers in Montana.  Information will be 
a result of the statewide westslope cutthroat trout assessment meetings 

collected on all species regardless of life history.  Exchange 
concluding on October 24, 2002. Data exchange will occur in the first 

Barriers data with the StreamNet database.
quarter of 2003.


Objective
2
Task:
2
StreamNet Fourth Quarter Performance Report, FY 2002
Page 17 of 56
ODFW
1
Update, maintain, correct and exchange adult migration 
1.  The GIS Analyst created coverages of status level 1 barrier data in order

barrier information.
to work in the direction of posting these data to the FTP site and make 

them available publicly.  He also documented online files and data 

processing procedures.

2.  The Asst. Database Manager added latitude and longitude fields to the 

barrier table, and made extensive changes to all of the forms in the 

barrier/dam database.

3.  Oregon submitted barrier data to StreamNet.  The data submission 

included 2,101 barrier records, which is 96% of the total number of barrier 

records in the ODFW database.

ODFW
2
Update, maintain, correct and exchange anadromous and 
The GIS Analyst completed QA efforts in relation to the Fish Barrier 

resident fish barrier data.
table, and Oregon submitted 1,210 additional fish barrier data records to 

StreamNet.

WDFW
1
If funding and time permits, review existing Washington state 
Upon learning that ODFW would soon come out with a Screens DEF 

barriers (in GIS format) and identify additions and corrections 
proposal, the WDFW StreamNet Data Manager started assessing the 

needed and plan for future exchanges.  Any barrier work plan 
likeliest WDFW contacts for this type of data.  She reviewed WDFW 

will depend first on establishing a WDFW Dams spatial layer 
web sites and contacted the Yakima Screen Shop, requesting their data.

(see Objective 1, Task 5, Job 1).

Objective
2
Data Development and Updates, Other Data sets
Task
3
Juvenile data, abundance and outmigration

Develop and maintain information on smolt production (as determined from smolt traps), juvenile abundance (as determined 

through snorkel, electrofishing, and other surveys), and smolt density model estimates.  Primary emphasis will be on 

maintaining the existing smolt density model data.  The rest of this data category is still under development and may require 

additional resources to accomplish.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Seek to obtain tribal data on smolt abundance.  Inform 
No work this quarter. These data types will be explicitly addressed in the 

Steering Committee on data availability
prototype data system developed and tested with Yakama Nation data 

next year.

IDFG
1
Begin design and collection of  juvenile trapping component 
IDFG biologists used the IDFG/StreamNet Juvenile Trapping program to 

in IDFG/StreamNet Fish Information System. At current 
conduct quality control on data collected last year.  They have found the 

funding levels this task will be of lower priority than Objective
program valuable for  managing their data and for conducting queries.

1 data components and progress will depend on completion of

Objective 1 tasks. This task is also dependent on 

collaboration with non-StreamNet projects in IDFG.


Objective
2
Task:
3
StreamNet Fourth Quarter Performance Report, FY 2002
Page 18 of 56
IDFG
2
Incorporate the General Parr Monitoring database into the 
We obtained the general parr monitoring database, formatted as a single 

IDFG/StreamNet Fish Information System and submit to 
large flat file.  After creating metadata, we will submit these data to 

PSMFC.
PSMFC to post as an independent data set on the StreamNet web site.

WDFW
1
As funding and time permits, collect and scope existing 
Our Region 5 Compiler continued to keep the Cedar Creek adult and smolt 

juvenile data to plan future conversion and submission efforts.
trap databases current by adding collected data weekly, running error checking

routines and general database maintenance.  A master table for the 2002

smolt trap data was generated to be incorporated into reports being prepared

by Shane Hawkins and Dan Rawding of WDFW.  Several queries were

performed on the master Cedar Creek database to fulfill data requests.
Objective
2
Data Development and Updates, Other Data sets
Task
4
Age

Develop and maintain information on age/sex composition of returning adults, primarily for anadromous species.  This is a 

medium priority, with the primary focus on developing data for a test location for each cooperating agency this year as a 

means of testing data organization/format and utility.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Survey member tribal fishery programs to determine 
No work this quarter. These data types will be explicitly addressed in the 

availability and format of salmon age data.  Inform Steering 
prototype data system developed and tested with Yakama Nation data 

Committee on data availability
next year.

IDFG
1
Compile year 2001 Age/Sex Composition data.
2001 age composition data continued to become available in conjunction 

with hatchery returns, and entry of these data continued.

MFWP
1
During the field office visits in 2002, the availability of age 
Work continued on this ongoing job.

data will be determined.  Information will be gathered on what 

is being collected, in what format and for what geographic 

areas.  Data will be acquired, if available, and reviewed with the

Steering Committee.

ODFW
1
Compile age frequency data for an as-yet undetermined basin 
The Database Analyst requested and received a newly updated Age table to 

or hatchery in the Oregon portion of the Columbia Basin as a 
use for adding to and submitting ODFW's age data.

prototype for organizing age data.

Region
1
Assist data contributing agencies in development of data, 
We loaded a small test record set of 102 records of Age data from IDFG.

including formatting, coding, data entry, error checking, and 

submitting to the regional database.


Objective
2
Task:
4
StreamNet Fourth Quarter Performance Report, FY 2002
Page 19 of 56
 Objective
2
Data Development and Updates, Other Data sets
Task
5
Production factors and run reconstruction

Develop and maintain information on survival, production factors, spawner / recruit estimates, and run reconstruction.  This 

is currently a low priority, but the existing spawner / recruit estimate data will be maintained.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






All

No work was performed on this task during the fourth quarter

Objective
2
Data Development and Updates, Other Data sets
Task
6
Habitat

Acquire data sets related to fish habitat (including water quality, stream/watershed habitat quality, temperature, 

invertebrates, and miscellaneous habitat data) from the multiple agencies, tribes and organizations within the Columbia 

Basin and compile and maintain them in standardized, consistent formats or archive them in original format, as appropriate. 

This is currently a low priority under the existing contract, and data development will be pursued only on other funding.  

Data developed on other funding will be organized and included in the StreamNet database.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






All




No work was performed on this task during the fourth quarter.

Objective
2
Data Development and Updates, Other Data sets
Task
7
Genetics

Develop and maintain information on genetic information and data sources for areas where genetics data exist.  Efforts this 

year will concentrate on organizing existing information, and then working on a Data Exchange Format.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






MFWP
1
Obtain results from genetic analysis from the University of 
Work continued on this ongoing job.   We received a data dump from the 

Montana Genetics Lab for sampled populations of Montana's 
lab during this quarter.

species of special concern.

MFWP
2
Update fish distribution table when new genetic samples affect 
Work continued on this ongoing job.

fields/records.

MFWP
3
Exchange data to the StreamNet regional database when a 
There is no DEF for genetics yet.

DEF is approved by the Steering Committee.


Objective
2
Task:
7
StreamNet Fourth Quarter Performance Report, FY 2002
Page 20 of 56
Objective
2
Data Development and Updates, Other Data sets
Task
8
Information generated during Subbasin Planning

Work with Subbasin Planners to acquire information that is developed for Subbasin Plans and make it available basin wide 

in a standardized format.  Data that fits existing DEF will be incorporated in the queryable database.  Otherwise, data will be 

posted 'as is' and made available on the StreamNet website.  Actual data development beyond the existing DEF would require 

additional resources.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Work with Oregon Technical Support Team (when funded and
Subbasin planning was delayed until FY03 in Oregon.

formed by NWPPC) to obtain existing data in electronic 

format

CRITFC
2
Work with Oregon Technical Support Team (when funded and
Subbasin planning was delayed until FY03.

formed by NWPPC) to develop applications to capture 

additional data generated during subbasin planning

MFWP
1
Will communicate with Montana's CBFWA representative to 
We have not heard anything more about the website posting of subbasin 

better understand where they are in the planning process. 
planning documents for the Flathead and Kootenai subbasins.  We will 

Currently we receive all survey data generated from BPA 
follow up with our CBFWA representative.  Several data management 

contracts in Montana.  Will discuss other products that may 
projects were reviewed with our CBFWA representatives prior to providing

become available.
comment during the CBFWA project review in September.

Objective
2
Data Development and Updates, Other Data sets
Task
9
Supplemental data sets

Obtain data sets that are important to regional monitoring and management but that do not fit the existing DEF for posting 

'as is' on the StreamNet web site.  Primary emphasis will be toward resident fish data developed by BPA funded fish and 

wildlife projects, data developed by cooperating agencies on other funding, and data developed by the FWP.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






ODFW
1
Pursue supplemental data sets on an opportunistic basis 
Staff continued to correspond and coordinate with partners in the Oregon 

consistent with StreamNet direction.
Fish Finder Project, which will add species location information to the 

StreamNet data system.   The Oregon Fish Finder database currently has 

over 1400 independent species occurrences in more than 400 water bodies.


Objective
2
Task:
9
StreamNet Fourth Quarter Performance Report, FY 2002
Page 21 of 56
Objective
2
Data Development and Updates, Other Data sets
Task
10
Carcass placement

Work with management agencies to capture information on placement of salmon carcasses and results from carcass 

placement projects.  This is currently a low priority and will require additional resources to take on as a primary data type.  

Existing data may be acquired for posting 'as is'.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






ODFW
1
Exchange carcass placement report 'as is' for 1999 placement 
1.  The Webmaster reconstructed the html version of the 2001-2002 

efforts.
Carcass Placement Report, and posted the new version on our NRIMP site.

The reconstruction was necessary because the previous html version was 

having intermittent display problems.

2.  The Project Leader provided a link to ODFW's Carcass Placement 

Report to regional StreamNet staff.  This meets our requirement to 

provide this information as an independent data set.

Objective
2
Data Development and Updates, Other Data sets
Task
11
Populations - status and delineation

Develop a data set to describe population status as determined by other agencies.  This is currently a low priority, and efforts 

will be exploratory in nature during FY2002.  Links to existing data may be posted on the StreamNet web site.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






MFWP
1
Species of Special Concern are currently identified on the 
The project leader continues to work with FWP Fisheries Division on 

MRIS website; when the Montana Natural Heritage Program 
Native Species Management areas.

website includes status information on these species, we will 

create a link between our site and theirs.  Will also look into 

linking to USFWS website if information is available on 

Threatened and Endangered Species.  Will link to MFWP new 

native species web page when that becomes available.


Objective
2
Task:
11
StreamNet Fourth Quarter Performance Report, FY 2002
Page 22 of 56
Objective
2
Data Development and Updates, Other Data sets
Task
12
Develop other data sets

On an opportunistic basis, develop data that relate to other existing data sets in the StreamNet database or would be useful 

for regional planning, monitoring or management efforts.  This is a low priority, but some efforts may be expended if the data

appear useful and they can be obtained within current resources.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






ODFW
2
Compile and exchange marked-to-unmarked ratio data ( 
The Project Leader contacted Phil Roger at CRITFC, as well as other 

relative to dam, weir, spawning ground, etc. counts) for an 
StreamNet partners in order to determine regional needs related to 

undetermined location in the Oregon portion of the Columbia 
mark-to-unmarked ratio data.  We wanted to make sure we were working 

basin as a prototype for these data.
on the right things.  Based on the response, it is clear more discussion 

needs to occur at the Steering Committee level to ensure we all know the 

direction for this data category.  Consequently, Oregon's efforts will be 

halted until the project direction is solidified.

ODFW
3
Compile and exchange hatchery-wild fraction data for an 
1.  The Database Analyst resubmitted our Hatchery Fraction Data to 

undetermined location in the Oregon portion of the Columbia 
StreamNet in an Access 2000 database.   The tables were redesigned similar

basin as a prototype for these data.  It is not clear if these data
to the Age table.  There is a FracID field used to correspond to the Trend 

are still available since the dissolution of PATH, and the data 
table, similar to the AgeID field, and then fields that ODFW would like to 

developed by PATH, which are not in StreamNet, need to be 
see in the table for capturing hatchery fraction data.

captured so that they are not lost.  We intend to attempt to 
2.  Staff met to discuss our Hatchery Fraction data and the need for a DEF 

locate and obtain the data in some fashion.
for this particular data type.

Region
1
Advise and assist data developers with other data sets not 
1.  We acquired ESU boundary layers from NMFS.  The GIS Data 

currently in the StreamNet system.  Low priority and within 
Specialist aligned boundaries to match current 100k hydrography.

current resources only.
2.  We acquired 5th/6th field HUC boundaries from REO.  These layers 

will be used in the next project year to allow query of data by 5th or 6th 

field HUCs.


Objective
2
Task:
12
StreamNet Fourth Quarter Performance Report, FY 2002
Page 23 of 56
Objective
3
Data Management and Delivery

Provide high quality data management services, with specific emphasis on creation of regionally consistent data

sets and the timely delivery of data to users in formats that meets their policy, planning, and management needs

Objective
3
Data Management and Delivery
Task
1
Maintain and enhance tabular database systems at the project and regional levels

Maintain functional tabular database programs at the agency and regional levels to make consistent tabular data sets for 

anadromous fish, resident fish and to a lesser extent wildlife available through the StreamNet online database system.  At 

both the regional and agency levels, provide database management and administration necessary for accomplishing 

StreamNet objectives, to include: 1) maintaining and updating the hardware and software systems necessary to support the 

StreamNet project, and 2) enhancing or optimizing StreamNet database structures and capabilities.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






IDFG
1
Maintain and enhance hardware and software for the 
1.  We provided routine system administration to the servers and 

IDFG/StreamNet Fish Information System.  This tasks 
workstations in IDFG/StreamNet.  

includes general system maintenance, addition of new servers 
2.  Our applications and services from our older NT4.0 server were 

and workstations where possible, providing necessary system 
migrated to our new Windows 2000 servers.

administration and disaster recovery, and maintaining software
3.  We configured a subdomain on the IDFG domain so that we can provide

licenses.
adequate security and access to our new resources.

4.  A backup and recovery system was implemented on the new servers. 

5.  We installed IIS (Internet Mapping Services) as our web-server and 

prepared for the installation of ArcSDE and ArcIMS.

6.  We installed additional development software including the .Net 

framework and security patches on our servers.

7.  We installed and configured additional hardware, including a scanner, 

R/W CD drive and two new managed switches.

8.  We installed uninterruptable power supplies and related software on all 

of our servers and workstations.

9.  Detailed system documentation, security plan, and disaster recovery 

plans were started.

10.  Our programmer analyst began work on building XML documents and 

templates for eventual use in transferring data to PSMFC.  This included 

starting a technical white paper proposing data exchange using XML.

MFWP
1
Provide a high-quality, state-level data management system, 
We have been closely involved with the development of Montana Fish, 

emphasizing coordination with StreamNet regional staff, 
Wildlife and Parks' IT plan which has included looking at various goals to 

MFWP and other state and federal natural resource agencies to
help standardize data collection and further integrate StreamNet data 

encourage the use of consistent data attributes and data sets 
structures into the state and federal fisheries agencies.

among all agencies.


Objective
3
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 24 of 56
ODFW
1
Provide state-level StreamNet database management, 
1.  The Database Manager created a utility that takes a database and 

administration, and development.  Enhance StreamNet and 
creates C++ header and implementation source files from selected tables.  

ODFW database structures, interfaces, tools, and capabilities as
These files will allow applications to instantiate objects of whatever type 

needed.  Maintain hardware and software.
(a Trend object, for example).  These objects will then be the interaction 

point for users, instead of the data set itself.  This is the beginning of 

separating our logical and conceptual models away from our physical 

model, which are currently one and the same.  This will allow our data to 

become self-aware and let them think for themselves, ensuring that our 

business rules are followed along the way.  This will be a big step in QA for 

our information, as these objects will not allow themselves to be put into 

an inconsistent state.

2. Staff worked together to begin the creation of an ODFW specific Trend 

object.  This object will encapsulate all the information we require to 

document a Trend and will be able to convert itself into a StreamNet 

Trend following any rules set forth by the DEF.

3.  Staff met to develop a standardized approach for creating metadata for 

our "tabular" databases.  We agreed upon a common set of elements to use 

in our Overview (Tier I) level metadata.   We also agreed upon a 

preliminary approach for our Tier II, or more detailed metadata that is 

still likely to be refined as we put it into practice.

4.  The Assistant Database Manager made further improvements to the 

dam, barrier, fish barrier, and hatchery facility data entry forms.

5.  Staff investigated hatchery releases made in Idaho but listed as 

originating from Oregon Hatcheries.  So far, no solution has been found.  

There may actually be no known solution because neither agency’s 

institutional memory can confirm or refute whether Oregon released or 

transferred fish into Idaho.

6.  The Database Manager started the process of gathering and compiling 

new hatchery return data to update the data sets by going through the 

application he created last year for automating the data retrieval process.  

He is streamlining some areas of the system based on a better 

understanding of the data.

7.  The Assistant Database Manager added latitude and longitude fields to 

the barrier table, and made extensive changes to all of the forms in the 

barrier/dam database.  She reviewed all of the queries in the database and 

removed replication from those that were no longer useful.

Region
2
Maintain and upgrade StreamNet database servers and 
Routine maintenance and administration of SQL Server databases and 

software.  Administer SQL Servers.  Advise on office software 
servers continued.  SQL Server 7.0 was upgraded on the test 

acquisition.  Maintain and optimize database structure and 
database/ArcSDE server to SQL Server 2000.

function .


Objective
3
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 25 of 56
WDFW
1
Coordinate activities to maintain all new and existing WDFW 
1.  We used the natural spawner data submitted this quarter as a test for 

internal tabular databases, code and cross-code assignment files
Bob Woodard (the Region 5 Database Manager )to take over direct data 

related to StreamNet tabular and spatial submissions for data 
submittals to StreamNet henceforth for natural spawner and hatchery 

sets defined in Objectives 1 and 2.     Submit any tabular 
returns.  This strategy will improve one of our data bottlenecks.  Although

databases as warranted to coordinate with spatial layer 
it didn't work as planned and Leslie Sikora (the general StreamNet Data 

exchanges.  Maintain the hardware and software necessary to 
Manager) did a lot of manipulation and review for the submission, the 

the database system.
effort identified and resolved general issues that will allow Bob to solo on 

the next submissions.

2.  After StreamNet issued an updated database (MS Access mdb) in August,

staff incorporated the newer files into their process, especially assessing 

StreamNet's snapshot of WDFW and Washington data and 60K PSMFC trends.

Objective
3
Data Management and Delivery
Task
2
Maintain and enhance the GIS and hydrography database systems at the project and regional 

Maintain functional Geographic Information System programs at the agency and regional levels to make consistent GIS 

layers for anadromous fish, resident fish and to a lesser extent wildlife available through the StreamNet online database 

system.  At both the regional and state levels, provide GIS management and administration necessary for accomplishing 

StreamNet objectives, to include: 1) maintaining regional and agency-level GIS systems, including hardware and software, 

and 2) maintaining a regionally consistent hydrography layer at the 1:100,000 scale.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






IDFG
1
Maintain and enhance hardware and software for the 
1.  We provided routine system administration to the servers and 

IDFG/StreamNet GIS and Fish Information System. This task 
workstations in IDFG/StreamNet.

includes general system maintenance, addition of new servers 
2.  We installed IIS (Internet Mapping Services) as our web-server and 

and workstations where possible, providing necessary system 
prepared for the installation of ArcSDE and ArcIMS.

administration and disaster recovery, and maintaining software

licenses. We will also be evaluating the impact and cost of 

moving from ArcInfo 7.2.1 and ArcView 3.2 to ArcGIS 8.1. 

Depending on that outcome, we may make this major 

software migration this year, including necessary hardware 

reconfigurations.

IDFG
2
Provide GIS support and data infrastructure to the 
1.  Using non-StreamNet funds we  installed GIS data including coverages, 

IDFG/StreamNet Fish Information System. The 
scanned topos, and digital elevation models in several IDFG offices, 

IDFG/StreamNet Fish Information System is built upon a 
including the Eagle Fish Research Lab and the Nampa Regional IDFG 

foundation of GIS data and we will continue to provide that 
office.  We also installed a set of ArcView tools, including a geographic 

base. Products from this task will play a key role in integrating
information locator, an Idaho projector tool, and a set of fish tools for 

GIS with traditional tabular data models, specifically SQL 
attaching data to StreamNet hydrography and assigning LLIDs and 

Server and Microsoft Access.
measures to fish data.


Objective
3
Task:
2
StreamNet Fourth Quarter Performance Report, FY 2002
Page 26 of 56

2.  Using non-StreamNet funds, we modified our Geographic Information 

Locator (GIL) ArcView tool to use image catalogs for the scanned topographic

maps and orthophotoquads. This simplified maintenance of the program.

We also added the Geographic Names Information System to GIL.

3.  We coordinated with the IDFG Clearwater Region office about getting 

them set up with our GIS data and tools.

MFWP
1
Maintain, update and enhance MFWP GIS data layers, provide
We are currently updating the Bighorn Sheep, Mountain Goat and Black 

these data as distributed files, on the web or as part of map 
Bear layers (funded outside StreamNet); we just completed antelope and 

requests.  Integrate the use of GIS into management decision 
will update westslope cutthroat trout following then Federal Assessment 

making processes.(Most of this work is conducted outside the 
process.

StreamNet contract with MFWP dollars).  Maintain the 

MFWP StreamNet GIS system.

MFWP
2
Work with Natural Resource Information System staff and 
The maintenance of the hydrography data layer is ongoing; a training on 

StreamNet GIS staff to maintain the 1:100 K NHD 
the NHD for Montana will occur in October.  StreamNet staff will assist 

hydrography for Montana.  Data layer will be enhanced with 
with development of the training program.

lakes and reservoirs and include stream level LLID routes.

ODFW
1
Develop and maintain a fully functioning GIS system and the 
1.  The 24K Project GIS Coordinator spent some time trying to identify 

database structures that help improve spatial data management
"duplicate arcs" in the converted 100K distribution.  She found that any 

and transfer with ODFW staff and the regional StreamNet 
event that translates to an arc with greater than 500 vertices gets split 

system..  Maintain the hardware and software systems 
into two (or more) arcs, all with identical attribute information (e.g. 

necessary for the GIS.
BEGMEAS and ENDMEAS).  After researching options to adjust the 

BEGMEAS and ENDMEAS values on the arcs, much discussion with our 

GIS Analyst, and performing a brief survey of a few data users, we 

concluded to drop the BEGMEAS and ENDMEAS items from the arcs.  

Users will still have access to that information via the event tables--our 

main concern was that users would use the BEGMEAS and ENDMEAS 

items to calculate length for summary purposes, and get erroneous values.

2.  The GIS Analyst completed metadata for Oregon’s dams coverage.  He 

also documented online files and data processing procedures.  Lastly, he 

created coverages of status level 1 barrier and dam data in order to work in 

the direction of posting these data to the FTP site and make them 

available publicly.

Region
1
Assist the database manager, as needed, with the spatial 
The GIS Specialist assisted in the spatial location of features within the 

component of data and its implementation online.
database.


Objective
3
Task:
2
StreamNet Fourth Quarter Performance Report, FY 2002
Page 27 of 56
Region
3
Maintain functioning  GIS software at regional office (two 
The GIS Specialist updated our GIS software to ArcGIS8.2, and ArcIMS 4.0

seats) + server products, including installing new software and 

making upgrades to old software, fulfilling contract obligations

to ESRI (software vendor), and keeping abreast of GIS 

software developments that could be beneficial to the project.

Region
4
Maintain a library of StreamNet GIS layers for internal use and
The GIS Data Specialist converted several data layers' metadata from text 

as downloadable data on the web site with complete 
based format to FGDC compliant format.

documentation (metadata).

Region
5
Maintain a regionally consistent 1:100,000 hydrography layer
The 1:100,000 hydrography layer was maintained.

(the PNW Reach File) for internal use and public access 

through consultation with the state stewards of the hydrography.

WDFW
1
Coordinate activities to maintain all new and existing WDFW 
1.  WDFW StreamNet tabular staff continue to be key players in creating 

internal spatial layers related to StreamNet tabular and spatial 
the infrastructure to spatially enable tabular data and educate everyone 

submissions including but not limited to 100K hydro (streams 
about the issues.  Gil Lensegrav (StreamNet Tabular/GIS Compiler) 

and lakes), marine areas, distribution, production (hatchery 
provided WDFW's Sara LaBorde (Special Assistant to the Director) with a 

and dam), and release site layers.  Manage regionally standard 
PowerPoint presentation, outlining the steps to georeference study sites 

location codes (LLIDs).  Submit any spatial layer as warranted 
with existing GIS tools.  In general, Sara is leading the effort to induce 

to coordinate with tabular exchanges.  Maintain the hardware 
WDFW to fund more GIS projects.

and software necessary for system function.
2.  We developed a process and ArcView project to digitize points relevant

to natural spawner salmon data for a portion of a 100K stream or to 

represent a 24K stream on the 100K hydrolayer.  These points are 

essentially to visually convey the data and subsequently determine the 

BegFt and EndFt measures.   We will use this ArcView project and layer to 

add points as needed for other data types (i.e. steelhead natural spawner, etc).

3.  A compiler traveled to Ellensburg to confer with Gabriel Temple about 

the applicability and follow-up work needed on the database and spatial 

files he delivered last quarter. 

4.  We refined more of our previous work on the spatial layer that defines 

the boundaries of the Salmon Management and Catch Reporting Area and 

are delivering it to requestors (like NMFS) as warranted. 

5.  The Region 5 WDFW StreamNet Data Manager began setting up a 

process and workstations for GPS/GIS manipulations. The greatest GIS 

experience has evolved out of our Olympia office so an Olympia-based 

compiler traveled to Vancouver to assist with setting up the PCs as needed.

6.  WDFW's GIS Data Manager re-programmed his system to make the 

hatchery facility and lake layers accessible after a major system/platform 

change to the Network Attached Storage (NAS) system.


Objective
3
Task:
2
StreamNet Fourth Quarter Performance Report, FY 2002
Page 28 of 56






7. WDFW presented potential issues related to future data sharing with 

StreamNet related to WDFW's move to linking fish and habitat data to the

WDFW routed 24K hydro layer built for Washington state. WDFW 

agreed to draft a written summary of these issues and circulate the draft 

prior to the next Steering Committee meeting to keep the discussion alive.

Objective
3
Data Management and Delivery
Task
3
Data management and coordination

This task includes data management after they have been developed.  Once data are submitted to the regional database, assure they fit

established formats, perform appropriate error checks, and load the data into the StreamNet database and perform routine management

of the data.  The regions and contributing agencies will collaborate to fix problems and assure seamless loading of data into the database.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






IDFG
2
Review and update entire redd count data set, in order to ensure
IDFG/StreamNet completed its review of existing redd count data.  This did not

the proper past assignment of trend definitions, location 
include a review of trend definitions, but the data from the actual field Surveys

identifiers, and accurate counts.

IDFG
3
Add additional stream routes and assign LLIDs to 1:100,000 
We continued to collect a list of modifications to make in the 100K 

scale hydrography. New routes will be added as required to 
hydrography.

support locational data in the IDFG/StreamNet Fish Information

System. All new routes will be submitted to PSMFC.

ODFW
1
Work with regional staff as necessary to assure seamless 
1.  The Database Manager developed a tool to compare Trend data at StreamNet

loading of data into the regional database.
to data in Oregon’s Trend database, providing the ability to assure data are

consistent between databases.  Reference, EscData, and Trend tables that highlighted differences between the StreamNet version and the ODFW version were provided to Oregon’s Database Analyst.  She reviewed 1,057 of the Trend differences.  This was very helpful in finding some coding errors.  She requested and received the notes the Regional Database Manager made while updating the StreamNet database with an ODFW Trend submission.   Field values were changed where necessary to match StreamNet's (i.e. HistoricID changed from null and "0", to 99; Unknown).  A missing reference was located, and correct data were verified.

2.  The Database Analyst talked to the Regional Database Manager about the 
process for submitting age and mark recapture data, and followed up on her hatchery fraction data submission

3.  Staff contacted Regional Database Manager to understand the purpose and 

direction of the HatcheryxProduction Table forum discussion.

4.  The Project Leader contacted Regional Database Manager regarding the format 

StreamNet would like to see 'unrolled' hatchery release data submitted in.


Objective
3
Task:
3
StreamNet Fourth Quarter Performance Report, FY 2002
Page 29 of 56

5.  The Assistant Database Manager responded to an inquiry from Regional 

Database Manager regarding Oregon's hatchery infrastructure capabilities.

6.  The GIS Analyst followed up with issues related to the recent distribution data

submission to StreamNet.  Only 8 records needed further evaluation, 3 of which had

to do with reconciling records with WDFW and IDFG for the Columbia and Snake 

rivers.  He contacted the district biologist to confirm our use-type designations for

summer steelhead in the Snake River.  We're down to a single record remaining to 

be reconciled that IDFG is now researching.

Region
1
Whenever new tabular data with a spatial component are 
The GIS Specialist received, formatted Oregon anadromous fish distribution as

submitted to the project (e.g., fish distribution, hatchery 
a GIS layer.

facilities, etc.), create regional GIS layer(s) from this 

information where possible.  Verify correct format, accuracy 

and logical consistency of spatial data sets and attributes 

through coordination with state GIS contacts and then load 

data to the regional database in coordination with the database

manager.  Post mappable layer(s) for the online query system

and as downloadable layer(s) for StreamNet GIS users.

Region
3
Update and append data as submitted by StreamNet participants.
1.  Trends in the 60,000 series, originally entered by PSMFC, were replaced by 

Isolate erroneous or duplicative data and work with source
WDFW, ODFW,IDFG and CDFG.

agencies to correct problems.  Produce downloadable versions
2.  Trend & Escapement data were loaded from WDFW (statewide natural spawner

of StreamNet databases.   Maintain logs of data submissions
data through 2000) and CDFG; these data types were received from ODFW and

and major database changes.
will be loaded next quarter.

3.  Hatchery Facility records were updated from IDFG and CDFG, and were 

received from ODFW.

4.  Hatchery Returns data were loaded from IDFG and CDFG, and were received

from ODFW.

5.  Dam Facilities information was loaded from a FERC spreadsheet and from 

CDFG, and was received from ODFW.

6.  Spawner Recruit data (1129 records) from ODFW were loaded.

7.  A test set of Hatchery Release data was received from ODFW in PSC exchange

format prior to being rolled-up by coded-wire tag code.


8.  A test Hatchery Fraction (artificial vs. natural production ratios) record set was

received from ODFW for evaluation as a new data category.

9.  Barriers updates were received from ODFW.

Region
4
Examine the StreamNet database for errors and report any 
Work continued on this ongoing task.

found to the appropriate entity for correction.


Objective
3
Task:
3
StreamNet Fourth Quarter Performance Report, FY 2002
Page 30 of 56
WDFW
1
Work with regional staff as necessary to assure seamless 
1.  The WDFW StreamNet Data Manager met in Portland with 

loading of data into the regional database.   Explore new ways 
StreamNet's Regional Data Manager to discuss a variety of current issues.

to simplify the instructions to the Regional Manager on how 
2.  After notification that some location-related field data was missing in 

to post our data submission and purge any old records that are 
the August Natural Spawner Salmon data submission, we submitted 

now irrelevant to avoid follow-up issues.
corrections in September to provide complete location-related data.

Objective
3
Data Management and Delivery
Task
4
Data Exchange Standards

Establish and maintain data exchange standards to ensure consistent content and format of data that originate from multiple data sources.

Track adopted and proposed data exchange formats and location coding (including metadata) for data categories described under Objectives

1 and 2.  At the regional level, this task will provide coordination and technical assistance regarding interpretation of database structures

and codes.  At the agency level, this task will provide similar coordination and technical assistance to activities applicable to StreamNet.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Review and comment on DEF issues brought to the Steering 
Proposed DEF changes were reviewed and commented on as appropriate.

Committee

CRITFC
2
Propose a draft DEF for genetics data to the Steering 
A draft DEF was completed earlier in this contract year. There is no agreement

Committee, based on the application and comments received 
among the state agencies on what genetic information to share through StreamNet,

under Objective 2, Task 7,  job 1.  Work with MFWP on 
so the Steering Committee should place a low priority on further development of

development of the draft.
genetic data. Individual state approaches are encouraged to test various options.

FWS
1
Review and comment on DEF issues brought to the Steering 
Pastor continued checking on the progress in development of a new Hatchery

Committee
Returns DEF.

IDFG
1
Working with the StreamNet Steering Committee, maintain 
1.  The Steering Committee started an effort to develop a protocol for making new

and enhance the data exchange standards as needed.
or changes to data exchange formats.  We provided input to the first draft.

2.  All IDFG/StreamNet staff participated in the development of new and existing

data exchange formats.

MFWP
1
MFWP StreamNet will participate in the design, development 
The project manager developed a first draft of a DEF process for review by the

and maintenance of standard codes and data exchange formats.
Steering Committee.  Discussions will occur at the October meeting.

This will occur through involvement on the Steering 

Committee and technical work groups.

MFWP
2
Work with CRITFC to develop a draft DEF for genetics data 
The broader effort to develop a genetics DEF did not progress as planned this

for adoption by the Steering committee
quarter.  Montana will continue to utilize its existing DEF, and will participate

in development of the broader DEF in conjunction with the CRITFC staff.

MFWP
3
Work with Regional StreamNet staff and Steering Committee 
Montana has adopted the DEF and has no requested modifications.

to create a Data Exchange Format for Distribution and Use Type.


Objective
3
Task:
4
StreamNet Fourth Quarter Performance Report, FY 2002
Page 31 of 56
ODFW
1
Participate in the design, development and maintenance of 
The Database Analyst developed and submitted a DEF for Hatchery 

standard codes and data exchange formats. This will occur 
Fraction data and participated in forum discussions related to this proposed

through involvement on the Steering Committee and technical
DEF.

work groups. There is no set schedule for this task, because it is

highly dependent on issues facing the Steering Committee.

ODFW
2
Develop and propose a DEF for screening data.
The Assistant Database Manager worked on preparing the fish screening 

and passage data exchange format for submission to StreamNet.  She 

completed the first draft of the Fish Screening and Passage Data Exchange 

Format (DEF) and submitted it to Oregon staff for review.   A second draft

was then completed, reviewed, and submitted to StreamNet as a draft data 

exchange format.  A StreamNet forum discussion to allow folks to 

comment on the DEF was also initiated.

Region
3
Enhance the StreamNet data reference system by repairing or 
Data References were appended from ODFW, WDFW & IDFG.

establishing procedures for updating and reconciling data-

related references between the StreamNet database at PSMFC

and the StreamNet Library database housed at CRITFC.

Region
4
Maintain and update the StreamNet Data Exchange Format as 
1.  WDFW and PSMFC worked with personnel from California Fish and 

necessary to incorporate additions and modifications agreed to
Game on proposed changes to the structure of the habitat restoration 

by the Steering Committee.  Record accepted revisions in the 
projects data exchange format.  These proposals will be brought to the 

DEF document.  At least one update of the DEF document will
Steering Committee during the first quarter of FY-03.

be made during the year.
2.  Regional personnel reviewed a proposal from ODFW for adding a 

hatchery fraction data category to the StreamNet DEF.  This proposal will

be brought before the full Steering Committee during the first quarter of FY-03.
Region
6
Create a white paper examining the implications for a major 
A first draft of the DEF simplification paper was completed this quarter 

simplification of the StreamNet Data Exchange Format.  A 
and sent to several people for comments.  At the end of the quarter this 

simplified DEF, using much flatter tables, could greatly ease 
work component was approximately 2/3 complete.

data submittal for StreamNet participants and potentially 

speed data flow to the regional database.  It may also permit 

much easier data capture from people outside of the 

StreamNet project.  However, potential complications of such

an approach could include data integrity problems, 

unacceptable workload shifting, and a variety of other issues.  

Explore these issues and create a report on the potential 

benefits and detriments of a simplified DEF.

Region
7
Assist with development of XML schema based data exchange 
We acquired XMLSpy software, but had little time to investigate it's value 

option for both incoming and outgoing data.
in accomplishing this work component.


Objective
3
Task:
4
StreamNet Fourth Quarter Performance Report, FY 2002
Page 32 of 56
WDFW
1
Engage in data exchange format (DEF) discussions.  Lead new 
1. We continued to provide feedback on the latest proposals to change the

efforts to amend the format as warranted when WDFW's data 
 Habitat Restoration data exchange format (DEF).

cannot be accurately converted.  Provide metadata for tabular 
2. WDFW staff provided feedback to Montana's proposal for formalizing 

and spatial data sets according to guidelines adopted by the 
the DEF creation/adoption process.

Steering Committee.
3. At the August Steering Committee meeting, WDFW staff approved the 

proposal to replace various location related fields with a new LocationID 

field in several of the exchange formats (proposal was adopted). WDFW 

staff also engaged in discussions on null values in Count Value, the 

usefulness of computed mean values, and the appropriateness of Regional 

staff deriving missing values in state data. These last discussions were left 

for future follow up actions.

WDFW
2
Develop a revised DEF for Hatchery Return data and propose 
We spent some time reviewing WDFW's 2001 hatchery returns data to 

to the Steering Committee
assess it's fit for the latest StreamNet DEF proposal and general issues.  We

also reviewed IDFG's counter DEF proposal. Our final act was to post the 

most recent draft DEF, a summary of reasons for the changes,  and a 

proposed path forward to the Forum for follow up discussion and 

resolution by the Steering Committee (under the proposed guidance of 

PSMFC staff). We summarized this posting at the August 2002 SC 

meeting, emphasizing our view that the Regional staff should begin leading 

the effort to find resolution with a final DEF. The Region has greater clout

to bring the discussion to quicker resolution.

Objective
3
Data Management and Delivery
Task
5
StreamNet Internet Site

Continue to maintain and enhance the existing client-server system to provide access to StreamNet data products through the

Internet.  The StreamNet home page will continue to be recognized as the project's primary data delivery vehicle.  Priority 

will be given to incorporating data developed through Objectives 1 and 2 and providing access to reference materials secured 

through Objective 4.  Appropriate training on the use of the system will be provided through a combination of on-line help 

and in-person training sessions.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






ODFW
1
Recommend and/or take part in review of new products and 
The Assistant Database Analyst reviewed and commented on StreamNet's 

features.  Provide feedback on content, suitability, navigability
new dam facilities mapping feature, at the request of David Graves.

and data currency issues.


Objective
3
Task:
4
StreamNet Fourth Quarter Performance Report, FY 2002
Page 33 of 56
 ODFW
2
Work with Regional StreamNet staff to link the StreamNet
No input was submitted from CRM by the deadline for this task.

website to available Columbia River fisheries information 

(including Columbia R. Compact Action Notices, In-Season 

Updates, Joint Columbia River Management Staff Reports and 

possibly in-season catch estimates), along with informational.


text to describe each link
ODFW
3
Finalize a summary of real-time data services that can be 
No input was submitted from CRM by the deadline for this task.

provided, as well as a description of how these services differ 

from current data services provided in the Basin.

ODFW
4
Manage and maintain the ODFW Natural Resources 
1.  The Webmaster responded to numerous information requests from web 

Information Management Program website and it's links to 
site visitors.  She also added a link to StreamNet's Interactive Mapping 

StreamNet.
Applications page to all of our NRIMP maps pages.  She posted Monthly 

Features for July, August, and September, and updated and posted the 

Monthly Feature index page and the What's New page.  Lastly, she updated

numerous other pages including the Contacts, 24K Contacts, State Agency

Links, and FAQ pages.

2.  Oregon’s 2001 Carcass Placement Summary Report was posted on the 

NRIMP website, as was information pertaining to Oregon’s Fish Screen 

Database.

Region
1
Maintain the GIS Data, Map, and PNW Reach File Internet 
The GIS Specialist continued to maintain the GIS Data, Map and PNW 

pages.
Reach File Internet pages.

Region
2
Add an internet mapping component to the StreamNet site to 
The programmer monitored and ensured that the mapping applications 

allow users to access StreamNet data through an interactive 
were always available during transition to the new GIS Specialist.

map interface.  Internet mapping component will utilize 

spatial database engine (SDE) technology to improve speed 

and performance, and will utilize ArcIMS software for 

application design and delivery.  Internet mapping component

will serve at least 2 purposes:  (1) to provide users with a 

vehicle to display and query StreamNet data in a spatial 

format; and, (2) to provide an alternate means of entry to 

access information in the current StreamNet query system.


Objective
3
Task:
5
StreamNet Fourth Quarter Performance Report, FY 2002
Page 34 of 56
 Region
3
Maintain and enhance the look and usability of the current 
1.  We added enhanced error reporting functionality to help us determine 

web-based query system.
the exact URL where web site users are when they report an error.

2.  We began updating the query system screen and download report output

 from Output Review.

3.  We updated the output report for Redd Counts to reflect requested 

changes by the Steering Committee.

4.  The hatchery category output reports were enhanced to show hatchery 

Use Types.
Region
4
Develop and test a new and enhanced web-based query system 
1.  We implemented the latest ColdFusion version (MX) on the test query 

based on a more open and flexible programming environment 
system.

(Cold Fusion).
2.  We began testing and planning for using then new ColdFusion version 

to add functionality to the Tabular Query System.

Region
5
Deploy features of the new flexible query system as 
1.  With modernized georeferencing of the Protected Areas database 

components are approved by the Steering Committee
completed, the web query system was modified to use these updated 

methods.  This allowed more complete integration of this data type into 

the query system, which reduced some query system programming 

complexities and also allows users to query for these data using the 

standard geographic criteria available for the other data categories.

2.  Several requests have been made over the past few years to permit 

searching for specific time series via the TrendID number.  A concern with

implementing this feature has been that TrendID numbers are not static, 

though they change infrequently.  During this quarter, it was decided to 

implement this ability in the web query system, but to do so with a warning

disclaimer regarding the possibility that TrendIDs may have changed.  

This feature was implemented during the quarter.

3.  A number of query system enhancements that had been completed were

checked for functionality and removed from the list of enhancements to perform.
Region
6
Maintain logs of web query history and error events.  Track 
Apache log format changed at the beginning of August which accidentally 

and report internet site usage by month and investigate web 
broke our usage analysis tool's ability to parse the logs.  We are now in the

query system errors encountered.  Assist programmer in 
process of converting logs for August and September to get usage and error

debugging web query system problems that may be data related.
numbers.

Maintain and upgrade StreamNet web server and software.


Objective
3
Task:
5
StreamNet Fourth Quarter Performance Report, FY 2002
Page 35 of 56
 Region
7
Guide development and enhancement of the StreamNet web 
The regional fisheries biologist (PSMFC) and the assistant librarian 

query system from the perspective of data users.  Review 
(CRITFC) reviewed the output of the web query system for all data 

changes to the web query system to ensure they are 
categories.  They evaluated the completeness, accuracy, and format of the 

implemented appropriately and do not create unforeseen bugs.
information in the on-screen output and the ASCII files produced by the 

query system.  This overall examination was needed to ensure that changes

to the database that had been implemented in the past due to changes in 

the data exchange format were being included in the output to users.  It was

found that quite a few items were not being provided for the users.  These 

items were identified and a list was given to the programmer, who began 

the process of modifying the web query system to include the missing 

items and correct the few errors found.

WDFW
1
As time permits, review new products and features of the 
We reviewed StreamNet's ArcIMS application as it relates Dam related 

StreamNet Internet site. Provide feedback on content, 
data and provided more feedback.

suitability, navigability and data currency issues, especially 

issues related to providing static or dynamic map capabilities.

Objective
3
Data Management and Delivery
Task
6
Tool development and maintenance

Provide programming services to project participants to support efficient data entry and transfer.  Tools may be developed at the

regional or agency levels.  Even when developed for within agency use, tools should be shared among all project participants.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Provide support services to CRITFC staff working on 
Advice and suggestions were provided to staff working on inter-agency M&E and

interagency information issues, as needed
subbasin planning issues. These efforts, however, are only in the planning stage.

IDFG
1
Continue to develop the IDFG/StreamNet Fish Information 
1.  The interfaces and databases for our hatchery facilities and hatchery returns

System (FIS). The FIS provides data entry and management 
data were updated to reflect recent changes in the data exchange formats.

tools to IDFG biologists. It also provides for an electronic 
2.  We began development of an interface and analysis module for defining

flow of data from the field to StreamNet. It ensures data 
and updating StreamNet trends.  This module is intended primarily to

integrity, data and coding standards, and an efficient transfer 
address an immediate need to review trend definitions of redd count data,

of data from the field to StreamNet.
but will be utilized for maintaining the trend definitions for all data categories.
MFWP
1
Maintain and enhance the edit/entry interface for fisheries 
Work continued on this ongoing job.   We worked with several National Forests

survey data distributed to individuals with a MFWP Collector's 
on data formats.

permit, including federal land management agencies.

MFWP
2
Explore creating a complete user interface for MFWP 
Work continued on this ongoing job.

biologists, preferably a web based system; standardize look-up 

tables across the state.


Objective
3
Task:
6
StreamNet Fourth Quarter Performance Report, FY 2002
Page 36 of 56
 MFWP
3
Maintain the U of M system for genetics analysis input, 
Work continued on this ongoing job.   We received a another database dump 

Future Fisheries for restoration project data entry, and other 
from the Genetics lab and checked it against the MFISH database.

interfaces upon request if they relate to StreamNet workplan.

WDFW
1
Review and give feedback on StreamNet's tools.  Also build 
The WDFW StreamNet Data Manager provided feedback to the Regional 

internal tabular and GIS tools and procedures to efficiently 
StreamNet Fish Biologist to discuss issues pertinent to his white paper on 

manipulate data , including the conversion of WDFW's 
flattening the DEF before the Region submits the paper for global discussion.

Paradox data to MS Access.

Objective
3
Data Management and Delivery
Task
7
Data / Information Requests

Receive and respond to requests for data and information, source materials, and custom products.  Response to requests will be honored

within the limits of available resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.

Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural resource management 

activities.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






IDFG
1
Respond to requests for data and queries of the IDFG/StreamNet
We filled 47 requests for data or assistance that came directly to our office.

Fish Information System. These requests come from a variety
The requests consisted of 20 project specific species lists, 8 GIS data sets,

of sources, federal agencies, state agencies, and private
5 fishery data sets, 9 requests for assistance or technical problems, and 5 GIS

consultants.  All data requests will be logged for reporting.
maps.

MFWP
1
Receive and respond to requests for data, source materials, and
The staff filled 20 GIS request during the quarter including 12 fisheries related

custom products.  Respond to requests within the limits of 
GIS requests.

available resources, with priority given to information requests

having direct relevance to the F&WP.

ODFW
1
As requested, consistent with other deliverables in this 
A total of 10 data, 7 document, 6 map, and 23 'other' requests were answered

contract, receive and respond to requests for data, source 
during this quarter. A detailed list by requester and request type can be made

materials, technical training, and custom products.
available upon request.  Also, 2,747 data downloads were made from the ODFW

FTP site during this quarter.  The list of requests below is provided as an

example of the range of requests we respond to.  These requests include:


1.  A query of our database to provide all the information we had on 

ODFW Oregon Plan-related projects.  This was not an easy task, as we do 

not code our projects by agency or program.  We were able to provide a 

complete list of projects whose reference data comes from an ODFW 

contact.  Additionally, we provided a long list of trends where the agency 

was not identified, giving the requester the opportunity to sort through the

titles to determine if the project was of interest to her.


Objective
3
Task:
7
StreamNet Fourth Quarter Performance Report, FY 2002
Page 37 of 56

2.  A request from the StreamNet web page (via Bruce Schmidt) to assist a 

user with projection information.

3.  A request from the Nehalem Watershed council regarding where to find 

ODF Forest Practices Act fish bearing stream information in GIS format.

4.  Questions from the new Clackamas STEP biologist about GIS software 

and data.  She is hoping to get set up with ArcView and as much relevant 

data as possible in order to provide support for her work.

5.  FTP tech support to an EBA (ODFW temporary technician position) 

assisting with the Chinook Monitoring Project.

6.  A request for source information for a Protected Areas data set.

7.  A requested for metadata for our Wildlife Management Units GIS coverage.

8.  A request for a Klamath Water Rights map for Jill Zarnowitz, ODFW.

9.  A request to convert a postscript file to pdf format.  The requester was 

also told about freeware (Ghostscript and GSView) available for converting 

postscript to pdf.

10.  Questions from a user about projection information as well as current 

vs. historic distribution.  This request lead to clarifications in the metadata 

related to this issue.

Region
1
Respond within one day whenever possible to users who 
Regional staff responded to 58 requests for information or help during the 

request information or assistance.  Requests may be for help in
quarter.  Twenty nine of these requests were GIS or map related.

navigating the StreamNet web site to find desired 

information, help in learning to use the on-line data query 

system, help in finding information not contained in 

StreamNet, assistance finding GIS layers, providing unique or 

customized data, or a variety of other types of requests.

WDFW
1
Generate maps, data reports, and electronic copies of data sets
Staff responded to requests for thirty data requests and documented them 

as requested.  Provide PRIORITY data support for subbasin 
in a detailed database available on request.  Our clients continue to be 

assessments and other new elements of the NWPPC Fish & 
interested in all data types, including requests for assistance on how to 

Wildlife Program, within existing resources.
manipulate their own data or use available software.


Objective
3
Task:
7
StreamNet Fourth Quarter Performance Report, FY 2002
Page 38 of 56
Objective
4
Library / Reference Services

Provide professional library services to the Columbia Basin's fish and wildlife decision-makers, planners,

managers, and researchers by acquiring and cataloging StreamNet source documents and other related


material; and by providing open and efficient access to these materials

Objective
4
Library / Reference Services
Task
1
Collection Development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document data sources,

Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies, interested parties, and

other libraries.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Coordinate source material submissions for data compiled by 
1.  The Library received and cataloged materials from California and Washington.

Participant
2.  The Library received approximately 50 boxes of materials from a closed library

in Canada and from a document supplier in Idaho (Inez Hopkins).  Some of these

documents may be useful in the StreamNet collection as materials that were never

received or possibly are missing.

CRITFC
2
Develop collection of materials related to the Columbia Basin,
The library added approximately 325 new items to the library catalog.  As 

including reports from other Fish and Wildlife Program projects,
mentioned previously, many more items were received than could be cataloged.

other agency documents as they relate to the Basin, and other
In addition, many records were updated to add more information about the

published and unpublished materials as requested by clients.
documents.

CRITFC
3
Maintain and develop a collection of journals related to 
The Library reviewed all the current subscriptions and have chosen to continue

fisheries and aquatic sciences as well as other related scientific 
most and add a few new titles that will be of use to patrons.  We received 

topics.
approximately 200 loose issues of journals we do not have subscriptions to and

have filled in back years of current subscriptions.

CRITFC
4
Format the library reference table of StreamNet documents 
The Librarian continued working with the Regional Data Manager to integrate the

for inclusion in the StreamNet database.  New updates will be 
library reference information into the StreamNet SQL database so that the data

sent to the regional database monthly after that.
may be linked directly with the documentation.

MFWP
1
Update the StreamNet library with references and publications 
We will update when it is requested.

from the Fisheries Division Library on an annual basis.

MFWP
2
Collect and catalog supporting references to document the 
Work continued on this ongoing job.

sources of the distribution information and other data types 

developed under Objectives 1 and 2, and to connect the data to

references.  Submit updated references to the StreamNet Library


Objective
4
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 39 of 56
ODFW
2
Provide originals/copies of all documents and reports 
The Database Analyst compared tables made between StreamNet's and 

referenced in the compilation of new StreamNet data holdings,
ODFW's Reference table.  She reviewed approximately 1,600 of the 

but not already housed in the StreamNet Library.
Reference records for discrepancies.  Following this, she prepared the 

Reference table for submission.  The reference submission was made to 

StreamNet, our first with more electronic documents than paper ones.  In 

addition, she incorporated new references from staff, which were added to 

the table but not submitted yet.  To improve management of the reference

data set, she created a table called Whose_Reference, to track who 

provided the reference initially.

ODFW
3
Organize and submit to the StreamNet library all references 
This job is essentially a sub-component of Objective 4, Task 1, job 1.  

related to the data developed under Objectives 1 and 2.
Therefore no information is provided here.

WDFW
1
Engage in discussions to finalize procedures to submit spatial 
Staff continued to process references for any data compiled for StreamNet 

data references.  Continue to collect documents used as source 
and submit them to the library in concert with data submitted to 

materials for any data in Objectives 1 and 2. Documents will 
StreamNet.  This quarter, to expedite data submissions  we started using a 

be assigned reference numbers and forwarded to the StreamNet
temporary reference code if we had data ready for a submission but the 

library as per established SN guidelines.
reference data wasn't completely ready.  The temporary reference code 

will be replaced in subsequent submissions and the physical reference 

documents, etc will be then be submitted to the library.  Although the 

reference issues are usually minor, this is the most efficient process to 

minimize the circulation of incomplete physical references.

Objective
4
Library / Reference Services
Task
2
Provide Access to Collection

Provide user access to the materials described in Task 4.1 by providing facilities for storage of paper and electronic copies of 

documents, an online catalog of all documents in collections, and staff to answer location questions and respond to requests.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Provide and maintain an appropriate facility for the storage 
The CRITFC and Ashforth Pacific signed the lease for the increased space 

and public use of the StreamNet Library collections.
for the Library, effective November 1, 2002.  We have drawn up 

preliminary floor plans and have purchased shelving to store materials.

CRITFC
2
Catalog and organize the materials for ease of use by clients 
The Librarian completed re-cataloging approximately 50 StreamNet 

and staff.
references.  In addition, several reference documents were identified for 

filing in the numerical filing system and moved to filing cabinets for easier 

storage.  These documents will be on the priority list for digitization.


Objective
4
Task:
2
StreamNet Fourth Quarter Performance Report, FY 2002
Page 40 of 56
CRITFC
3
Provide access to the catalog of materials via the Internet and
The Library began using Dreamweaver to update the library catalog on a 

update the online catalog on at least a monthly basis.
regular basis.  This process can now be accomplished in a matter of 

minutes rather than the hour it took previously.  We have also begun 

looking at how we may make the library website more interactive for users

to find what they want more quickly.   Several more patron web pages 

have been added for people to access documents they have requested.

CRITFC
4
Develop and execute a plan to place electronic documents in 
The library continued to digitize documents by patron request.   We have 

the catalog and on the library website.
also completed the process of adding a duplexing printer to the library so 

that we can make hard copies of documents that are currently only 

electronic.  As these documents age, many agencies rotate them out of 

public view on their web sites, making them difficult to retrieve.  Electronic

copies also tend to degrade with use and will eventually be unreadable.  We

are attempting to preserve this large body of work.

CRITFC
5
Develop and keep schedule of open times and reference desk 
The library has remained open during posted hours.

staff hours.

Objective
4
Library / Reference Services
Task
3
Library Services

Manage the StreamNet Library and provide library services to the StreamNet user community, Fish and Wildlife Program, 

and the general public.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Provide information and reference services to library clients
The library staff answered over 343 requests.  At least 34 were from 

federal agencies, 170 were from outside consultants, 97 from CRITFC and 

tribal employees and 42 did not disclose their affiliation.

CRITFC
2
Provide information about services and hours to library clients
The library web pages were kept up to date for holidays and open hours.  

via print and Internet
Staff only print the library brochure in small runs to make sure the 

information stays as current as possible.

CRITFC
3
Provide interlibrary borrowing services for library patrons to 
Statistics on interlibrary loaning are now wrapped into the reference 

access materials not yet owned by the StreamNet Library.
requests, as invariably reference requests eventually turn into interlibrary 

requests.

CRITFC
4
Provide access to hardcopy and electronic files of draft and 
We continued the evaluation of bibliographies from the 1990 individual 

final documents related to subbasin planning and the NPPC 
subbasin plans so these documents may be added to the subbasin pages.

amendment process.


Objective
4
Task:
3
StreamNet Fourth Quarter Performance Report, FY 2002
Page 41 of 56
ODFW
1
Enhance, maintain, and update ODFW Library software and 
1.  ODFW's Library was closed during this quarter due to budget constraints.  Our

procedures to ensure adequate tracking of information 
goal is to reopen the Library between October 2002 and January 2003.

requests, key word searches, and easy comparison to the 
2.  We acquired a copy of "Field Identification of Coastal Juvenile Salmonids" by

StreamNet Library holdings.
W.R. Pollard, B.F. Hartman, C. Groot, and Phil Edgel from Jeff Rodgers to fill a

library wish list request that was posted on the NRIMP web site.  Our web site

was modified to reflect that this request had been fulfilled.

ODFW
2
Respond to requests for ODFW documents and other source 
ODFW's Library was closed during this quarter due to budget constraints.  Our goal

materials through the ODFW Library.
is to reopen the Library between October 2002 and January 2003.

Objective
4
Library / Reference Services
Task
4
Inter-library Coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other collections that

will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Provide interlibrary lending services for other libraries to 
We provided over 60 items to other libraries.

access the library's unique collection

CRITFC
2
Maintenance of memberships in appropriate library and subject-
1.  The Assistant Librarian participated in the tribal focus group as part of the 

related associations.  Ex. IAMSLIC, NRIC, OFWIM, etc.
regional data inventory project being conducted by SAIC for the Council. 

2.  The Librarian attended the NRIC annual conference. 

3.  The CRITFC StreamNet staff participated in the Science booth at the 

Wy-Kan-Ush-Pum festival.  

4.  The Library hosted the Downtown Portland Librarian's group in September.

CRITFC
3
Provide consultations for groups and other agencies on library 
Library staff answered questions from S. P. Cramer & Associates on setting up a

organization and services.
library.

CRITFC
5
Work with subbasin planning groups and TRTs to identify 
There were no contacts from the TRTs or subbasin planning groups this quarter.

modifications and new uses to make information related to 
The Council's subbasin planning activities have largely been delayed until FY03.

these processes easier to retrieve

ODFW
1
Provide an index of Oregon Fish Commission, Oregon Game 
ODFW's Library was closed during this quarter due to budget constraints.  Our

Commission, and Oregon Wildlife Commission processed 
goal is to reopen the Library between October 2002 and January 2003.

reports to the StreamNet Library for the purpose of identifying

documents that are not currently within library holdings.
ODFW
2
Coordinate with the Oregon State Library system to enhance 
ODFW's Library was closed during this quarter due to budget constraints.  

access to published periodicals, journals, and other documents 
Our goal is to reopen the Library between October 2002 and January 2003.

for StreamNet users.


Objective
4
Task:
4
StreamNet Fourth Quarter Performance Report, FY 2002
Page 42 of 56
Objective
5
Services to Fish and Wildlife Program Activities

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife

Program projects

Objective
5
Services to Fish and Wildlife Program Activities
Task
1
Data and services to support the Subbasin Planning effort

Within existing data categories and staffing levels and as workloads permit, assist Subbasin Planning efforts by 1) providing data in formats

that fit planner needs, 2) working with planners to locate data within the StreamNet database and contributing projects' databases, and

3) advising and assisting planners on data management issues.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Provide described services to CRITFC staff working on 
Subbasin planning activities in most areas have been delayed until FY03.

subbasin planning and NMFS' TRT groups

MFWP
1
Work with Montana's CBFWA representative involved with 
There were no requests for data received during the quarter.

subbasin planning and provide data, map products and 

assistance as needed.

ODFW
1
Participate in Subbasin Planning meetings and provide data, 
1.  The Project Leader participated via conference call in the Oregon 

advice, and related assistance to subbasin planning efforts in 
Subbasin Planning Coordination meeting.

Oregon (within existing resources and as workloads permit)
2.  The Project Leader participated in the TOAST (Technical Outreach 

Assessment Support Team) Oversight Group meeting on Sept. 20th, where we

discussed TOAST's role in filling data needs for Subbasin Planners, the data-related

services subbasin Planners can expect from TOAST, and the upcoming TOAST

Gorge Workshop focus/agenda which is scheduled for Oct. 7 & 8.


3.  The Project Leader was asked by Ron Boyce (ODFW CBFWA Rep.) to 

review five of the six Systemwide data management projects during the CBFWA

Mainstem and Systemwide Project Review process.  The sixth project is

StreamNet, so for obvious reasons, he didn’t get to review StreamNet.  A

great deal of time was spent on this effort, as most of the proposals required

more than 50 pages to be reviewed.  Other Steering Committee members were

asked to aid in this effort, and comments received were incorporated into the 

reviews where appropriate.  The final reviews and comments were shared with

the other Steering Committee members.


4.  The Project Leader attended the initial session of the CBFWA Project 

Review meeting to get a sense of what the review process is like and what 

needed to be prepared to adequately participate in the process.  Later in the

week, he  attended the Data Management Project review session and provided

input on the 5 of the 6 data management projects on behalf of ODFW.


Objective
5
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 43 of 56
Region
1
Generate customized maps and information for subbasin planners
The GIS specialist created a series of subbasin maps for use by CRITFC.

from StreamNet data or other data provided by the planners, as

long as this work can be accomplished within existing resources.

WDFW
1
Participate in Subbasin planning meetings and provide data and
WDFW have pegged specific staff as Species Specialists to better respond 

advice as needed.
to data requests and special data initiatives like Subbasin Planning.  Region 

5 WDFW StreamNet staff met with Sara LaBorde of the Salmon Recovery

Board and the WDFW salmon specialists.  A request for detailed return 

information on the Lower Columbia River tributaries was presented to the 

group.  Following the meeting, our WDFW StreamNet staff manipulated 

their natural spawn escapement and age data per request.  Final approval to

release this data to the contractor (Cramer and Associates) will come from

WDFW officials in October 2002.

Objective
5
Services to Fish and Wildlife Program Activities
Task
2
Support monitoring and evaluation efforts

Assist in the development of products that contribute to the monitoring and evaluating (M&E) of Fish and Wildlife Program effectiveness.

Specific areas of involvement will include:  participation in Program-related monitoring and evaluation work groups; periodic re-evaluation

of the StreamNet data plan to ensure consistency with M&E needs; and design of databases and formats to house and disseminate M&E

information to the degree possible under the existing contract.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Work with NMFS, NWPPC and subbasin planning groups to 
The project leader has assisted other resource management agencies to 

identify M&E needs and plans
develop an M&E project proposal for the Columbia Basin and has 

participated in several interagency meetings concerning this issue.  

Subbasin planning activities in most areas have been delayed until FY03.

Objective
5
Services to Fish and Wildlife Program Activities
Task
3
Support for and participation in regional data management initiatives

Work with regional entities to promote and implement sound data management programs that ensure efficient organization,

management and delivery of pertinent fish and wildlife related information within the Columbia Basin.  Efforts may include

determination of regional data needs, identification of obstacles and challenges to effective regional data management, and 

development of recommendations and will take place in a collaborative atmosphere.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Participate on Regional Data Management Committee and 
The project leader is a member of the NWPPC/NMFS Columbia Basin 

other groups to improve data management in the region
Collaborative Information System project team, the data inventory 

project being conducted by SAIC. Work this quarter focused on completing

the user survey and preliminary analysis of partial results.


Objective
5
Task:
3
StreamNet Fourth Quarter Performance Report, FY 2002
Page 44 of 56
ODFW
1
Participate in discussions and offer solutions related to 
1.  Staff participated in the Columbia Basin Cooperative Information System focus

Columbia River Basin database management and information 
group meeting held at PSMFC in Gladstone. The meeting was facilitated by SAIC.

distribution issues, as needed.
2.  Staff held a brief conference call to clear up some issues related to the SAIC

Columbia Basin Coordinated Information System Data Inventory and Needs

Assessment process that we participated in some time ago.  The feedback we 

submitted was totally mixed in with feedback from others and was credited to

others.  In addition, the format SAIC provided (PDF) could not be modified.  We

provided a response to SAIC requesting an editable copy.

Region
1
Participate with regional entities in the development of 
1.  StreamNet continued its participation in the regional data needs and data 

effective regional data management programs and approaches.
inventory project (CBCIS).  The Program Manager participated as a member of the

Provide input based on years of StreamNet experience with 
Project Team for the project, and also set up a focus group meeting with StreamNet

management of data sets on a regional basis, along with 
and the other data management projects under PSMFC.  Input on the data held

insights into challenges, obstacles and costs.  Support effective
in StreamNet was provided to SAIC.

regional data management and delivery at reasonable cost 
2.  Regional staff reviewed a California Fish and Game proposal for managing

with avoidance of duplication of effort.  Support and 
migration barrier data.  Our review helped to improve their (and ultimately our)

encourage regional data needs assessments.
system, and also allowed for better coordination between the two efforts.

Objective
5
Services to Fish and Wildlife Program Activities
Task
4
Archive function for regional data sets, as requested

Work with regional entities to aid in the capture and distribution of data generated through Fish and Wildlife Program 

activities and to help determine the most appropriate means of storing and disseminating them.  Where data do not fit in 

existing StreamNet data sets, develop archive functions to at a minimum make data available 'as is', regardless of their 

current form.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






MFWP
1
Be available to Montana entities as a source of information 
There were no requests received during the quarter.

and assistance for capturing F&WP-related data, as needed.

Objective
5
Services to Fish and Wildlife Program Activities
Task
5
Data and services as requested by other FWP participants

In consultation with CBFWA, the Council, and BPA, StreamNet will provide technical assistance and data services to Program projects

as requested, to the degree possible under the current contract.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Assist in providing services as requested and as time and 
The role of StreamNet in managing data and literature developed during subbasin

budgets allow
planning was discussed with regional and Oregon planners and coordinators.  A

preliminary budget was developed for, in part, data management services for

Oregon subbasin planners.


Objective
5
Task:
5
StreamNet Fourth Quarter Performance Report, FY 2002
Page 45 of 56
 IDFG
1
Provide technical assistance to fisheries projects in IDFG. 
1.  The project manager for the Salmon region Steelhead project contacted

Under current funding from both the F&WP program and 
us to discuss coordination.  He is requesting support with data management

IDFG, we are very limited in our ability to provide this 
and analysis similar to what we provide to Idaho Supplementation Studies. 

assistance. Assistance will generally be focused where there is 
Such support would expand our ability to provide steelhead data to 

some mutual benefit to both StreamNet and the other project.
StreamNet.  Specifically, we will provide technical assistance for data 

requirements for Steelhead Creel Survey and review of the Coded Wire Tag

data formats to extract steelhead release, capture and return summaries.

2.  We met with the new project manager for Idaho Supplementation 

Studies and the IDFG Nampa Fish Research Office to coordinate our 

activities and to discuss technical support.

3.  We provided assistance to fish research staff to troubleshoot genetic 

sampling data that didn't appear in the correct location on GIS.

4.  We updated the maps in the IDFG fishing regulations for two IDFG 

regions.

5.  The Idaho Conservation Data Center asked for our assistance in sorting

out a problem where one of their clients apparently had a different set of 

fifth field watersheds than we use.

MFWP
1
Data services will be provided by Montana StreamNet staff on 
The project leader gave a PowerPoint presentation at the August NWPPC 

request.
meeting on the StreamNet program in Montana.  The program was well 

received and generated questions and discussion.

ODFW
1
In consultation with CBFWA, the Council, and BPA, Oregon 
1.  The Project Leader received an email request for help with fixing 

StreamNet staff will provide technical assistance and data 
problems in the Wildlife Habitat Conservation and Management program 

services to Program projects as requested, to the degree 
database.  Fortunately, the requestor is flexible on time and has money to 

possible under the current contract.
pay for the service.  Specific details of the problem were requested so we 

could better evaluate our ability to help.

2.  The GIS Analyst met with the Clackamas STEP biologist to discuss 

available GIS data and the potential for building GIS capacity at the 

Clackamas office.

Region
1
Respond to requests to the StreamNet project from F&WP 
1.  StreamNet staff met with Council staff and contractor in response to 

participants for data, maps, or GIS products or general 
their request for data to support the Artificial Production Review and 

assistance.  Provide assistance, including custom map work 
Evaluation effort.  Data availability was demonstrated, and advice was 

where feasible.  Direct users to other resources if requests 
provided on how to obtain the needed information.  A link to related data 

exceed project capabilities.
from the Fish Passage Center was added to the StreamNet website to assist 

in the effort.

2.  At the request of CBFWA members, StreamNet staff from all agencies 

assisted with review of project proposals for the CBFWA project review 

process.


Objective
5
Task:
5
StreamNet Fourth Quarter Performance Report, FY 2002
Page 46 of 56
Objective
5
Services to Fish and Wildlife Program Activities
Task
6
Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas data set, b) archive the official version as a 

historic record, and c) in consultation with the Council, respond to requests for information concerning Protected Areas
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






Region
1
Maintain the Protected Areas database within the StreamNet
The Protected Areas database and the new interactive Internet mapper for these data

database
were maintained throughout the quarter.
Objective
6
Project Management / Coordination

Provide effective leadership that ensures the production of high quality products targeted at critical applications

and the development of these products in a timely, cost-effective manner.

Objective
6
Project Management / Coordination
Task
1
Manage project activities

Administer all aspects of the project at the regional and sub-contractor levels, including oversight of budget, personnel, work statement

preparation and implementation, coordination among participating agencies, active participation in steering committee work, and

project reporting.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Attend and participate in Steering Committee meetings
The CRITFC StreamNet Project Leader participated in all steering 

committee discussions and meetings.

CRITFC
2
Effectively administer the CRITFC StreamNet project
Normal project and personnel management was provided.  Work was very 

routine this quarter.

FWS
1
Represent FWS in Steering Committee meetings.  Produce 
Pastor participated in the August Steering Committee meeting and 

quarterly reports w/in 30 days of quarter end.  Produce FWS 
produced the Q3 Accomplishment Report.

component of FY2001 final report.  Create FWS StreamNet 

budget & statement of work for FY2003.  Contribute FWS 

portion of Project Renewal documents.

IDFG
1
Prepare budgets, work statements, and progress reports
1.  We completed and delivered the FY2002 third quarter report.

2.  We developed an expanded budget proposal in response to the ISRP review

of StreamNet.

3.  We helped develop the response to the ISRP review of the StreamNet proposal.

4.  We developed and submitted the FY03 Statement of Work and budget.

Objective
6
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 47 of 56
IDFG
2
Provide project management and staff supervision for IDFG 
1.  The IDFG/StreamNet project manager completed annual performance 

StreamNet.
evaluations for several staff.

2.  The IDFG/StreamNet project manager compiled comments from 

Steering Committee members about the StreamNet Project Manager's 

annual performance evaluation.  The information was compiled into a 

report to the project manager's supervisor at PSMFC for use in 

preparation of his evaluation.

3.  In order to provide faster development of quarterly reports, we 

instituted a new weekly work diary process.  While somewhat informal, it 

provides immediate access to staff progress reports at the end of each 

quarter.

4.  We currently have two empty FTE positions.  After developing a way 

to fund these, the project leader started the paper work to fill them.  This 

will give us an additional programmer analyst and GIS analyst that, while 

not on StreamNet funds, will contribute to StreamNet through 

coordination of work.

IDFG
3
Participate in Steering Committee activities, including 
The IDFG/StreamNet project coordinator participated in this quarter's 

Steering Committee meetings, project direction, and data 
steering committee meeting.

exchange format development.

IDFG
4
Participate in and provide for IDFG StreamNet staff 
1.  The IDFG/StreamNet programmer analyst attended a 3-day "XML 

appropriate professional and technical development.  This 
Applications with SQL Server 2000" class.

includes technical training and participation in professional 
2.  He also attended a free2-day Microsoft seminar for .Net developers.

organizations and conferences.
3.  Our entire staff attended a 3-day Project Management class.  The class 

spent half the time on theory and the other half on using Microsoft 

Project.  While not everyone on our staff will utilize the software, it was 

valuable to have them learn the theory and how the software works so that

they can meaningfully contribute to planning and managing our 

StreamNet work.

4.  The IDFG/StreamNet project coordinator attended the Northwest ESRI

Users Conference.  As this year's president the project coordinator ran the

annual board meeting and the general business meeting.

MFWP
1
Provide normal supervision of Montana StreamNet staff and 
1.  The partial position left by Steve Carson when his position was put on 

project. Produce quarterly reports within 1 month after the 
1/2 time wildlife funding will be filled via a contract for next fiscal year due

end of each quarter.
to job freezing in Montana.  

Produce final report within 2 months of the end of the 
2.  The project leader provided a Montana Statement of Work and budget 

contract period.  Participate in Steering Committee meetings. 
to StreamNet regional staff in September.

Collaborate on developing a final detailed Statement of Work 

for FY02.


Objective
6
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 48 of 56
ODFW
1
Administer all aspects of the project for Oregon, including 
1. Meetings:  Oregon’s Project Leader attended the Aug. 6-7 StreamNet 

budget oversight, personnel, work statement preparation, staff
Steering Committee meeting in Gladstone.

work plan preparation, project implementation and 
2.  Reports and SOW:  Oregon staff completed and submitted Oregon's 2002

coordination, reporting, and participation with the Steering 
2nd and 3rd Quarterly Reports.  The Project Leader reviewed the final drafts

Committee and technical issue working groups.
of StreamNet's Q-2 and 3 reports, and provided comments to PSMFC.

3. Provincial Review Process Activities:  The Project Leader attended 

StreamNet's Provincial Review Proposal presentation to the ISRP in 

Portland, where Bruce Schmidt (PSMFC) gave the presentation.  The 

Project Leader read the ISRP review of StreamNet's 3-year proposal and 

communicated with Ron Boyce (through an attempt to communicate with 

Tony Nigro) seeking direction and input from ODFW.  He reviewed and 

provided input on StreamNet's response to the RM&E panel's comments 

on StreamNet’s Systemwide Provincial Review proposal.  He spent a good 

amount of time developing Oregon's portion of the ISRP response from 

StreamNet, including a description of Oregon's QA/QC procedures for redd 

count data, and a task by task breakout of our budget request for FY-2003. 

He also reviewed and commented on StreamNet’s response to specific 

ISRP questions, which was primarily written by Bruce Schmidt.

Region
1
Project Administration:  Perform ongoing administration of 
1.  The regional GIS data manager position became vacant during the 

the StreamNet project, to include budget development and 
quarter.  A replacement was recruited, applicants were screened and 

tracking, contract monitoring, personnel functions, inventory
interviewed, and a new person was hired for the position.  Sufficient 

control, etc.
overlap between the old and new GIS data managers was possible so that 

significant training of the new person occurred.

2.  Significant time was spent in the project renewal process.  The project 

proposal was presented to and reviewed by the ISRP.  Review comments 

from the ISRP and the RM&E Workgroup were prepared and submitted.  

The project proposal was presented to and reviewed by CBFWA.  

3.  Discussions were held with the BPA COTR on the need for bridge 

funding, since the project year ends well before the current review process 

is expected to have funding recommendations completed.  A level budget 

(no increase from FY 2002 despite actually realized and known future salary 


cost increases) was prepared along with a base level Statement of Work and 

submitted to BPA.

4.  Performance appraisals were conducted for all regional staff members. 
Region
2
Reporting:  Submit quarterly progress reports to BPA within 
The Quarter 2 and Quarter 3 progress reports were completed and 

one month of the end of each quarter and submit an annual 
submitted to BPA.  These report submittals permitted the project to catch 

report within two months of the end of the fiscal year.
up with all reporting requirements.


Objective
6
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 49 of 56

Region
3
Maintain effective relationship with the StreamNet Steering 

The summer steering committee meeting was hosted by PSMFC on August 6and 7.

Committee.  Organize and conduct quarterly Steering 


Committee meetings to facilitate project oversight and setting

direction/goals.  Coordinate regional project activities with 

Steering Committee involvement and direction.

WDFW
1
The WDFW StreamNet state coordinator will participate in 
1.  WDFW staff finalized work proposals, budgets, and FTE information for 

all Steering Committee and StreamNet Project management 
FY2003for both "bridge period" funding and the Final FY2003 (base) version.

activities, including meetings and follow-up work assignments 
In addition, staff generated out-year budget estimates for FY2004 and FY2005,

(progress reports, Statements of Work, budgets).
as well as supplemental budget and work proposals for two FTEs worth of "new 
work", in coordination with other StreamNet participants.

2.  The WDFW FY2002 Third Quarter report was finalized and submitted, along

with Selected Highlights and Related Work contributions.

3.  The Project Manager attended the August 6-7, 2002 Steering Committee meeting

and gave progress reports on data submissions (written by the Data Manager), data

development work, exchange formats work, and other related initiatives. At this 

meeting, the Steering Committee reviewed current work and issues placed on the

agenda, then spent most of our time discussing the ISRP and RM&E Workgroup

comments to the StreamNet 3-year proposal and generating responses.

4.  We helped organize and attended an information gathering session in Olympia

sponsored by SAIC for the Columbia Basin Cooperative Information System

project. Staff provided written input during and after the session.

5.  WDFW staff also prepared documentation of current QA/QC procedures for

StreamNet data compilation.  This document covers only generic procedures and

we began collecting more documentation for specific procedures.  Project Manager

O'Connor agreed to serve on a Team (including Phil Roger, Bill Kinney, and Greg 

Wilke)charged with generating an overall framework and subsequent details of a

formal StreamNet QA/QC Process.  The Team did not meet its deadline of

September 30 to circulate initial thoughts; this will be discussed further in October.


6.  WDFW provided updates to the Regional Data Manager's list of Agency Data

Contacts and provided feedback to CRITFC StreamNet Representative (Phil Roger)

on the CRITFC Genetics Data Exchange proposal.

7.  The WDFW StreamNet Project Manager provided input and review of the 

annual evaluation for the StreamNet Regional Project Manager.

WDFW
2
The state coordinator and the state data manager will jointly 
1.  All supervisors and staff completed annual performance evaluations.

manage all aspects of StreamNet in WDFW, including budget, 
2.  Supervisors re-wrote Michelle Smith’s (the Region 5 WDFW 

personnel, work scheduling, and product delivery.
StreamNet Compiler) job description and submitted appropriate paperwork

to upgrade her position to a Fish & Wildlife Biologist 2 position per the 

responsibilities of her past and future work.


Objective
6
Task:
1
StreamNet Fourth Quarter Performance Report, FY 2002
Page 50 of 56
Objective
6
Project Management / Coordination
Task
2
Participate in Fish and Wildlife Program development activities

Work with regional entities to assist in the area of data management as requested to support development of Fish and Wildlife Program

projects and programs.  Organize, facilitate, and/or participate in appropriate coordination meetings with BPA, CBFWA, the Council,

ESA officials, ISAB/ISRP, and/or staff and management of participating organizations to identify ways StreamNet can effectively

contribute to the Fish and Wildlife Program (FWP) and facilitate  capture and dissemination of data.  Participate in advisory groups, task

forces, and other groups whose purpose is enhancing the effectiveness of the Fish and Wildlife Program and its data development activities.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






MFWP
1
Provide services as requested
The project leader helped review all the data management projects prior to the

CBFWA review; duties were split among the 4 state coordinators to ease workload.

Region
1
Work with regional entities to contribute data management 
The regional fisheries biologist participated in a field trip to observe the 

expertise with development of activities within the scope of 
stream and riparian habitat monitoring methods used under the Northwest 

the Fish and Wildlife Program.
Forest Plan.  Specifics of the sampling design were discussed relative to 

other monitoring efforts.

Objective
6
Project Management / Coordination
Task
3
Coordinate with other related activities

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities beyond the Council's

Fish and Wildlife Program to identify means for collaborative data collection, storage, and dissemination.  Collaborative data activities

will include tribal fishery programs within the Columbia Basin, federal land managers’ fishery programs, state fish and wildlife agencies,

and, with respect to water use and stream development, state water resource management and environmental quality agencies.  Collaboration

with coast-wide and private data collection/compilation efforts will be pursued when this supports overall project goals.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Work with NMFS and non F&WP agency staffs to improve 
1.  The Project Leader is a member of the NWPPC/NMFS CBCIS project 

and provide data management services to the region
team to assess Columbia Basin information needs and options.  The fourth 

quarter effort was spent developing an information needs survey.

2.  The Project Leader worked regularly with tribal, state, and federal staffs

to coordinate recovery planning and subbasin planning efforts.

IDFG
1
Coordinate and collaborate with other organizations, including
1.  The IDFG Wildlife Bureau contacted us for technical assistance related 

federal, tribal, state, and local governments and private 
to database design for their Female Mountain Lion Quota program.  This is

organizations. Such coordination and collaboration will be 
a potentially important link for us to make, given the range of 

selected and conducted in such a manner as to provide benefit 
information that may be needed in upcoming subbasin assessments and 

to IDFG and StreamNet database systems or to distribute 
plans.

StreamNet data.


Objective
6
Task:
3
StreamNet Fourth Quarter Performance Report, FY 2002
Page 51 of 56
MFWP
1
Maintain communication between state and regional entities
The fisheries data manager has helped organize and participated in the 

Westslope Assessment process in Montana.  StreamNet staff will provide 

technical staffing at the meetings that will occur in Great Falls, Bozeman, 

Missoula and Kalispell.  The MFISH data structure and data have been used 

for all the assessment and mapping.  All data collected from the 

assessments will be put into MFISH.

ODFW
1
Establish / maintain working relationships with data collection
1.  The Project Leader attended a meeting at OSU to assess the status, 

projects within and outside ODFW to promote efficient and 
location, and condition of the historic habitat survey archive and it's 

beneficial data sharing.
possible transfer to the OSU Digital Library.  These habitat surveys 

contain a great deal of historic fish sightings, and may be very useful for 

developing or updating future historic habitat distribution data.

2.  Staff met with Janine Salwasser and Doug Terra from OWEB to get a 

better understanding of what they are trying to accomplish and to see 

where ODFW and StreamNet fit in.

3.  The Project Leader spoke with Bobbi Riggers (OWEB) about the 

restoration data delivery system developed by NOAA-Fisheries.  Bobbi 

currently doesn't have access to it, but describes it as the best 

representation of their data she's seen so far.  This system is maintained 

on NOAA-Fisheries internal system, so no one can access it without 

permission.  When I contacted NOAA Fisheries to get a look, I was told 

they are still trying to give OWEB access and they'll work with me once 

they've solved the issues with OWEB.

4.  The Project Leader attended the Hydro Framework Meeting in 

Portland and updated everyone on the status of our 24K Fish Distribution 

Project.  He also learned that the 24K Hydro development is behind 

schedule and they intend to ask OWEB for an extension (without addition 

money).  The BLM-State effort is running smoothly, but BLM and the 

Forest Service are still not in agreement on who should do what areas or 

how it should be done.

5.  The Project Leader met with Jeff Dambacher, ODFW Fish Research, to

officially transfer the Oregon fish museum collections data set to NRIMP. 

The data set is complete with metadata, is in .e00 format, and may be useful

for developing a historic distribution layer for some species.  Jeff would like

us to find a way to publicize the data set and make it more widely available.


6.  The Project Leader contacted Peter Lofy (BPA) regarding carcass 

placement projects for which he is the COTR.  Peter’s projects are located

in Idaho, Washington, and Oregon, and all projects deal with much more 

than just carcass placement efforts.  He agreed to provide the names of the

project leaders, and we agreed to coordinate with StreamNet counterparts 

in the other states to address as many of these projects’ data needs as possible.


Objective
6
Task:
3
StreamNet Fourth Quarter Performance Report, FY 2002
Page 52 of 56
Region
1
In order to broaden the scope and utility of the StreamNet 
1.  A presentation on StreamNet and it's data contents and data services 

database, develop appropriate proposals for data development 
was given to BPA staff with the intent to improve communication and 

activities that would compliment the main StreamNet data 
coordination.

holdings.  Ensure proposed work is not currently conducted by 
2.  The program manager and regional fisheries biologist met with 

other entities.  (Examples may include traditional StreamNet 
personnel from the Oregon Watershed Enhancement Board to discuss 

data types outside of the Columbia River basin, 
possible overlap among the two projects, and how to best support each 

macroinvertebrates, water temperature, and habitat restoration.)
other.

Conduct of such work will be dependent on availability of

additional resources.  Once awarded, efforts will conform to the

approved contract.  Such work will be coordinated with this 

work plan so that activities under this task do not impede

accomplishment of the remainder of the work plan.  This task 

is necessitated by the fact that project staff have time available 

that is not covered by the BPA contract.
Objective
6
Project Management / Coordination
Task
4
Prepare and present public information related to the StreamNet Project.

As needed, produce public information materials and participate in various meetings and forums to explain the project's 

capabilities and purpose and to generate support and additional data sources.  Activities may include brochures, 

demonstrations, posters and talks.
Project
Job
Planned work elements

Accomplishments, Fourth Quarter 2002






CRITFC
1
Prepare and present demonstrations and descriptions of the 
We gave a presentation on electronic document projects at the Natural 

library services available through StreamNet
Resource Information Council.

MFWP
1
Determine if Montana needs any publications, documents and 
An information sheet was provided during the presentation at the NWPPC

produce them if needed.  Review regional products when 
August meeting in Helena prior to the presentation done by the Montana 

necessary.
StreamNet project leader.

ODFW
1
Produce public informational documents on StreamNet data 
The Database Analyst worked on collecting information to re-work the 

activities for natural resource oriented publications, give oral 
Incidental Fish Observation write-up for publication in Inside Tracks 

presentations to relevant user groups, and participate in 
magazine.  She requested and received reviews from NRIMP staff and 

various meetings and forums.
incorporated the changes into a final draft along with a copy of the 

ArcView map she updated with the number of forms submitted by HUC.


Objective
6
Task:
4
StreamNet Fourth Quarter Performance Report, FY 2002
Page 53 of 56
Region
2
Develop materials to support the project.  Improve public 
1.  After correcting the software error that had prevented delivery last 

materials such as the StreamNet brochure, data inventories, 
quarter, on July 10 the first StreamNet Newsletter was sent via email to 

etc. as needed.  Maintain and update explanatory materials 
the 7034 unique email addresses we had collected.  It was anticipated that 

such as the Query System User Guide and documents that 
many of these would be old addresses or addresses that were parsed 

explain data categories and structures.
incorrectly from web pages.  As per our expectation, 2994 messages failed 

and were returned, meaning 4040 messages were received by the target 

audience.  In addition to these direct mailings, we sent the newsletter to 

the following email discussion groups (listserves):  Fish and Wildlife 

Information Managers; American Fisheries Society; and Watch Over 

Washington.  We also had prearranged for two recipients of the newsletter

to forward it to the Oregon Watershed Enhancement Board's email 

discussion group, and the Northwest Biomonitoring Workgroup's email 

discussion group.  In addition, the Newsletter, along with the URL to sign 

up for future newsletters, was submitted and published in the Western 

Division of the American Fisheries Society's newsletter, "The Tributary."  

One week after sending the newsletter via email, 646 people (16% of 

recipients) were signed up to receive future newsletters.  Their affiliations 

were as follows:  angler or environmental group=29; BPA=10; Canada=8; 

CBFWA=2; consultants=33; EPA=8; federal land manager=26; 

industry=11; local government=32; NMFS=44; NRCS=4; NWPPC=8; 

PSMFC=14; PUD=7; state fish and wildlife agency=95; other state 

government=63; state legislature/governor's offices=4; tribal=43; 

university=30; US House or Representatives=4; USACOE/BOR=26; 

USFWS=31; USGS=17; watershed councils=16; other=18; unknown=63.  

We plan to send a StreamNet newsletter about 3 times per year, as new 

information is available on the web site.  People continued to sign up 

through the quarter, and at the end of the quarter there were 854 people 

signed up for the newsletter.

2.  The first draft of the white paper completed last quarter describing the 

data available in the Habitat Restoration Projects portion of the 

StreamNet database was updated based on edits received and then presented

to the SC for further review before acceptance.


Objective
6
Task:
4
StreamNet Fourth Quarter Performance Report, FY 2002
Page 54 of 56
Supplemental Information
Work accomplished outside the specific work elements in the FY 2002 Statement of Work

This section describes specific accomplishments during the fourth quarter that did not relate specifically to any of the Tasks / Work Elements 
in the annual Statement of Work.  Such work contributes to the overall mission of the StreamNet Project, but in some cases was opportunistic in nature, and in other cases was conducted by staff related to StreamNet but on other funding sources, made possible by the fact that a number of StreamNet staff are supported by the StreamNet Project contract for only a portion of the year.
Project

Accomplishments, Fourth Quarter 2002











CRITFC

The Project Leader, as chair of the technical team for the Council's subbasin planning efforts in Oregon, had numerous discussions and meetings scoping and developing watershed assessment methods and defining other technical tasks required to complete subbasin plans.  These activities, as well as participation in the Council's CBCIS project and discussions concerning M&E needs and initiatives, are done at no expense to the StreamNet project but can significantly affect support for StreamNet and affect future needs and activities.

IDFG

Using non-StreamNet funds, we continued our work to attach the Idaho fishing regulations to the StreamNet hydrography.  We now have about 95% of the lakes and 50% of the streams completed.

MFWP

The MFISH query system continues to receive about 4,000 visitors each month; further enhancements have been made and the new system has been well received.  The FWP GIS data is now downloadable from the agency's website at fwp.state.mt.us; the system is entirely database driven so anytime data are updated or a new layer is available, it is automatically loaded to the downloadable system; in the first month the data were available, the page had 1400 visitors.  Work continues smoothly on the agency's IT plan; final comments have been provided to the state IT Division; next steps include putting together focus groups for the first 3 goals to deal with staff infrastructure and data standards and centralization.  The new MWILD (Montana Wildlife Inventory Database) is off to a good start; coordinating with the Montana Natural Heritage Program closely; will be able to hire 2 data entry technicians in December through the agency's SWG Comprehensive Planning Process so all existing occurrence and habitat survey data can be entered into the system.  We are also developing individual DMS for bald eagle.  We are also creating a field guide for all species in Montana that will be part of the FWP website.  We are currently updating FWP black bear, bighorn sheep and mountain goat GIS layers.   Using ArcIMS for providing upland game bird data on the web and will convert our Hunt Planner over to ArcIMS this fall.

ODFW

1.  
The 24K GIS Coordinator participated in a series of interviews to find a new GIS specialist for the StreamNet project.

2. Our GIS Analyst implemented FTP security tightening measures.   Under the new structure, anonymous users will only be allowed to write to a single /pub/Incoming directory and will not be able to see the files there.  Primary users will have password protected access which enables them to upload data to their directories, plus download data from the Incoming directory, which will facilitate transfer of files to staff from outside agency staff of the public..

3. Oregon’s Project Leader talked with Rich Carmichael (ODFW Research, LaGrande) about expanding our VSP effort to support the Upper Columbia TRT efforts.  Rich is seeking 6 months of funding from NMFS and will request 6 additional months from the NWPPC.  He's focused primarily on Steelhead distribution (which we have), age, length, and other life history information.  Once we know more about how much money we have, we'll talk more about how best to administer the project.

Supplemental Information
StreamNet Fourth Quarter Performance Report, FY 2002
Page 55 of 56
4. The GIS Analyst responded to a disk failure on Eagle, our ArcInfo license server.  He performed troubleshooting to identify the problem disk and proceeded to physically disconnect it from the SCSI chain.  The file systems on the disk included Milt's old directory, a Unix answer book and our ArcInfo install including the license server functions.  ArcInfo was reinstalled and the license server functions were re-established on a different file system and disk.  He also modified various system tables to handle the new configuration. Fortunately nothing was lost except for nearly a day of time.

5. Oregon’s Database Analyst removed and stored Juvenile data records from the Oregon Trend data set until a DEF is provided by StreamNet

6. The Assistant Database Developer communicated with ODFW staff to spread the word about Map features on our web site.  ODFW office receives numerous requests for maps from local hunters, and the Map Links page will provide the office staff with an online resource to direct the hunters to.
Region

During the quarter, a number of materials from StreamNet and it's two predecessor projects, CIS and NED, were found in filing cabinets.  These items were examined for current utility or historical significance.  Items of interest were provided to the StreamNet Library for archival.  Others, such as old versions of the DEF, were converted into .pdf format by the Library staff and will be added to the StreamNet web site as historical documentation of the evolution and development of the StreamNet database structure.
WDFW

1. 
WDFW staff played a key role in six meetings of the state's Data Development Group, which is advising state agencies on the data standards and procedures for planning, collecting, and managing Monitoring data in support of salmon and watershed recovery.

2. The WDFW StreamNet Project Manager worked with JSAP project participants and a consultant to review data system designs and schemas for the "Universal Fish and Habitat Database", intended to store data collected in support of resident fish stock assessments in Northeast Washington (above Grand Coulee Dam). This data store will be designed to support extraction and conversion of data for exchange with StreamNet as required.
3. WDFW staff began the year-long process of incorporating fish distribution data from StreamNet, Limiting Factors Analysis, Bull Trout 2000 statewide review, and the SaSI stock status data set into a single statewide spatially enabled fish database that is linked to WDFW's 24K routed hydro layer. Standard definitions for presence and use categories were negotiated, and these definitions factored into StreamNet discussions that resulted in adoption of the StreamNet GeneralizedFishDistribution format. This new database will allow much simpler exchange of data with StreamNet, once issues surrounding the differences between the 24K and the 100K hydro layers have been dealt with.

Supplemental Information
StreamNet Fourth Quarter Performance Report, FY 2002
Page 56 of 56
�EMBED Word.Document.8 \s���








_1098250779.doc
[image: image1.png]






_1098250777.doc
[image: image1.png]






