	[image: image2.wmf]  
[image: image1.wmf]
	StreamNet Project
BPA Project No. 198810804

Fiscal Year 2004
Fourth Quarter Progress Report
July 1, 2004 through September 30, 2004


Bruce Schmidt
Pacific States Marine Fisheries Commission

Cooperators
Phil Roger, Columbia River Intertribal Fish Commission
Bart Butterfield, Idaho Department of Fish and Game

Janet Hess-Herbert, Montana Fish Wildlife and Parks

Cedric Cooney, Oregon Department of Fish and Wildlife

Steve Pastor, U. S. Fish and Wildlife Service

Dick O'Connor, Washington Department of Fish and Wildlife

November, 2004


                                            Table of Contents                                             Pg.

Introduction………………………………………………………………
 2


Objective 1.  Data Acquisition and Development………………..…….
 8

Objective 2.  Data Management and Delivery…………………………

22

Objective 3.  Library / Reference Services…………………………….

38

Objective 4.  Services to Fish and Wildlife Program Activities………

41

Objective 5.  Project Management and Coordination…………….…..

46

Supplemental Information: Work accomplished outside the S.O.W...

55
Introduction
StreamNet is a cooperative, multi-agency data compilation and data management project authorized by the Northwest Power Planning Council’s Fish and Wildlife Program (FWP), funded primarily by the Bonneville Power Administration.  The project is administered by the Pacific States Marine Fisheries Commission.  Three fourths of the project consists of sub-projects within the state fish and wildlife agencies, Columbia River Intertribal Fish Commission and the US Fish and Wildlife Service to develop databases within the respective agencies and to facilitate data transfer regionally. The remaining fourth consists of the regional staff and the database at PSMFC.
The StreamNet Project compiles, manages, standardizes and distributes information related to fish resources in the Columbia River basin, with additional information available for the rest of the Pacific Northwest.  The state, tribal and federal fish and wildlife agencies collect and utilize data related to the region’s fish and wildlife resources to meet their own mandates.  A subset of these data, primarily the annually collected types of information that are routinely used to monitor trends within fisheries and populations and provide management information, are compiled by StreamNet into regionally standardized formats and publicly distributed.  In this manner, data common to fisheries management but collected and stored in multiple formats by the individual agencies are standardized and made uniformly available basin wide, primarily through the StreamNet website (www.streamnet.org).  StreamNet also ties all data to the regional 1:100,000 scale routed hydrography (GIS stream network) so that different kinds of data can be compared on a geographic basis and mapped.  The project utilizes the Internet as its primary means of data distribution, but also provides custom data services to FWP participants.  The StreamNet web site provides access to information in a queriable database and also provides maps, individual data sets not contained in the queriable database, and library references.  All data in the StreamNet database are referenced to source documents that are housed in the StreamNet Library.  Work reported herein is tied to the specific jobs contained in the FY-04 Statement of Work, available at http://www.streamnet.org/about-sn/project_management.html.
Introduction


StreamNet Fourth Quarter Performance Report, Fiscal Year 2004
Page 2 of 56
This report documents accomplishments made by the project and its cooperators during the fourth quarter of Fiscal Year 2004 (FY-04).  Since the cooperating agencies work on different jobs throughout the year, and not all agencies address the same jobs in their respective portions of the Work Statement, the work accomplished in this quarter varies by cooperator.  Tasks and jobs that did not have any work addressed during the quarter are not included in this report.

Work priorities for FY-04 include updating existing long term data sets, managing the data and infrastructure necessary to maintain and deliver data, maintaining the StreamNet Library, providing data services to regional entities associated with the Fish and Wildlife Program, and project administration.  Activities in the Fourth Quarter of FY-04 included routine development, maintenance and posting of various data sets, as well as routine administrative activities to continue project function.  Key highlights of activities in addition to routine project functions this quarter are presented by cooperator below, with details provided in the body of this report.

Regional StreamNet at PSMFC (Region)
During the fourth quarter we published an updated version of the downloadable StreamNet database, ASCII files of StreamNet tables, Data Dictionary definitions and Data Categories Help pages.  The downloadable database makes all of the StreamNet data available to users in one convenient format, but because the update is only done about twice a year, the most current data are still available only through the online query system or by direct request.  Other data work included the receipt, processing and validation of major databases submitted by the cooperators, particularly from ODFW this quarter.
Work continued on updating the StreamNet Data Exchange Formats (DEF).  We completed a new DEF for habitat restoration projects, which will be put forward for formal adoption early in fiscal year 2005.  Because of some technical issues with the current DEF for hatchery returns and age data, we are revising the DEF and hope to have these data available early next fiscal year.

StreamNet continued to participate in and support various regional programs.  We implemented and supported an online discussion group tool for Subbasin Planning in Oregon, and implemented and supported a web site for Oregon’s subbasin technical team , TOAST.  We continued participation in the Pacific Northwest Aquatic Monitoring Partnership (PNAMP), the Collaborative Systemwide Monitoring and Evaluation Project (CSMEP), and the Northwest Environmental Data-network (NED).
The StreamNet website (www.streamnet.org) continued to serve as our primary data delivery tool.  We performed routine web server maintenance and conducted an upgrade, and accomplished ‘up time’ of greater than 99.5%.  We investigated available options for a replacement database platform should our current database software become too expensive for us to maintain.  Routine query system updates and bug fixes were performed, including updated XML output.  We implemented a “new” ASP.NET web server for testing and for implementation of CalFish, our companion project in California.  The server was actually an old PC that was reconfigured for this purpose.
Introduction


StreamNet Fourth Quarter Performance Report, Fiscal Year 2004
Page 3 of 56
The new GIS specialist became familiar with StreamNet data and processes.  He continued to expand the regional spatial data library and met with the state StreamNet GIS Specialists to develop a plan for an interim mixed-scale hydrography dataset.  He completed ESRI training for ArcIMS customization and administration, and upgraded the regional GIS software to ArcGIS 9.0 and ArcIMS 9.0.  He also worked with NOAA Fisheries to develop a new IMS application for the presentation of Critical Habitat data for the thirteen northwest anadromous fish species under review.  This effort will form the basis for a future redesign of the existing StreamNet IMS applications.
Administrative tasks continued during the quarter, including completion and submission of the FY-05 Statement of Work and budget.  We worked carefully with cooperators and staff to maintain project spending within the FY-04 budget in one of the tightest budget years ever.  

Columbia River Intertribal Fish Commission (CRITFC)

The StreamNet Library continues to be recognized and used as a major resource for archiving and accessing regional environmental information.  Usage was steady or slightly increased compared to previous quarters and year-ago statistics.  The Library also received major contributions of material from other agencies and is negotiating with the Audubon Society for management of a portion of their literature related to Columbia Basin habitats.

Archiving of Oregon subbasin planning data was nearly completed.  Our success in this effort is serving as the model in regional discussions on archiving other subbasin planning data.  The Project Leader is a member of a working group addressing the archiving needs.

The Project leader also participated in several regional inter-agency efforts to bring greater standardization to data collection and management efforts.  These include the Pacific Northwest Aquatic Monitoring Partnership, Northwest Environmental Data Network, Cooperative System Monitoring and Evaluation Project, and the John Day Analytical Framework Group.  Throughout these discussions a strong role for StreamNet was advocated.
Idaho Department of Fish and Game (IDFG)

Idaho StreamNet completed the compilation and submission of Idaho’s core 2003 data.  A business rules engine for our internal database was completed and implemented.  Utilizing both StreamNet and non-StreamNet staff members, we conducted data workshops for the bull trout status review.  Maps of the initial data have been distributed for review and we are checking the database for errors and inconsistencies.  We provided support to CSMEP by developing and starting their next set of data inventory work books and we are overseeing IDFG staff in completion of those workbooks.
Introduction


StreamNet Fourth Quarter Performance Report, Fiscal Year 2004
Page 4 of 56
Montana Fish, Wildlife and Parks (MFWP)

Data entry continued for the 2002-2003 field seasons in the fourth quarter.  Data exchange did not occur for the fish distribution table or the barriers table due to the massive amount of new information for those two data types that was provided during bull trout assessment process for Idaho and Montana, which StreamNet staff facilitated.  Those data sets will be exchanged in the 1st quarter of FY-05.
A draft creel table was sent to StreamNet in the fourth quarter.  Work continues slowly on the annotation layer for the Montana hydro level and several "fits and starts" have occurred over the year.  We will pursue moving this job to NRIS staff to complete the annotation; this was not a priority of the StreamNet SOW and was taken on in order to improve the quality of map requests.  

Genetic letters were converted to pdf format in the fourth quarter and new results were entered but not exchanged due to the absence of a DEF; this will be updated as an independent data set.  A genetics database was created for Montana State University's new genetics lab.  Support and training was also provided to the lab manager.  

Montana staff continued to assist in the development of the Resident Fish Hatchery Release DEF and the Restoration Project DEF.  HUC level maps were generated and provided to every state and federal biologist in Montana displaying Westslope or Yellowstone Cutthroat distribution, location of genetic sampling sites and a table listing the results for the genetic sample.  18 GIS map/data requests were also filled during the quarter.  

Montana has participated in several conference calls of the NED project and provided a historical perspective on Montana's involvement in regional data management.  The subbasin plans for Montana were reviewed by staff and determined that the only new data type may be fish disease/pathogens; parts of the plan were integrated into Montana's Comprehensive Fish and Wildlife Plan.  

Discussions have continued with respect to Kalispell office staff moving to Helena; Lydia Bailey will move to Helena as the GIS/Natural Resource Data Manager; Jeff Hutten will continue as the StreamNet western Montana Information Specialist but only at a half-time level, and Kim Lindstrom will resign as of January 1 and her position will be rewritten and moved to Helena.  StreamNet duties associated with Jeff and Kim will be reassigned to the remaining staff positions and some duties will be moved to a contract with NRIS.
Final review of the FY-05 budget occurred and agency work plans were completed for StreamNet duties.  The Information Management Unit received .24 FTE from the Fisheries Division for fish data/map requests and technical support outside of the StreamNet Work plan.  The Fisheries Manager's meeting was attended in September to discuss a data dissemination policy which includes the distribution of MFISH data on a statewide level.
Introduction


StreamNet Fourth Quarter Performance Report, Fiscal Year 2004
Page 5 of 56
Oregon Department of Fish and Wildlife (ODFW)
Progress was made on most project deliverables that were slated for attention during this quarter.  CBFWA’s request for us to conduct data inventory work, and then develop an online database application for the CSMEP project continued to contribute to delays in or postponement of some planned activities.  Support of the CBFWA effort continued throughout this report period.

Specific deliverables completed this quarter included the submission of updated Dam, Barrier, and Trend datasets, the posting of updated carcass placement data, internal and external project coordination, reference submissions to the Library, and development of the CSMEP Database Web application.  The other significant data related effort centered on providing unrolled hatchery release information to StreamNet for the first time.  This pilot submission will assist Regional StreamNet to develop the capability to map and present release information at the individual stream level.

Great attention was paid to organizing and standardizing the way Oregon and StreamNet as a whole manage and maintain reference information.

A pilot effort to develop enhanced 100K stream route data for the Grande Ronde basin was completed this quarter, along with the generation of linear event data for the 24K fish distribution.

A great deal of work was accomplished this quarter related to data and database management infrastructure improvements, including tool and metadata development, which are described in this report.

Work on Oregon’s various data update protocols continued this quarter.  The draft Distribution Data Update Protocol was presented and discussed at the Resource Management Team meeting, where we received the go-ahead to incorporate the final changes to the Protocol document and move forward with implementation.
US Fish and Wildlife Service
Activities during the fourth quarter were routine in nature, including participation in the Steering Committee and ongoing compilation of data related to the national fish hatcheries.

Introduction


StreamNet Fourth Quarter Performance Report, Fiscal Year 2004
Page 6 of 56
Washington Department of Fish and Wildlife (WDFW)
Newly defined staff roles became effective this quarter.  Our new Location Data Manager still spent about half her time on lingering responsibilities from her previous role.  Yet a smorgasbord of the various location issues cropped up this quarter.  Researching these issues gave us a refresher on the variety of work needed and practice with new spatial tools.  We are now better equipped to prepare a detailed work schedule for FY-05.  We also have generated a work plan for the new data compiler who will start work December 1, 2004.

The QC effort for the PCSRF project data provided a blueprint for organizing and documenting QC efforts on other datasets.  The blueprint works well for a very cumbersome dataset so it should accommodate other datasets easily.  WDFW will put it into place in FY-05 as part of our data conversion and exchange efforts.

Martin Hudson's paper "The StreamNet Hybrid Hydro Initiative - Status and Issues Discussion" captured the early challenges and initial solutions tested for creation of a hybrid 24K/100K hydro layer for StreamNet.  Jon Bowers of ODFW was also instrumental in issue identification and solution testing.  Creation of this region-wide layer will allow WDFW to update two-year-old 100K-based fish distribution currently available at StreamNet Online with more extensive 24K-based data that is based on a higher-resolution hydro layer.  This exciting break-through should result in much-improved StreamNet spatial data starting in the fourth quarter of FY-05.

Significant work was conducted in support of the CSMEP project.  WDFW StreamNet staff tested the Web-based data entry tool for CSMEP dataset inventory data by entering data from the Lewis basin inventory.  Several rounds of data entry were initiated, and comments on the application (screens and operation) were forwarded to the ODFW staff who created and maintain it.  The Project Leader and the Region 5 Data Compiler participated in regular CSMEP Project conference calls to update CSMEP staff on dataset inventory work progress and to keep tabs on related work.
Introduction


StreamNet Fourth Quarter Performance Report, Fiscal Year 2004
Page 7 of 56
Objective
1
Data acquisition and development

Support the need for region wide fisheries data for research, monitoring, modeling, and management 
through acquisition and regional standardization of new information and updates to previous information for priority fishery data types.  Data types may be addressed by all data providing agencies, or for specific data types by a single cooperating agency on behalf of the entire project.  This Objective addresses both anadromous and resident fish species, although priorities may differ.  The tasks under this objective are identified as high or low priority under the constraints imposed under base level funding.  Work on the low priority types will largely be limited in scope or effort unless new funding is approved.
Objective
1
Data acquisition and development
Task
1
Anadromous distribution and life history (habitat use) at the 1:100,000 scale

Document the occurrence, distribution and life history characteristics of anadromous fish species.  Project participants made major updates last fiscal year utilizing the new Data Exchange Format (DEF).  Maintenance of this data set will continue.  This is a high priority data set.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
IDFG
1
Update 100K anadromous fish distributions based on input 
We began work to import the updated salmon and steelhead distribution data from

obtained from subbasin assessment work and NOAA 
subbasin planning into the StreamNet DEF.

Fisheries critical habitat designation.

ODFW
1
Update, maintain, correct and exchange anadromous fish 
The GIS Analyst updated chum salmon distribution in the mainstem Columbia to 

distribution and documentation information.
include spawning use in 3 areas that were recently documented by ODFW

researchers.  He also implemented changes to the Distribution database for the 

records that conflicted with impassable culverts.  The changes were all based on

site visits by ODFW biologists and they resulted in 46 miles of "current" habitat

being changed to "historic" habitat.

The Data Technician continued to enter new records into the Incidental Fish

Observation database, which contributes to Oregon’s fish distribution and

distribution documentation datasets.  We currently have a total of 209 entries

into the IFO Database.

WDFW
1
The StreamNet database currently has all WDFW 
The 100K scale anadromous fish distribution data for Washington will remain fixed

anadromous distribution data collected at 100K resolution.  
(frozen); it will be replaced by 24K scale data once a compatible 4-state 

Submit corrections if warranted.
hydrography layer can be developed (estimated in the third quarter of FY-05).
WDFW
2
If the data exchange format issues are resolved to 
DEF and hydro layer issue related to supporting 24K scale data have 

accommodate WDFW's 24K distribution data collections, 
been identified and resolution will commence in FY-05.

convert and exchange WDFW's most current data.  


Objective:
1
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 8 of 56
Objective
1
Data acquisition and development
Task
2
Resident fish distribution and life history (habitat use)

Document the occurrence, distribution and life history characteristics of resident fish species.  Existing resident fish distribution will be

maintained, and project participants will begin expanding data for additional species.  This is high priority for Montana and Idaho, and new 

data will be developed by the other states as time allows.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
IDFG
1
Update  100K resident fish distributions using new IDFG 
We began work to import the distribution data from the Yellowstone and westslope

data surveys and sources, including westslope cutthroat, 
cutthroat trout status assessments into the StreamNet DEF.

Yellowstone cutthroat, interior Columbia-basin redband, 

and bull trout.

MFWP
1
Complete Distribution and Use Types data sets from data 
Data entry continued for the 2002-2003 field seasons in the fourth quarter.  The

collected from biologists, documents and reports during 
data were not distributed due to continuing work on the Bull Trout Assessment

2001-2002 using LLID stream routes and Montana's lakes 
project.  Data will be exchanged by 11/30/04.

coverage and watercode system. Exchange with StreamNet.  

Complete distribution and use type data sets for 2002-2003.  

Update entire state, including missed data from Western 

Montana in FY03.  Focus on target species during the year 

if opportunity arises.  Exchange the data to the regional 

database in the approved DEF format.

MFWP
2
Visit MFWP, other state and federal fisheries biologists in 
Data entry was ongoing in the fourth quarter.  Staff helped conduct the bull trout

2004 to collect 2002-2003 fish distribution and supporting 
status review in western Montana by collecting information on distribution and 

survey data and references.   Input all this information into 
barriers and entering them into MFISH.

the MFISH tables.  To aid in visits, provide maps and other 

support documents to biologists.

WDFW
1
Via distribution proofing parties, organize the effort to 
Transfer of westslope cutthroat trout distribution data to 24K scale hydrography will

update WDFW westslope cutthroat distribution data and 
commence in FY2005.

compile that data in concert with the existing federal data 

that was compiled in 2002. 

WDFW
2
Convert and exchange the westslope cutthroat distribution data.
This conversion and exchange was postponed until FY-05 due to higher priorities.
WDFW
3
As time and funding permit, scope data availability and 
The Project Leader and Fish Distribution Data Tech prepared maps and data forms

work to compile, convert and exchange distribution data for 
for formal Washington bull trout workshops intended to perform extensive statewide

other priority resident species (including coastal cutthroat 
assessment of bull trout population status as part of a federally-mandated five-year

and rainbow trout).
review.  We conducted three workshops in Ellensburg and Olympia, with two more

workshops and the data entry work scheduled for October 2004.  Additional bull

trout distribution and use data, along with updated barriers information, were

collected at these workshops in addition to the specific assessment-related data

needed.  Conversion and exchange of these data will be completed in FY-05.

Objective:
1
Task:
2
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 9 of 56
Objective
1
Data acquisition and development
Task
3
Adult abundance in the wild

Develop and maintain (update) information on adult abundance for native fish species, resident and anadromous, including escapement, redd counts, peak spawner counts, trap counts, dam and weir counts, and resident fish populations (where calculated by other agencies).  This is a high priority data type.  Also included in this data category are data gathered during spawning ground surveys regarding straying of hatchery fish onto spawning areas, i.e., marked/unmarked ratio.  These are lower priority under base funding.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Update mainstem Columbia and Snake River dam counts 
Updates were submitted to regional staff.  A few questions will be resolved during

through 2003 and provide updated data to the StreamNet 
the next quarter.

database.

CRITFC
2
Update available tribal spawning ground survey data.
Updates were submitted to regional staff.  A few questions will be resolved during

the next quarter.

IDFG
1
Complete the compilation of the 2003 field season redd 
The final 2003 redd count data were submitted to PSMFC this quarter.  We began to

count data from IDFG.  Prepare the data for inclusion into 
compile the 2004 redd count data.

StreamNet and submit.



IDFG personnel (non-StreamNet) used StreamNet databases and applications to complete the entry of 1960 - 2002 carcass data from spawning ground surveys.  Work is proceeding on the 2003-2004 carcass data capture.

MFWP
1
Collect all 2003 stream and lake fish survey data during field 
Data entry collected from the field biologists was completed in the fourth quarter.  

office visits; data may be one time visits, index streams 
The data were not distributed due to continuing work on the Bull Trout Assessment

and/or results from gill nets in lakes and reservoirs.
project.  These data will be included in the data exchange to be completed by

11/30/2004.

MFWP
2
Input 2003 data into MFISH, including trend, count and 
Data entry collected from the field biologists was completed in the fourth quarter.  

references.  Through the DEF Process, we will explore the 
The data were not distributed due to continuing work on the Bull Trout Assessment

creation of a DEF for Montana's stream survey data.  If DEF 
project.  These data will be included in the data exchange to be completed by

is not developed, Montana will look into submitting these 
11/30/2004.

data as a supplemental dataset to the StreamNet website.

ODFW
1
Update existing anadromous, resident, and non-game 
Trend updates were performed using data collected from ODFW District Biologists,

abundance and index trends through 2002. 
as well as other data contributors in the Columbia Basin.  Staff completed entry of

Opportunistically collect new trend information, including 
John Day Basin steelhead and Chinook redd counts, a number of routine counts in

marked-to-unmarked ratio data (relative to dam, weir, 
the Willamette R., PGE trends for the North Fork Dam on the Clackamas R., and

spawning ground, etc. counts) and hatchery-fraction data.
Marmot Dam on the Sandy R., and lower Columbia coho spawning survey counts.  

We continued to focus on other lower and mid-Columbia data entry, particularly in the Willamette and Deschutes subbasins.  Staff corrected, but also noted the types of errors found in updated trends in preparation for the focused QA/QC efforts that will be conducted during the next fiscal year.

Objective:
1
Task:
3
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 10 of 56

The final Trend data submission of the year was made on September 17th.  The submission consisted of 365 updated trends (including 188 new trends),containing 2,476 data records .  The 365 trends break out into the following data types:  Adult Return Dam/Weir counts (72), Adult Return-Estimates of Spawning Population (72), Adult Return-Redd counts (140), Adult Return-Peak/Other Spawning Counts (94), and Harvest-Freshwater/Estuary (3).  There were 25 new references associated with this data submission.
WDFW
1
Update and enhance the existing natural spawner database 
Natural spawn data for the 2003 return year was completed to the greatest possible

(escapement estimates and/or detailed counts) for available 
extent.  Some data are incomplete due to the lead biologist not getting the final

species (including a focus on steelhead data AND any dam 
numbers done by the end of the Q4 reporting time.  In years past, the StreamNet

or weir counts that might not already be captured in our on-
person in charge of the escapement data completed the final escapement numbers

going Adult Abundance collection).
for the biologist in order to have a complete data submission.  With a considerable amount of effort being put into the CSMEP project in August and September, generating a final escapement estimate for a given population was not possible.  A data exchange of 2003 escapement

Objective
1
Data acquisition and development
Task
4
Hatchery releases

Develop and maintain (update) information on the release of hatchery reared fish.  Emphasis this year will be on developing release data before release information is rolled up into PSC location codes.  Release data for resident species under base funding will be developed only where the data are readily available (primarily Montana).  Efforts will be made to complete cross references between PSC release codes and LLID stream location identifiers.  This is a high priority data set.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
MFWP
1
Exchange Montana's hatchery release data after 
The proposed hatchery releases DEF is still in development.

development of a resident DEF and/or modifications to the 

existing anadromous hatchery release DEF.  Number of 

years and number of waters will need to be determined.

ODFW
1
Compile and submit anadromous hatchery releases through 
Staff worked with Regional StreamNet staff during the quarter to address conflicts

2002, and 2003 where available.
between ODFW’s release data and StreamNet’s current Hatchery Release DEF.  A

sample dataset of unrolled hatchery release information was compiled manually and submitted to Regional StreamNet in late August in an attempt to quicken the process of creating a new Hatchery Release DEF.  We also suggested changes to the current DEF that would allow more concise data to be provided and to reduce the number of trends that get created during the compilation process.  Once the final DEF is crafted and approved, we will revise our automated data compilation process to match it, and submit all of Oregon’s hatchery release information.


Objective:
1
Task:
4
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 11 of 56
 ODFW
2
Create a cross table to link Pacific Salmon Commission 
Staff continued to work on cross-links to PSC codes during the quarter.  We 

codes to LLID stream based locations to provide more 
discovered that many of the watercodes that occur within ODFW’s Hatchery 

precise locations for releases.
Management Information System (HMIS) have never been used in conjunction with 

a hatchery release record.  Of the 2,250 remaining unmatched watercodes, only 700 have actually been used, and of those, only 306 have been used this decade.  Efforts this quarter have focused on reconciling the recently used codes that have associated release records, with 9 codes being matched this quarter.  In addition, we were able to associate many more records with Township/Range/ Section information, which if accurate, should improve our chances of finding the correct water bodies.  However, this effort will take much longer than anticipated, as we are down to the toughest codes to match with LLIDs.  Work will continue until all the unmatched codes that have actually been use are linked with LLIDs.

Region
1
Assist contributing projects with cross referencing PSC 
This fiscal year ODFW acquired direct access to the state hatchery release database

codes with LLID codes, as needed or requested.
(HMIS).   We discussed with ODFW how best to interpret that database and convert

those data to a yet-to-be-developed StreamNet data exchange format (DEF).
WDFW
1
For anadromous species, finish researching, compiling, 
The existence of WDFW's 24K hydro layer has slowed the progress on compiling 

converting existing WDFW anadromous release data as 
release data.  We met with WDFW's hatchery release data manager to discuss the

detailed, "unrolled" records.  Submit the data (and yearly 
impacts to cross-coding PSC (RMIS) codes, and the need to reformat his location

updates) directly to the StreamNet database (instead of via 
code file (WALOCS) and create data dictionaries.

RMIS).

WDFW
2
For anadromous species, WDFW and WDFW StreamNet 
The need to migrate all WDFW centralized hatchery data to a new platform created

staff work jointly to create a more efficient and predictable 
new internal priorities, and release data work was postponed until FY-05 in favor

means to compile the unrolled releases.
of concentrating on adult returns data.

WDFW
3
WDFW resident stocking data is fractured in several collections
The internal WDFW re-prioritization (See Objective 1, Task 4, Job 2) affected both 

by year.  Work at researching, compiling, standardizing and
resident stocking and anadromous release data.

converting data for any years we have finalized at a given time,

until all collections are submitted.  (Progress with this data set

relies heavily upon initial improvements to our Lakes spatial

layer).

 Objective:
1
Task:
4
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 12 of 56
Objective
1
Data acquisition and development
Task
5
Hatchery returns

Develop and maintain (update) information on the return, disposition and straying (e.g., from other hatcheries) of adult fish returning to hatcheries, including information on coded wire tags.  This is an anadromous related task only.  Priority will be placed on updating total return and egg take data through 2002.  Development of disposition data is lower priority and would require additional resources.  This is a high priority data set.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
FWS
1
Data received from National Fish Hatcheries will be 
Carson NFH and Little White Salmon NFH spring Chinook return 

processed and added to the new hatchery return file in the 
information was added to the CRiS Returns file.

DEF, after a new program is written and debugged.

IDFG
1
Complete compilation of the 2003 field season hatchery 
The 2003 hatchery returns data were completed and submitted to PSMFC this 

return data from IDFG. Prepare the data for inclusion into 
quarter.

StreamNet and submit

ODFW
1
Compile data on returns to ODFW hatchery facilities 
Staff worked through the StreamNet Forum to resolve issues with our ability to use

(updated through 2002 returns where possible).
the current Hatchery Returns DEF.  The forum was monitored throughout the 

quarter, and responses were posted when appropriate.  In order to meet our contracted obligation, we ultimately decided to roll up the data without the capture location information, and without including information from STEP programs.  Hatchery return data was submitted to StreamNet on September 17th, amounting to 154 hatchery return trends containing 1,481 annual data records, and 8,144 Hatchery Disposition records.

WDFW
1
Update and enhance the existing hatchery return database 
A concerted effort to convert all old DEF hatchery return data to the new DEF was

for available species per the newest DEF.
made.  Most of the hatchery return data has been converted to the new DEF but we

have hit some stumbling blocks as questions arose because other agencies are restructuring their agency data as well.  WDFW is in the process of converting hatchery return data in Paradox over to MS Access.  This process will incorporate a lot of new features that will help facilitate the data exchange process in the future.  No data exchange of hatchery return data was performed in the 4th quarter due to the time and effort put into dealing with WDFW and other agency concerns and problems.
WDFW
2
WDFW and WDFW StreamNet staff work jointly to create a
First drafts of the new internal WDFW returns data tables were released in late

more efficient means to analyze and simplify the hatchery 
September.  Further work here will be taken up in FY-05.

return data flow from the internal WDFW database. 


Objective:
1
Task:
5
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 13 of 56
Objective
1
Data acquisition and development
Task
6
Dams and Fish Passage Facilities

Develop and maintain information on dam facilities.  Update information as necessary.  This is a high priority data set.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
IDFG
1
Update dam information as necessary.
It was not necessary to make any updates to our dams and fish passage database this

year.

MFWP
1
Continue to update Montana's spatial coverage and 
Because there were no new dams or fish passage facilities identified, the current 

associated tabular file of dams.  Exchange with StreamNet.
StreamNet data are current.

ODFW
1
Maintain and update, as needed, based on errors found in 
A new Dam table was submitted to Regional StreamNet in mid- September, which

the Oregon dam and fish passage facilities information.
covered some recent deletions and modifications.

WDFW
1
Update the dam database, adding records and improving 
Prompted by the StreamNet Data Manager's questions, WDFW's Location Data

field entries as warranted.
Manager started researching how a "retired" staff member compiled the existing

Dam dataset.  We are awaiting a response from the National Inventory of Dams 

(NID) stewards regarding the redundant locations of several dams and 400+ dams we found were missing from the NID website.
Objective
1
Data acquisition and development
Task
7
Hatchery facilities

Develop and maintain information on anadromous and resident hatchery facilities, including information on location, design, management and

authorization.  Update information as necessary.  This is a high priority data set.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
FWS
1
The hatchery facility database file will be updated as needed.
The Access table version of the Hatchery file was updated.  Several no longer used

facilities were again entered in this table, and several records were updated with new

hatchery manager information.

IDFG
1
Update hatchery facility data as necessary.
It was not necessary to make any updates to our hatchery facilities database this 

year.

MFWP
1
Update the StreamNet hatchery database with Montana's 
Data were reviewed by biologists in the Fisheries Division and one missing hatchery

public and private facilities.  Exchange with StreamNet upon 
facility was discovered.  We are still awaiting a classification for this facility as to

completion.
ownership.


Objective:
1
Task:
7
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 14 of 56
ODFW
1
Maintain and update, as needed, based on errors found in 
One new hatchery facility ID was submitted with the Trend submission on 

the Oregon hatchery facilities information.
September 17th.

The Database Manager worked with Regional StreamNet staff on an issue regarding the lack of references for some of our hatcheries in the StreamNet Hatchery table.  A workable solution was agreed upon, and the appropriate changes were made to the database.

WDFW
1
Update the hatchery database, adding records and 
No physical progress was made with the Hatchery Facility database this quarter.  

improving field entries as warranted, including record 
Several facilities changed their names, etc.  Yet, before we even update WDFW's

updates for related tables (i.e. HatcheryXProduction data).
internal database we need to re-organize the entire database accessibility and format.  

With our current investment in location data management this FY, we are closer to

testing the alternatives.
Objective
1
Data acquisition and development
Task
8
Harvest

Develop and maintain (update) information on sport and commercial harvest.  Higher priority is assigned to anadromous species.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Complete and update ocean and Columbia River catch data 
This update was postponed due to the demands of supporting subbasin planning

through 2003
efforts.  A supplemental contract for support to the John Day subbasin planners

will occupy key staff through January 2005.

IDFG
1
Work with IDFG Fisheries staff to incorporate IDFG harvest 
Because of unanticipated commitments, primarily to CSMEP and the Bull Trout 

data into StreamNet.
Status Review, we did not work on incorporating Idaho harvest data into StreamNet

this year.

MFWP
1
Explore the possibility of exchanging Montana's limited 
A draft table for creel survey data was sent to PSMFC in the fourth quarter.

creel survey data using the current Harvest DEF.  Exchange 

if data is compatible and/or desired by the Steering Committee

ODFW
1
Compile and exchange Oregon sport harvest data through 
We have requested updated harvest information from ODFW staff who are 

2001.
responsible for maintaining this data, but had not received the information by the

end of the quarter.  We will continue to pursue this data and update the information 

in StreamNet once it becomes available.


Objective:
1
Task:
8
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 15 of 56
WDFW
1
Although we should only be in maintenance mode for this data
WDFW StreamNet made no significant progress on this data task in FY-04 due

set, WDFW re-organized their data collection process several
to low priority and emergence of other areas of focus.

times since our last StreamNet update (and it's still in flux) so it

poses a large workload.  As such, we need a large allotment of

time before renewing this effort and this year we're devoting any

discretionary time to barriers.  As funding and time permits,

compile freshwater harvest for key Columbia Basin salmonid 

stocks for both anadromous and resident data, using existing

WDFW data sets (i.e. Angler Fish Database) and other sources.

Standardize the data (to stock if possible), convert and submit

it to the StreamNet database.
Objective
1
Data acquisition and development
Task
9
Hydrography

Maintain a regionally consistent routed hydrography layer at the 1:100,000 scale.  This LLID based hydrography is the basis for georeferencing and displaying locations for all other data in the StreamNet database, and as such is an essential data set.  Data will be updated as necessary.  Exploratory work will be initiated in preparation for the eventual, inevitable move to the 1:24,000 scale hydrography being developed by other entities.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
MFWP
1
Using the NHD, complete updating the routes using the 
No edits were completed in the fourth quarter.  Data were exchanged 10/18/04.

updated NHD layer; quality check the cross-reference 


between the LLID system and MFWP's watercode system (a

system still used to index fishing pressure, hatchery plans 

and numerous other databases).

MFWP
2
Error check and edit Montana's lakes layer which was 
Editing continued on the lake layer during the fourth quarter.  Data were exchanged

created using 1:24 000 and 1:100 000 base hydrography.  
10/18/04.

Provide to StreamNet for use with Hatchery Release Data.

MFWP
3
Using ArcGIS, create new stream annotation layers at 3 
Work continued slowly on this and several "fits and starts" have occurred over the

Scales: generalized, HUC level and Stream Level.
year.  We will pursue moving this job to NRIS staff to complete the annotation.  

This was not a priority of the StreamNet project and was added to improve our 

hydrography layer; it was removed from the FY-05 SOW.

ODFW
1
Maintain and update, as necessary, the 1:100,000 scale 
The MultipleHUCStreams table in the ODFW Hydrography database was updated

hydrography files for Oregon.  Submit all changes to the 
this quarter.

StreamNet database at the Regional office.



Objective:
1
Task:
9
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 16 of 56

The GIS Analyst completed a pilot effort to develop enhanced 100K stream route data for the Grande Ronde basin.  He also generated linear event data for the 24K distribution.  The process was summarized and the data were submitted to the Regional StreamNet GIS Specialist.  A meeting will occur early in the next quarter to follow up on this effort and discuss ways to improve upon the process.

 WDFW
1
Update, as necessary, the Washington 1:100,000 scale Stream,
On July 9 we met with Framework participants to continue to discuss coordination

Lake, and Marine Area hydrography files.  Submit all spatial
efforts for creating a standard Washington state 24K hydrography layer.

and tabular changes to the StreamNet database at the Regional
 

office for inclusion in the PNW regional hydrography layer. 
Our Location Data Manager started tabular comparisons of the 24K hydrography

against the 100K hydrography to research the 24K compatibility with our data cross-references.  She also started researching the GNIS and Washington State Naming Board's requirements to formalize or change official names.

Stan Hammer (WDFW) started collecting GPS readings for various hatchery release sites as he conducted his standard field work.  Sikora met with Hammer (and his supervisors) to direct his work.  More direction is needed when time permits.

The Location Data Manager used ARCGIS to match select lake MUCODES with existing lake polygons.  She also reviewed staff efforts to create a spatial cross-reference table for spawner data tied to stream catalog codes.

Objective
1
Data acquisition and development
Task
10
Habitat restoration / improvement projects

Acquire data sets related to habitat restoration / improvement projects from the multiple agencies, tribes and organizations within the Columbia Basin, and compile and maintain them in standardized, consistent formats.  Preliminary work has been completed on this data type, but regional priority has not been assigned to developing these data.  Work continues on improving the data structure and DEF, primarily through work being done by a related project in California.  This currently remains a low priority data type under current base funding, but is ready should a higher priority be assigned by regional entities.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
MFWP
1
Continue to collect, centralize and maintain all stream 
Data entry is complete and the data will be exchanged by 11/30/2004.

restoration projects data for Montana using the "Future 

Fisheries Interface" which StreamNet staff maintains and the

Fisheries Division inputs data.  Exchange data to the 

Region twice during the year.

MFWP
3
If the opportunity arises, participate in any regional actives 
Montana has been involved in the review and testing of the proposed 

related to restoration projects including the Pacific Coast 
DEF for restoration projects and approved of the changes.

Salmon Recovery Fund.


Objective:
1
Task:
10
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 17 of 56
WDFW
1
If funding and time permits, convert  habitat restoration 
We continued work refining QC tools/queries for the PCSRF data. 

project data stored in Washington's IRC's (Interactive 


Committee for Outdoor Recreation) PRISM database and 
To create a glossary database to augment any project dataset, we searched for an

submit to StreamNet.  NOTE - We anticipate a pilot effort 
electronic copy of the late Neil Armantrout's publication Aquatic Habitat Inventory

(under other funding) to compile other source habitat 
Terminology.  Although the American Fisheries Society sells printed copies, they

restoration data in StreamNet's newest format.
don't have an electronic copy and we're currently at an impasse.

The loss of our data compiler this quarter and hiring delays that will last until November effectively froze further habitat restoration project work until FY-05.
Objective
1
Data acquisition and development
Task
11
Barriers

Develop and maintain data sets for barriers to fish migration.  This category is still being organized.  Existing data on adult barriers will be maintained and updated as practical.  Other sources of data will be explored.  Work on juvenile barriers and culverts may require revisions to the DEF.  The primary emphasis is on anadromous species except in non-anadromous areas.  This is a low priority data set under current base funding, and will be addressed as time and other priorities allow.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
MFWP
1
Complete update to barrier location, species affected and other
Data exchange was delayed because additional fish passage barriers were added

fields on stream barriers in Montana once the data collected
during the bull trout status review conducted by Montana and Idaho.  This effort

during the Westslope Cutthroat Assessment Process conducted
is near completion and data will be exchanged by 11/30/2004.

in 2002 is reviewed by MFWP biologists.  Information will be

collected on all species regardless of life history.  Exchange

Barriers data with the StreamNet database.
ODFW
1
Update and maintain Oregon's Barrier data and minimal Fish 
We evaluated a variety of options for resolving the issue of numerous and erroneous

Barrier data development based on new barrier information.
categories in the Fishway Type table, and worked with ODFW staff to arrive at a

list of 6 primary types, with several additional categories such as "unspecified ladder".  The old fishway coding was converted to reflect the new fishway table values, and inconsistent diversion detail and project type coding was also cleaned up.  We corrected erroneous LLID and measure values associated with 100K barriers that were not mapping, and added a record to the Barrier database for the hatchery facility related structure at the Salmon River hatchery.  The Barrier dataset now includes all dams, culverts and natural barriers together.  There are 7 related tables, which include the fish passage table and all of the various barrier type-specific "detail" tables.  Metadata for our updated Barrier information was nearly completed until an ArcGIS 9 bug that does not adequately allow you to document the entity and attribute values for related tables was encountered.  Our GIS Analyst spent considerable time troubleshooting this problem, but completed the metadata (via a manual workaround) for the version 2 Barrier GIS dataset.  The Barrier, FishBarrier and LocMaster data and metadata were submitted to StreamNet in early September.


Objective:
1
Task:
11
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 18 of 56
WDFW
1
Scope any existing Washington state barriers data for a 
No progress was made on this low priority dataset in FY-04.  Barriers has been

pilot data submission this FY.  Data sources will at least 
upgraded in priority in the FY-05 work statement and the new data compiler will be

include the SSHIAP and TAPPS databases.
focused on this as one of the highest priorities.
Objective
1
Data acquisition and development
Task
12
Juvenile data (abundance and outmigration)

Develop and maintain information on smolt production (as determined from smolt traps), juvenile abundance (as determined through snorkel, electrofishing, and other surveys), and smolt density model estimates.  Primary emphasis will be on maintaining the existing smolt density model data and development of a DEF for these data.  The rest of the work for this data category is still under development and will require additional resources to accomplish.  This is a low priority data set under current base funding, and will be addressed as time and other priorities allow.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
ODFW
1
Compile juvenile abundance data as they are identified and 
According to correspondence with Bart Butterfield (IDFG StreamNet), they will not

become available.
propose a new juvenile abundance data section of the DEF, and because Oregon’s effort was dependent upon having a new DEF to work from, we were unable to complete this deliverable during this fiscal year.

WDFW
1
As funding and time permit, keep informed about other 
Continued effort was made to update and maintain the Cedar Creek smolt trap data.  

WDFW agency staff efforts to organize the juvenile data 
Statistical analysis was performed on the data and delivered to the Natural Resources

and scope existing juvenile data to plan future conversion 
Building headquarters in order to justify and maintain funding for continued data

and submission efforts.
collection.  A fit for this data within a StreamNet format will be pursued in the

future.  Maintaining this data for the regional biologists along with WDFW 

managers is important for not only resource tracking but management purposes.
Objective
1
Data acquisition and development
Task
13
Age

Develop and maintain information on age/sex composition of returning adults, primarily for anadromous species.  Emphasis on this data type will increase once the draft DEF is tested and finalized.  This is a low priority under current base funding.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Update CRITFC age data on sockeye and Bonneville Dam 
Updates were submitted to regional staff.  A few questions will be resolved during

sampling
the next quarter.

FWS
1
The Age table will be updated using the Snage program 
Age composition information for Carson NFH and Little White Salmon NFH spring

after processing is completed within the CRiS database.
Chinook were added to CRiS files.

IDFG
1
Complete the compilation of the 2003 field season age data 
The 2003 age composition data were completed and submitted to PSMFC.

using hatchery returns data from IDFG.


Objective:
1
Task:
13
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 19 of 56
ODFW
1
Compile age composition data as they are identified and 
Staff continued to contact potential age data providers this quarter, and continued to

become available.
work with Regional StreamNet to resolve issues related to the Age data DEF.
WDFW
1
As warranted, update Age data links with other "count" 
Continued effort was made to collect age data associated with hatchery return data.  

data records (i.e. hatchery returns and adult abundance).
Age data currently in Paradox has been ported to MS Access for future data

manipulation.

Objective
1
Data acquisition and development
Task
14
Production factors and run reconstruction

Develop and maintain information on survival, production factors, spawner / recruit estimates, and run reconstruction.  This is a low priority data type under current base funding, but the existing spawner / recruit estimate data will be maintained.  Current effort will focus on what aspects of this kind of data are most needed.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Coordinate with ESA recovery planning and NWPPC 
Some productivity data is available in datasets created during subbasin planning.  

subbasin planning efforts to capture available anadromous 
Some of this information exists in the EDT system maintained by Mobrand 

fish and bull trout productivity data for eventual DEF 
Biometrics.  It cannot be accessed through the interactive Web-based version of

testing and inclusion in StreamNet.
EDT, however.  We will continue to work with MBI to gain access to this 

information.
ODFW
1
Participate and/or contribute to the maintenance of existing 
The Data Analyst worked with Idaho and Washington counterparts to definitively

data related to production factors and run reconstruction.
identify the source of StreamNet’s existing Spawner-Recruit information.  Working

together, they located a corrected hard copy and electronic file of a 1997 document, 

and concluded that the Spawner-Recruit Data on StreamNet does indeed refer to this

1997 document.  This information was provided to Regional StreamNet so the trends 

could be updated with the correct reference number.
WDFW
1
Scope the availability of stock based catches used in the 
WDFW made no significant progress on this data task in FY-04 due to low priority

PSC treaty process which are crucial for run reconstruction.
and emergence of other areas of focus.


Objective:
1
Task:
14
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 20 of 56
Objective
1
Data acquisition and development
Task
15
Diversion Screening

Explore the availability of data on diversion screening.  Capture data on screens as time and other priorities allow.  The DEF will need to be finalized before much can be done with this data type.  This is a low priority data set under current base level funding.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
ODFW
2
Capture GPS coordinates for water diversions and fish 
The Data Technician attempted to obtain fish screen location information in the

screens in the Willamette subbasin.
Calapooia River system from below Thompson's Mill to the city of Albany, but

found only two possible current irrigators.  However, no landowners could be 

located, so no coordinates were taken.  She also worked during the quarter on

gathering fish screen location data for the Long Tom River system, gathering 

landowner names, and contacting Long Tom Watershed council representatives

for information.

WDFW
1
As funding and time permit, review existing Washington 
WDFW made no significant progress on this data task in FY-04 due to low priority

diversion screening data, identify additions and corrections 
and emergence of other areas of focus.

needed and plan for future exchanges.  Possible data sources

include Yakima Screen Shop, SSHIAP, TAPPS, HPA databases.
Objective
1
Data acquisition and development
Task
16
Other data sets

On an opportunistic basis, develop other types of data as available or as requested by FWP participants.  This relates to data relevant to StreamNet objectives which would be developed by StreamNet cooperators.  Actual acquisition, standardization, georeferencing and distribution of these data will be dependent on available time and funding.  These data may be included in the DEF in the future, or may be obtained and distributed as independent data sets in 'as is' condition.  This is a low priority under current base funding.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
MFWP
1
Provide updated genetic results information on Montana's 
Genetic letter entry continued in the 4th quarter.   Genetic letters were converted to

species of concern.  Explore providing data on Whirling 
.pdf format in the fourth quarter.  No DEF is available to exchange genetic data

Disease results for Montana's streams and rivers; creel data 
with StreamNet.

if format is not appropriate for harvest DEF; and fishing 

pressure data on Montana's lakes and streams.

ODFW
1
We will work with ODFW and other agency staff to facilitate
Staff obtained carcass placement information for 2002 - 2004 and posted the

either the incorporation of their data into StreamNet or 
information on the NRIMP website as an independent dataset for StreamNet.  A

independently posting their data on the StreamNet web site.
link to the new Carcass Placement data (up-to-date through May 2004) was included 

with the September 17th data submission to StreamNet.

No requests were received during this project period to post independent data sets from Oregon.

Objective:
1
Task:
16
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 21 of 56
Region
1
Advise and assist data developers with other data sets 
No work was requested for this job this fiscal year.

(those being compiled by StreamNet cooperators but not 

currently in the StreamNet DEF or the queryable database).  

Low priority, and within current resources only.

WDFW
1
On an opportunistic basis, develop other types of data, as 
WDFW developed no other data types in FY2004.

time allows

Objective
2
Data management and delivery

Provide high quality data management services, with specific emphasis on the creation of regionally consistent data sets and the timely delivery of data to users in formats that meet their policy, planning, monitoring, and management needs.
Objective
2
Data management and delivery
Task
1
System Administration

Manage and maintain the computer systems (hardware and software) necessary for supporting the tabular and GIS data systems at the regional and cooperating agency levels, including system backup.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
IDFG
1
Manage, maintain and enhance the computer systems 
Working with the IDFG IT Bureau and the State of Idaho Department of 

(hardware and software) necessary for supporting the 
Administration, we worked on developing Internet access to our IIS server with

tabular and GIS data systems, including system 
appropriate security through the state's firewall.  This will provide access by outside

administration, backup and recovery, hardware and software
agencies to our fish and wildlife databases.

upgrades, and security.


Routine system administration and management continued throughout the quarter.
MFWP
1
Manage, maintain and enhance the computer systems 
Ongoing.  No major problems were encountered in the system that is used to store

(hardware and software) necessary for supporting the 
tabular and spatial data for MFISH.

tabular and GIS data systems, including system 

administration, backup and recovery, hardware and software

upgrades, and security.


Objective:
2
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 22 of 56
ODFW
1
Manage, maintain and enhance the computer systems 
In order to improve our ability to manage and provide access to Oregon’s GIS 

(hardware and software) necessary for supporting the 
products, our GIS Analyst: 

tabular and GIS data systems, including system 
-- Continued to coordinate the transfer and renewing of ODFW’s various GIS 

administration, backup and recovery, hardware and software
licenses.  This process was completed this quarter.

upgrades, and security.
-- Researched ESRI's white papers and contacted a sales representative for pricing

information on IMS and SDE.  He met with the Oregon ESRI account manager and

also an SDE / IMS expert from the Olympia office to discuss both programmatic and

technical details of and ODFW implementation of these software packages.  He learned of the capabilities and limitations of each, in particular related to linear referencing systems.  He drafted an ArcSDE / ArcIMS evaluation plan, requested an evaluation copy of these two products, and worked with ESRI throughout the quarter to obtain them.  To further advance his understanding, he attended an ArcIMS user group meeting in Portland in August, where presentations were made on the Data Delivery Extension (DDE) to ArcIMS and also on the ESRI GIS Portal Toolkit.  He also participated in the Portland ArcSDE user group meeting in Portland in late August.

-- Researched SQL Server to better understand the various options and licensing available, and talked with ODFW Information Systems Division (ISD) staff regarding possibly using their Enterprise version of SQL Server.  He learned that ISD currently has some additional capacity and could potentially host some of NRIMPs/Oregon StreamNet’s applications.  We will follow-up on this option in the near future.

-- Researched MySQL and ArcGIS issues, in particular related to ODBC and OLE DB for accessing the (MySQL) barrier database from ArcGIS.  There are a number of issues that prevent seamless usage between the two programs with the long text field format causing some, but not all of the problems.  More research will need to be done on this before we can move forward in any meaningful way.

--Installed the development version of SQL server on his local machine and spent considerable time familiarizing himself with the database and application development architecture.

All staff performed other routine system administration functions during the quarter.
Region
1
Manage, maintain and enhance the existing tabular database
Routine backups were frequently made of all important databases.  Detailed review

systems, including hardware, software, tools, database 
of the SQL Server StreamNet database schema was undertaken relative to the

structure, QA/QC activities, and system administration, 
current StreamNet Data Exchange Format to make table and field naming, data types 

backup and security.
and definitions as identical as possible.
Region
2
Maintain and update, as necessary, the hardware and software,
Routine GIS system maintenance continued and GIS software was upgraded to  

including ArcView and other tools, extensions and projects, that
ArcGIS v9.0  and ArcIMS v9.0.

constitute the regional Geographic Information System.  Provide

system administration, backup and recovery, and security.

Objective:
2
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 23 of 56
Region
3
Maintain and upgrade the StreamNet web server and software,
There were no significant updates required this quarter and operational up-time was

including programming, tool development, system security, etc.
excellent, exceeding 99.5%.
Region
4
Assist with development of XML schema based options for 
We implemented basic web services using both ColdFusion and Microsoft IIS on a

both incoming and outgoing data.  Continue exploration of 
new .NET test server.  This "new" server is actually an old PC that was converted to

how XML can enhance data exchange and develop data use
this new function since no funds were available in the flat budget for a new server.

agreement to control subsequent use of StreamNet data by 


other websites.

WDFW
1
Manage, maintain and enhance the computer systems 
New GPS units were purchased to better collect and cover the vast index areas 

(hardware and software) necessary for supporting the 
within the Columbia River.  ArcGIS shape files were updated and new MS Access

tabular and GIS data systems, including system 
tables added to the Columbia River layers at the Vancouver office.  Routine patches

administration, backup and recovery, hardware and software
and updates were made to essential software in order to maintain day to day activity.

upgrades, and security.
Objective
2
Data management and delivery
Task
2
Application and Interface Development

Develop computer applications and interfaces that facilitate the entry, management and dissemination of tabular and GIS data at the regional and cooperating agency levels.  This will include development of new applications and tools as well as maintenance or modification of existing applications.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Develop data handling applications to ease transfer of tribal 
Gradual erosion of funding through budget restrictions and inflation have removed

data to StreamNet
support for this task at the present time.  Instead we will seek other funding sources

and collaborative partners to accomplish this task.  We will also encouraging tribal

staffs to use the StreamNet system more frequently, assuming that as use increases,


they will recognize the value of contributing their own data to StreamNet.
IDFG
1
Develop and/or maintain computerized databases, 
A business rules engine was completed and implemented for our local fish and 

applications and interfaces that facilitate the entry, 
wildlife databases.  Business rules conduct procedures such as checking for valid

compilation, management and dissemination of tabular
values entered into user interfaces.  They help to insure accurate data entry and


and GIS data.
maintain data integrity in the databases.  We enhanced our new Reference System

coded in VB.Net with the business rules engine.

We also worked on various other pieces of our database framework.  Progress was made on the Importer/Exporter program that transfers data between the distributed client-user databases and our central database.


Our data coordinator linked the IDFG Spawning Ground Report Microsoft Word documents to our spawning ground survey database.  This provides automatic updating of the Spawning Ground Reports whenever the database is updated.


Objective:
2
Task:
2
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 24 of 56
MFWP
1
Develop and/or maintain computerized databases, 
A genetics database was created for Montana State University's new genetics lab.  

applications and interfaces that facilitate the entry, 
Support and training was also provided to the lab manager. Routine database

compilation, management and dissemination of tabular
management was ongoing.


and GIS data.

ODFW
1
Develop and/or maintain computerized databases, 
An online Reference application was developed and posted on our production server.  

applications and interfaces that facilitate the entry, 
Users can now add new, or update existing records, as well as query the database

compilation, management and dissemination of tabular
using a Google-type query.  The search allows users to query on multiple authors

and GIS data.
and titles at once.

Development of a project proposal web application that could be used to propose new and track existing projects/efforts within our program, including StreamNet tasks continued during the quarter.  A beta version of the application was deployed to our production server and is being tested.

Our Database Manager completed work on a new ASP.NET application framework for use in developing any of our web application sites, including the graphical update.  The previous version that was created was used extensively to minimize common coding and the time required to implement web applications, but had some issues associated with login authorization that will be addressed by this new version.  Also included in the new framework is the ability to modify pages real-time without needing to code or compile the application.  The framework is now being used to implement one of our existing sites, as a test.

Our GIS Analyst developed a geodatabase raster catalog of all DRG's statewide, making the problem of having to load individual DRG's a thing of the past.  Having these data in a catalog enables nearly instantaneous display of DRG data statewide (at appropriate scales).  This could also be applied to either DOQ's or DEM's.

Region
1
Develop and/or maintain computerized databases, 
No new tools were requested or developed this quarter.  All existing databases and

applications and interfaces that facilitate the entry, 
tools were maintained.

compilation, management and dissemination of tabular and 

GIS data..  Assist cooperating agencies with tool 

development, as requested.  Tools may include input 

interfaces, error checking, geographic locators, etc.

Region
2
Maintain and improve the LLID/NHD hydrography 
No attempt was made to improve the hydrography conversion tool this year due to a

conversion tool.  Immediate need is to complete error 
combination of higher priorities and turnover in the GIS Specialist position.

trapping routines and polish the final application.


Objective:
2
Task:
2
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 25 of 56
Region
3
Create an Online Event Mapper to allow users to create 
Work on the online Event Mapper (to assign LLID values to locations on the 

event tables based on 1:100K Hydrography over the Internet.
1:100,000 hydrography) was delayed by the vacant GIS Specialist position last

quarter and the need for the new GIS Specialist to become familiar with StreamNet

functions and increase his familiarity with ArcIMS.  This job will be moved forward

to next fiscal year.

WDFW
1
Develop and/or maintain computerized databases,
Routine maintenance of WDFW StreamNet databases continued during the quarter.

applications and interfaces that facilitate the entry,


compilation, management and dissemination of tabular 

and GIS data.

Objective
2
Data management and delivery
Task
3
Data (content) Management

Manage data at the regional and cooperating agency levels to assure timely and accurate data flow from source to final distribution.  Activities include exchange of data to PSMFC, data loading, updating data, quality assurance procedures, metadata development, etc.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Manage data at the agency level (including data loading, data
Metadata have been completed for all archived Oregon subbasin planning data.  

updating and quality assurance), develop and maintain FGDC
Describing QA/QC procedures was begun for all data reported by CRITFC to the

compliant metadata for GIS data, work toward developing
StreamNet system.

metadata for tabular data, and exchange data to PSMFC

according to deadlines specified in this work statement.
FWS
1
Manage data at the agency level (including data loading, data
Hopefully, the final subtleties were added to the program that converts data form 

updating and quality assurance), develop and maintain FGDC
CRiS files to files in the StreamNet DEF.  After a substantial and sustained effort,

compliant metadata for GIS data, work toward developing
all known HatcheryReturn, HatchDisposition, and Age data for hatcheries and

metadata for tabular data, and exchange data to PSMFC
species in the Columbia River Basin were added to StreamNet files and submitted

according to deadlines specified in this work statement.
to PSMFC.

IDFG
1
Manage data at the agency level (including data loading, data
As mentioned under Objective 1, we submitted 2003 hatchery returns and age

updating and quality assurance), develop and maintain FGDC
 composition data to PSMFC.

compliant metadata for GIS data, work toward developing


metadata for tabular data, and exchange data to PSMFC
We started a cooperative effort with IDFG biologists to develop metadata for IDFG

according to deadlines specified in this work statement.
stream survey data.

MFWP
1
Manage data at the agency level (including data loading, data
Data within the data systems that we are responsible for were updated, backed up 

updating and quality assurance), develop and maintain FGDC
and quality checked where necessary.  No new metadata was developed this quarter.

compliant metadata for GIS data, work toward developing
 

metadata for tabular data, and exchange data to PSMFC

according to deadlines specified in this work statement.

Objective:
2
Task:
3
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 26 of 56
ODFW
1
Manage data at the agency level (including data loading, data
Staff worked throughout the quarter to correct, synchronize, and centralize the

updating and quality assurance), develop and maintain FGDC
various reference tables that exist among our staff, and to strategize how to avoid

compliant metadata for GIS data, work toward developing
synchronization problems in the future.

metadata for tabular data, and exchange data to PSMFC


according to deadlines specified in this work statement.
Staff continued to develop documents describing our QA/QC processes, particularly

within the trend, reference, and incidental fish observation datasets.

Staff worked throughout the quarter on the StreamNet forum issue related to updating references where the 'year published' field is populated with the placeholder, '9999'.  Efforts included comparing the list of references in question against the hardcopy references that are housed at our office, and against those on the StreamNet Library web site in order to populate this field with accurate information.  Many of the records have been corrected and submitted to Regional StreamNet.  The remainder will be addressed when the issues raised on the Forum are addressed.

As a follow up to the September StreamNet barrier data submission, the GIS Analyst conducted some Q/A targeted specifically at dam records.  He identified and corrected a number of duplicate records as well as a number that did not have proper LLID / measure coding.  These issues were cleaned up and the Dams data submission to StreamNet was prepared.

The GIS Analyst developed a set of data integrity rules that need to be enforced within the Barrier database.  These will be implemented either through application logic if we continue to maintain these data in MySQL or as relationship classes, domains, and validation rules, etc., within a GeoDatabase if we migrate these data permanently to an SQL Server 

ODFW
2
Continue development of a corporate information system.
Work on the corporate information system came in the form of development of

component applications, including our web application framework and our online

reference application.  Much of the work described under Objective 2, Task 2 

contributes to the development of a corporate information system.
ODFW
3
Coordinate and work with internal ODFW staff to improve 
We completed edits to the draft Distribution Update Protocol’s Objective, Issues, & 

the agency data collection efforts to allow more efficient 
Recommendations section, including the creation of a checklist, examples, and draft

compiling into internal intermediate ODFW-NRIMP/ 
flow chart outlining the update process to facilitate ease of use.  Several biologists

StreamNet databases and/or StreamNet databases.
were contacted for input on how the protocol should address changing "current" 

habitat to “historic” habitat for a variety of resident species including rainbow trout. lamprey, and various cutthroat trout.  Preparations for presenting the draft protocol to ODFW’s Resource Management Team (RMT) were also finalized.  The Update Protocol was presented and discussed at the RMT meeting in early September.  The Team gave us approval to incorporate the final changes to the Protocol document and move forward with implementation.


Objective:
2
Task:
3
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 27 of 56
Region
1
Assist data contributing agencies in development of data, 
Work continued refining Data Exchange Format issues with new HatcheryReturns,

including formatting, coding, data entry, error checking, and
HatchDisposition and Age data tables as compilers provided their first attempts at

submitting to the regional database.
providing these data.

Region
2
Examine the StreamNet database for errors and report any 
Many exchanges between the Regional Data Manager and agency data compilers 

found to the appropriate entity for correction.  Continue to 
occurred as data records containing errors, omissions, ambiguities or inconsistencies

improve error-checking capabilities.
were encountered.

Region
3
Update and append data as submitted by StreamNet 
We published updated Access 2002 and Access 97 versions of the downloadable 

participants.  Isolate erroneous or duplicative data and work
StreamNet databases on the StreamNet web site.  We replaced all individually

with source agencies to correct problems.  Maintain logs of 
downloadable ASCII files of StreamNet tables, Data Dictionary definitions and Data

data submissions and major database changes.  Produce 
Categories Help pages.

downloadable versions of the StreamNet databases to keep 


in synch with the updated regional databases.
Major data updates from ODFW were submitted and validated this quarter, 

including 185 new Trends, 1,936 new EscData (escapement) records, 1,429 new HatcheryReturns records, 4,926 Barriers (new and replacement records), and updates to Reference and Dam tables.  ODFW also submitted a sample database of Hatchery Release data, but this submission was not processed during this project quarter.  IDFG submitted 41 new EscData records and updated References that were validated.  IDFG and USFWS both submitted HatcheryReturns and Age data that did not complete validation during this quarter.CRITFC provided Library Reference key updates.CDFG submitted updates to Dams, Barriers and Location codes.

Region
4
Work with RMIS and the StreamNet partners to develop a 
A sample database of Hatchery Release data prior to combining planting records by

means of georeferencing hatchery release data.   Since it is 
coded-wire tag code was provided by ODFW, but was not processed or validated

not currently possible to georeference the RMIS hatchery 
during this project quarter.

release data to the 100K hydrography and the data can't be 

updated without such georeferencing, work with StreamNet 

data compilers to provide release data in StreamNet data 

exchange formats to be developed.  Until that time, send 

data users to the RMIS site for current release information.

Region
5
Help the StreamNet Librarian to optimally format an export 
The StreamNet Librarian provided updates to LibID keys in order to maintain the

of the library reference database of StreamNet documents 
one-to-one relationship between records in the StreamNet Library database and

for routine inclusion in the StreamNet database for use by 
the StreamNet data system's Reference table.

the web query system.


Objective:
2
Task:
3
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 28 of 56
Region
6
Whenever new tabular data with a spatial component are 
Limited progress was made on this task this quarter.  New tabular data were 

submitted to the Region (e.g., fish distribution, hatchery 
submitted to the region late in the quarter and they are undergoing review. These

facilities, etc.), create regional GIS layer(s) from this 
data will be incorporated into the regional GIS and posted in FY-05.

information where possible.  Verify correct format, accuracy 

and logical consistency of spatial data sets and attributes 

through coordination with state GIS contacts and then load 

data to the regional database in coordination with the 

database manager.  Post mappable layer(s) to the online 

query system, the ArcIMS interactive mapping system, and 

as downloadable layer(s) for StreamNet GIS users.

Region
7
Maintain a library of StreamNet GIS layers for internal use 
The library of GIS layers and metadata was maintained.

and as downloadable data on the web site with complete 

documentation (metadata).

Region
8
Obtain and refine layers such as ESUs, ecoregions, or 
Work continued to expand the regional spatial data library.  Draft Northwest critical

elevations, and create cross tables for use by the query system.
habitat data and modified regional watershed boundaries were obtained from NOAA

Fisheries.  Improved base data layers (administrative boundaries, transportation, etc.)

were compiled from numerous sources (USGS, ESRI, BLM, etc.).
Region
9
Assist the database manager with the spatial component of 
The GIS Specialist gained familiarity with the spatial referencing routines used by

data and its implementation online.
the on-line query system and helped the database manager resolve location coding

issues as they surfaced.

Region
10
Maintain and update, as necessary, the 1:100,000 scale 
The Regional GIS specialist worked with the states to develop a plan for enhancing

hydrography files for the states and the PNW region.  
the 1:100,000 scale hydrography with 1:24,000 scale linework in areas where

Submit all changes to the StreamNet database at the Regional
fisheries data exists.   Plan development is on-going and includes procedures for


office.
incorporating updates at the regional level.
Region
11
Integrate the functioning of the GIS system with the 
Routine coordination between the GIS and database systems continued during the

StreamNet fisheries and habitat database in support of the 
quarter.

query system.  Maintain up-to-date cross tables used via 

the StreamNet web interface to select information by 

geographic area.

Region
12
Maintain the Protected Areas database.  Provide access to 
See Objective 4, Task 5, Job 1.  This job is a duplicate and will be dropped in the

the Protected Areas data through the online queryable 
next work statement.

database and through the interactive map application.  

Work to resolve the remaining location issues where 

protected areas did not translate well to the 1:100,000 


hydrography


Objective:
2
Task:
3
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 29 of 56
WDFW
1
Manage data at the agency level (including data loading, data
We maintained and updated smolt and adult trap databases.  Documentation is

updating and quality assurance), develop and maintain FGDC
taking place to better understand the dynamics of these two databases and to

compliant metadata for GIS data, work toward developing
better understand the data contained within them.  Data were managed at the

metadata for tabular data, and exchange data to PSMFC
agency level as well as the StreamNet level to meet the special needs of both 

according to deadlines specified in this work statement.
entities.  Work is being done to bring WDFW data closer to the StreamNet DEF

which was developed to capture data not only for management purposes but to better meet the needs of everybody who is data driven.  Continued effort was made to better manage data and bring them closer to a standardized format for easier and more timely exchanges.

StreamNet Staff who manage key spatial datasets attended WDFW's metadata training on September 20.

Objective
2
Data management and delivery
Task
4
Data exchange standards

Establish and maintain data exchange standards to ensure consistent content and format of data that originate from multiple data sources.  Monitor adopted and proposed Data Exchange Formats (DEF) for data categories described under Objective 1. This task will provide coordination and technical assistance regarding interpretation of database structures and codes.  The formal process for creating new and revising old DEFs may require significant amounts of time, potentially more than a year, for complex data categories
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Work cooperatively through the Steering Committee, 
The Oregon subbasin planning data pose a number of questions concerning DEFs.  If

following the DEF Process document, to revise existing and 
these data are to be maintained for periodic updates of the watershed assessments,

develop new DEFs to assure regional data consistency and 
then we need to consider which of them are candidates for DEF development.  We

allow for inclusion of new data types.
will use the Oregon data archives to raise this question with the Steering Committee.  

Long term maintenance is really a regional question which must be decided by the

NPCC.  We will work to encourage the NPCC to adopt archiving and maintenance

procedures.

FWS
1
Work cooperatively through the Steering Committee, 
The StreamNet forum hosted very lively discussions of the new HatcheryReturns,

following the DEF Process document, to revise existing and 
HatchDisposition, and Age DEF for several weeks.  This required significant 

develop new DEFs to assure regional data consistency and 
participation of personnel who were involved in the redesign of this DEF,

allow for inclusion of new data types.
including the FWS StreamNet Project Leader.

IDFG
1
Work cooperatively through the Steering Committee, 
The data coordinator has continued to participate in DEF discussions, most notably

following the DEF Process document, to revise existing and 
for hatchery returns and barrier types.

develop new DEFs to assure regional data consistency and 

allow for inclusion of new data types.


Objective:
2
Task:
4
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 30 of 56
IDFG
2
IDFG StreamNet will take the lead on developing DEFs for 
Due to work on CSMEP and the Bull Trout Status Review, plus just already having

two new data categories:  Juvenile Fish Abundance and 
a full plate of data compilation, we did not initiate any new DEFs this year.

Run Reconstruction.

MFWP
1
Work cooperatively through the Steering Committee, 
Montana staff continued to assist in the development of the Resident Fish Hatchery

following the DEF Process document, to revise existing and 
Release DEF and the Restoration Project DEF.

develop new DEFs to assure regional data consistency and 

allow for inclusion of new data types.

MFWP
2
Co-develop a draft resident release DEF, in cooperation with
MFWP and WDFW Staff worked  on the hatchery release DEF and Mike Banach 

 Leslie Sikora, WA StreamNet
has developed a draft DEF.

ODFW
1
Work cooperatively through the Steering Committee, 
Staff communicated with Regional StreamNet and other StreamNet partners on

following the DEF Process document, to revise existing and 
issues related to the Hatchery Release, Hatchery Return, and Age data DEFs during 

develop new DEFs to assure regional data consistency and 
the quarter.

allow for inclusion of new data types.

ODFW
2
Review the Barrier DEF for juvenile fish passage and 
The GIS Analyst continued efforts to refine the DEF related to the StreamNet Fish

recommend an approach to the Steering Committee.
Barrier table.  He posted a proposed set of Fishway Type codes to the StreamNet 

Forum and solicited feedback as part of the DEF update process.  He also worked

with Regional StreamNet staff to find agreement on barrier related changes that

will be included in the upcoming draft DEF document.
ODFW
3
Initiate the process to develop a new DEF for fish screen data.
Effort toward developing a new fish screen DEF was redirected this year due to staff

vacancies and a shift in priorities.  Unless a DEF for fish screen data becomes a 

priority at the Regional level, this task will be postponed through FY-2005 as well.
ODFW
4
Investigate the potential for developing a Life-stage Timing 
Effort toward developing a life state timing DEF was redirected this year due to 

DEF.
priority shifts brought on by the CSMEP effort and staff vacancies.  Unless a DEF

for life-stage timing data becomes a priority at the Regional level, this task will be

postponed through FY-2005 as well.


Objective:
2
Task:
4
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 31 of 56
Region
1
Work cooperatively through the Steering Committee, 
Development of a new DEF for habitat restoration projects was completed and

following the DEF Process document, to revise existing and 
reviewed by all StreamNet partner agencies.  This data exchange format took

develop new DEFs to assure regional data consistency and 
significant time in both quarter 3 and quarter 4, with substantial time required to

allow for inclusion of new data types.  The regional 
negotiate lookup tables for the various activities that occur on the ground.  These 

Biologist will serve as the primary coordinator of the DEF 
changes will be incorporated into the next version of the StreamNet DEF document,

process and is responsible for updating and publishing the 
which is scheduled to be completed in the first quarter of fiscal year 2005.  This

official DEF document.
effort's time investment delayed other work.  Late in the quarter the Program manager and the Regional Fisheries Biologist attended the annual meeting of the Organization of Fish and Wildlife Information Managers.  At that meeting a representative of Ducks Unlimited from the San Francisco area presented work they have done on a habitat enhancement database for their scope.  The database structure shown was very similar to the new StreamNet structure, which we were happy to see.  Two independent database design efforts arriving at the same place is a good sign that a best solution was achieved.  Also, we think it holds promise of easily sharing data with Ducks Unlimited both in the San Francisco area and in StreamNet's area.

During this quarter difficulties arose with the data exchange formats we created last year for hatchery returns and age data.  Both issues arise when fish from several sources are pooled together prior to being sexed or spawned or trucked to other locations.  A probably best solution was identified prior to the end of the quarter but this effort was not quite finished.  It is anticipated that resolutions to these issues will be adopted for inclusion in a new DEF in the first quarter of fiscal year 2005.

While working with hatchery returns data, apparently duplicate data were found to actually differ because two stocks of the same subrun of fish returned to a single hatchery.  Because this is very likely confusing to data users, we discussed the possibility of capturing the "stock" of fish in the hatchery returns data.  Discussions about this continued past the end of the quarter and into fiscal year 2005.

Since the inception of our fish migration barriers data category (at least 6 years), we have been using a draft list of fishways that may be present to help fish pass barriers.  This quarter ODFW suggested we develop a better, smaller list of fishway types and presented a new draft list.  As the quarter came to an end, this new draft list was being reviewed by the Regional Fisheries Biologist.  The new list should be adopted with the next DEF.

Region
2
Investigate the use of the "TypeID" field in StreamNet time 
No work occurred on this task this fiscal year.  Other time-sensitive priorities that

series data in relation to other fields.  Propose fixes if 
came up prevented dedicating time to this job.  This task will be carried over into

appropriate, and adopt through the DEF modification process.
fiscal year 2005.


Objective:
2
Task:
4
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 32 of 56
Region
3
Initiate work on a new DEF for Fish Sightings data.  Review 
No work occurred on this task this fiscal year.  Other time-sensitive priorities that

the approach being taken in California and in coordination with
came up prevented dedicating time to this job.  This task will be carried over into

the cooperating projects, adapt for use in the Columbia Basin.
fiscal year 2005.
WDFW
1
Work cooperatively through the Steering Committee, 
The Location Data Manager worked with the Habitat Restoration Project DEF team

following the DEF Process document, to revise existing and 
to finalize their proposal.

develop new DEFs to assure regional data consistency and 

allow for inclusion of new data types.

WDFW
2
Co-develop a draft resident release DEF, in cooperation with
Early this quarter, discussions revealed that we generally agree that the hatchery 

Janet Hess-Herbert, MT StreamNet.
release DEF should focus on bare-bones information.  WDFW didn't have time this

quarter to finalize discussion on what this means and is planning time to engage in

this next quarter (FY-05).

Objective
2
Data management and delivery
Task
5
StreamNet Internet sites

Continue to maintain and enhance the StreamNet Internet sites.  Provide access to StreamNet data products through the Internet at both the regional and cooperating project levels.  The StreamNet home page (www.streamnet.org) will continue to be utilized as the project's primary data delivery vehicle.  Priority will be given to incorporating data developed through Objective 1 and providing access to reference materials secured through Objective 3.  The site will also be used to archive data sets developed by FWP participants for data that do not fit within the StreamNet DEF, including the means to index and search the archive.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Provide ongoing review of the StreamNet website through 
Oregon subbasin planning data archives are being posted to StreamNet.  While some

routine use of the site, providing feedback to StreamNet staff
questions concerning the best method of providing access to these data to users

at PSMFC on any problems, errors or needed improvements.
remain, it is likely data will be posted to the subbasin planning FTP site, at least 


initially.
CRITFC
2
Maintain, and enhance as needed, the web pages used to 
Library web pages were updated as needed.  Several documents were digitized and

provide public access to the StreamNet Library collections 
added to the website for retrieval by patrons.

and services, including hardware and software maintenance,

web page development, and system security.
CRITFC
3
Work with PSMFC staff to upgrade formats for displaying 
We added the availability of materials to the web catalog displays.

library catalog search results to facilitate development of 

bibliographies and to assist patrons locating needed literature.
ODFW
1
Provide ongoing review of the StreamNet website through 
Review of the StreamNet website continued during this quarter.  Specifically,

routine use of the site, providing feedback to StreamNet staff
Regional StreamNet staff were notified of a data type error in the online query 

at PSMFC on any problems, errors or needed improvements.
system, and of a road label display error in the IMS system.

Objective:
2
Task:
5
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 33 of 56
ODFW
2
Manage and maintain Oregon's web-based data integration, 
For the period of July through September 2004, our web server had 577,815 total

communication, and data transfer systems and their links to 
hits (FTP and HTTP combined), and 44,296 page views via HTTP and 4,520

StreamNet.
files downloaded totaling 1.53 GB’s via FTP.  The monthly page view statistics for 

the NRIMP website alone were 5,725 in July, 6,065 in August, and 5,842 in September for a total of 17,659

Many additions, modifications and improvements were made to the NRIMP web site, including posting the new report, “Upper Rogue Smolt Trapping Project, 2004”, re-establishing links to our stream flow restoration priority maps page, and updating the carcass placement, contact, and Barrier GIS pages to reflect the latest information.

The Database Manager has begun incorporating the Oregon.gov website design model into our web application framework.  This will allow our sites to adhere to the specifications of the Oregon.gov web initiative while maintaining our use of dynamically generated content.  The Assistant Database Manager updated the online NRIMP Reference site 

Region
2
Maintain and enhance the functionality, look and usability 
No significant updates were made to the web query system this quarter because of 

of the StreamNet web-based query system.
other priorities.

Region
4
Review and rearrange the links pages on the StreamNet web site.
A link to the Federal Caucus web site (www.salmonrecovery.gov) was added.
Region
5
Maintain the GIS Data, Map, and PNW Reach File Internet 
Routine maintenance continued for the GIS data, map and PNW Reach File web.

pages.
pages

Region
6
Maintain, update as necessary, and improve the Internet 
The GIS specialist attended on-line mapper (ArcIMS) training and began work on a 

mapping component to the StreamNet web site to allow 
new Internet mapping application for StreamNet.  This includes testing Web Map

users to access StreamNet data through interactive map 
Services as a means of adding background imagery (e.g., DRGs and orthophotos)

interfaces.  Improvements might include such items as 
to the StreamNet IMS applications.

adding DRGs or aerial photos to the IMS applications, and 

showing trend locations in the web query system.


Objective:
2
Task:
5
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 34 of 56
Region
7
Incorporate 5th and 6th field HUC GIS coverages into the 
This item was discussed during the fourth quarter, with the intention of determining 

web-based data query system and Internet mapping 
a timeframe for completion.  The discussion turned to the necessity and feasibility of

applications so data can be provided by HUC 5 and/or 6, as 
doing this job, as well as the work load involved.  It was decided that at least for the

data become available at those scales.
present time we would not pursue this functionality in the query system for two main

reasons.  First, this would require extensive effort, but during a reexamination of the

utility of this idea we decided that, for the types of data that we currently deliver, division by 5th-field HUC may be useful in the future, but division by 6th-field will probably never be of significant value.  Second, the existing 5th- and 6th-field HUC boundaries still have a few remaining problems.  For these reasons we thought it best to put this effort off until a more definite need develops in the future.

Region
8
Deploy new query system components and data categories 
Much progress was made in determining how to deliver age data via the web query

that are approved by the Steering Committee.
system.  We hope to have age data available for querying and download during the 

first half of fiscal year 2005.  The main issue remaining is identifying which years' 

records to include in the output.

Region
9
Maintain logs of web query history and error events.  Track 
Use of the StreamNet website remained strong during the quarter, with an average of

and report Internet site usage by month and investigate web
7,365 non-StreamNet visits per month from 4,362 unique IP addresses (Table 1).  

 query system errors encountered.
Use of the online data query system averaged over 10 per hour for the quarter on a


24 hr day basis.


Table 1.  Use of the StreamNet website during the fourth quarter, 2004.
	
	July-04
	Aug. -04
	Sept.-04

	Overall Page Requests
	51,244
	61,654
	57,156

	Number of Visits
	7,278
	7,656
	7,160

	Unique Visitors
	4,422
	4,312
	4,351

	Data Query Page Requests
	16,942
	17,522
	12,439

	Unique Query Sessions
	7,974
	9,992
	4,390

	Unique Query Sessions / hr.
	10.7
	13.4
	6.1

	Data Reports Viewed
	2,056
	1,629
	1,970

	FTP Files Downloaded
	581
	1,183
	1,216


WDFW
1
Provide ongoing review of the StreamNet website through 
No significant new capabilities needed review during FY-04.

routine use of the site, providing feedback to StreamNet staff

at PSMFC on any problems, errors or needed improvements.

Objective:
2
Task:
5
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 35 of 56
Objective
2
Data management and delivery
Task
6
Respond to data / information requests

Receive and respond to requests for data and information, source materials, and custom products at the regional and cooperating agency levels.  Response to requests will be honored within the limits of available resources, with priority given to information requests having direct relevance to the Fish and Wildlife Program.  Other priorities will include implementation of the Endangered Species Act and federal, state, and tribal natural resource management activities.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
IDFG
1
Respond to requests for data, maps, technical assistance, 
We responded to 21 requests for information, maps or technical assistance.  The

source materials, or custom data products at the agency 
requests were distributed as 2 state government, 1 federal government, 15 private

level, within the capabilities provided by base funding.  
industry, and 3 non-governmental organizations.  The requests included 19 species

Requests will be logged and reported.
lists or distribution queries, 1 for redd counts and 1 general GIS data.
MFWP
1
Respond to requests for data, maps, technical assistance, 
We provided a HUC level map to every state and federal biologist in Montana 

source materials, or custom data products at the agency 
displaying Westslope or Yellowstone Cutthroat distribution, location of genetic

level, within the capabilities provided by base funding.  
sampling sites and a table listing the results for the genetic sample.  We also filled 18

Requests will be logged and reported.
GIS map/data requests during the quarter.
ODFW
1
Respond to requests for data, maps, technical assistance, 
The monthly breakdown of unique users (reflected as distinct IPs) who viewed /

source materials, or custom data products at the agency 
downloaded data from the ODFW FTP site during this quarter is 160 (July), 166

level, within the capabilities provided by base funding.  
 (August), and 196 (September).  Also, 1.53 GB of data were downloaded from 

Requests will be logged and reported.
this site by 444 unique users. 

The monthly breakdown of unique users (reflected as distinct IPAs) reported for the April – June period were incorrect.  The actual number unique users who viewed / downloaded data from the ODFW FTP site during the previous quarter was 186 (April), 176 (May), and 168 (June).  

A total of 7 data, 3 document, 4 map, and 6 “other” requests were answered during this quarter.  A detailed list by requester and request type can be made available upon request.  The list of requests below is provided as an example of the range of requests we respond to.  These requests included:

a.  Providing MS Access technical support to ODFW Fish Division staff in Salem.  

b.  Summarizing barrier and stream mile information in response to a request related to potential trout angling opportunity areas within the Willamette basin.

c.  Summarizing fish passage barrier information above Bonneville Dam related to BiOp comments that ODFW is preparing.

d.  Responding to questions related to our life-stage timing dataset, a fire intensity dataset, and our fish presence survey data.

e.  Providing GIS technical support to the Statewide Wildlife Conservation Strategy effort.

Objective:
2
Task:
6
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 36 of 56

f.  Producing a map related to proposed changes to fishing regulations on the Rogue River.

g.  Providing our existing list of PSC Code - LLID cross references to NOAA-Fisheries staff in Seattle so he could map coastal coho hatchery release information.

h.  Creating a series of 8.5 "x 11" maps that would give a basic illustration of the hydrology of the Molalla, Santiam, and Upper Willamette/ McKenzie watershed areas.

i.  Providing an Oregon Lakes dataset with LLID's to DEQ.

j.  Providing Regional StreamNet with a list of data NRIMP provides access to that isn't provided to and made available on StreamNet.

Region
1
Respond within one business day to requests for data, 
Staff responded to 21 information requests during the quarter (Table 2).

information or help.  Log and report responses to all 


requests received.
Table 2.  Number and types of information and help requests serviced by Regional


staff during the fourth quarter, FY-04  
	Requester Type
	#
	
	Type of Request
	#

	Environmental group
Federal agency
General public
Graduate student
Local government
Private consultant
State agency
Tribe / tribal organization
  Total
	  2

  4
  4
  1
  1
  3
  3
  3

 21
	
	Can't find data
Data interpretation
Error report
General fish biology
GIS
Library
Map
Other
   Total
	  2
  2
  4
  2
  7
  1
  1
  2

21


Region
2
Finalize a standard user request tracking database structure 
Higher priority tasks came up this quarter and as a result this task was not addressed.  

so that all StreamNet partner agencies can use the same 
This task will be addressed next fiscal year as directed by the Steering Committee.

format for reporting responses to requests for data and 


other information or help.

WDFW
1
Respond to requests for data, maps, technical assistance, 
Over two dozen custom data requests were handled by WDFW StreamNet staff this

source materials, or custom data products at the agency 
quarter, largely involving fish distribution, spawner survey, and age data.  Custom

level, within the capabilities provided by base funding.  
maps were also generated for both internal and external customers.  WDFW's 

Requests will be logged and reported.
SalmonScape Web-based application and the StreamNet online application also

provide users with WDFW StreamNet data, though the specific figures there are 

hard to obtain.  In addition, over 100 standard data requests were handled by

WDFW's Priority Habitats and Species data release staff, all of which involve spatial

hydro or fish distribution data that are compiled and managed by WDFW StreamNet


Objective:
2
Task:
6
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 37 of 56
Objective
3
Library and reference services

Provide professional library services to the Columbia Basin's fish and wildlife decision-makers, planners, managers, and researchers by acquiring and cataloging StreamNet source documents and other related material; and by providing open and efficient access to these materials.  Provide a repository for the source documents for the data contained in the StreamNet database.
Objective
3
Library and reference services
Task
1
Collection development

Develop a collection of materials applicable to the mission of StreamNet.  Collect, catalog and organize materials to document data sources, Fish and Wildlife Program activities and reports, and other gray literature for access by regional scientists, agencies, interested parties, and other libraries.  Project participants will submit reference documents for all data contained in the StreamNet 
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Obtain reference documents for all data developed under 
Reference documents for data submissions were received from participants and

Objective 1 and submit them to the StreamNet Library for 
scheduled for cataloging.  Work proceeded on integrating the StreamNet references

inclusion in the collection and catalog.
with the classified collection.

CRITFC
2
Coordinate source material submissions for data compiled 
The library continued to receive information and references from participating 

by StreamNet participants under Objective 1.
agencies.  Oregon has been very proactive in making sure all their references are

correctly identified and up-to-date.

CRITFC
3
Develop a collection of materials related to the Columbia 
We began to work on bibliographies of documents published by BPA in order to

Basin, including reports from other Fish & Wildlife Program 
make sure we have a complete collection of documents for the Fish and Wildlife 

projects, other agency documents as they relate to the 
Division.

Basin, and other published and unpublished materials as 

requested by clients.

IDFG
1
Obtain reference documents for all data developed under 
Library materials referenced in our data submissions for hatchery returns and age

Objective 1 and submit them to the StreamNet Library for 
composition were submitted to the StreamNet library.

inclusion in the collection and catalog.

MFWP
1
Obtain reference documents for all data developed under 
New references were entered as they were received in the library.

Objective 1 and submit them to the StreamNet Library for 

inclusion in the collection and catalog.

ODFW
1
Obtain reference documents for all data developed under 
The Data Analyst continued to add references related to data captured under 

Objective 1 and submit them to the StreamNet Library for 
Objective 1 tasks, and performing quality assurance on the Reference Database

inclusion in the collection and catalog.
records.  She also researched, located, requested, acquired, and provided a copy

of a document needed by the StreamNet Library.

Objective:
3
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 38 of 56

Staff made a couple of StreamNet Library submission this quarter, including 15 references related to 24K fish habitat distribution data in early August, and 37 references in late-September.  The hardcopy documents associated with this submission were delivered to the StreamNet Library on September 29th.  We also submitted corrected/updated information on 13 previously submitted StreamNet Library references that had been changed in our reference database as a result of our quality assurance.
ODFW
2
Initiate organization of ODFW Library documents and update
Organization of the ODFW Library continued throughout the quarter.  The Library

the library bibliography with new titles as they are identified.
Technician sorted through many boxes, and shelved roughly half the materials in the

Library.  She also coordinated the efforts of a local volunteer who spent nearly30

hours sorting ODFW Progress Reports by title and putting duplicates into boxes.
WDFW
1
Obtain reference documents for all data developed under 
The Assistant Data Manager, Region 5, re-submitted documents to the StreamNet

Objective 1 and submit them to the StreamNet Library for 
library that were missing.  Various reports were collected to help document data

inclusion in the collection and catalog.
contained within the databases managed by the WDFW StreamNet data managers.
Objective
3
Library and reference services
Task
2
Provide access to collection

Provide user access to the materials described in Task 3.1 by providing facilities for storage of paper and electronic copies of documents, an online catalog of all documents in the collection, and staff to answer location questions and respond to requests.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Provide and maintain an appropriate facility for the storage 
The library space has been maintained.  We continue to evaluate our current floor

and public use of the StreamNet Library collections.
plan to ensure we are making the best use of our space and shelving.
CRITFC
2
Catalog and organize the materials for ease of use by clients 
We were able to hire two interns over the summer through funding from CRITFC

and staff.
member tribes.  These interns greatly assisted our efforts in loading temporary 

records into the catalog for a large number of materials.

CRITFC
3
Provide access to the catalog of materials via the Internet 
The catalog was updated slightly more frequently than monthly using the 

and update the online catalog on at least a monthly basis.
Dreamweaver software.

CRITFC
4
Develop and execute a plan to place electronic documents in
URL's for documents were added to the catalog as documents were processed for the

the catalog and on the library website.
digital collection.

CRITFC
5
Develop and keep a schedule of open times and reference 
The new library technician was hired and assisted with keeping the library open on a

desk staff hours.
regular schedule.


Objective:
3
Task:
2
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 39 of 56
Objective
3
Library and reference services
Task
3
Library services

Manage the StreamNet Library and provide library services to the StreamNet user community, the Council's Fish and Wildlife Program, and the general public.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Provide information and reference services to library clients.
Over 160 reference requests were received from clients.

CRITFC
3
Provide interlibrary borrowing services for library patrons to
We continued to develop our collections through patron requests and Interlibrary 

 access materials not yet owned by the StreamNet Library.
loan.
Objective
3
Library and reference services
Task
4
Inter-library coordination

Engage in networking activities with other agency and regional library service providers to provide better access to other collections that will enhance the StreamNet Library and to avoid unnecessary duplication of effort and materials
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Provide interlibrary lending services for other libraries to 
The library filled 40 requests from other libraries through OCLC.

access the StreamNet Library's unique collection.

CRITFC
2
Maintain memberships in appropriate library and subject-
The librarian attended the Pacific Northwest Library Association 

related associations. Ex. IAMSLIC, NRIC, OFWIM, etc.

CRITFC
3
Provide consultations for groups and other agencies on 
The librarian met with the Audubon Society of Portland to discuss the possibility of

library organization and services.
the organization depositing a major collection on ornithology with the StreamNet

library for management.  In addition, the USFWS Columbia River Research 

Laboratory delivered approximately 40 boxes of materials for the library's

collections.


Objective:
3
Task:
3
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 40 of 56
Objective
4
Services to the Fish and Wildlife Program

Provide technical data services to Fish and Wildlife Program decision-makers and appropriate Fish and Wildlife

Program projects.
Objective
4
Services to the Fish and Wildlife Program
Task
1
Data and Data Services to Support the Fish and Wildlife Program

Provide data management assistance to the Fish and Wildlife Program, as requested.  Services may include custom development of data, provision of data from the StreamNet database to support FWP activities (such as planning, monitoring and evaluation, etc.), and general advice and technical assistance with database management, data delivery, and GIS.  Work under this task will have to be based on time available, particularly for larger requests.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Participate in various NWPCC planning and management 
We met several times with NPCC, Mobrand, or StreamNet Regional staffs to discuss

work groups to improve and coordinate regional information
options for archiving data and other material developed during subbasin planning.  

management programs, such as serving as leader of the 
The NPCC has not decided how to archive subbasin planning information 

technical work group for Oregon's Subbasin Planning effort.
regionally.  We continue to urge resolution of this issue as opportunities arise.  The

newly formed Northwest Environmental Data Network lists this issue as one of its

tasks.  We will work through that group, at least in the short term.

Staff nearly completed archiving Oregon subbasin planning data.  These archives are

nearly 4 GB in size, containing information on all or parts of 15 subbasins. Most of 

the data are in GIS formats.

IDFG
1
At the agency level, support Fish and Wildlife Program activities,
The data coordinator documented the procedures used in the CSMEP pilot data

such as R, M & E, subbasin assessment, etc., by providing data
inventory.  He also set up new workbooks for new CSMEP subbasins: the upper

and maps of existing StreamNet data and technical information
Middle Fork Salmon River and upper Salmon River, and populated them with

management advice or assistance as requested, within available
relevant data from the earlier pilot data inventory.  He is now providing training and

time and budget under base level funding.
oversight to IDFG staff who are entering additional new data inventory information. 
MFWP
1
At the agency level, support Fish and Wildlife Program activities,
Montana continues to monitor the activities of CSMEP.

such as R, M & E, subbasin assessment, etc., by providing data

and maps of existing StreamNet data and technical information

management advice or assistance as requested, within available

time and budget under base level funding.

Objective:
4
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 41 of 56
ODFW
1
At the agency level, support Fish and Wildlife Program activities,
This task was dominated this quarter with supporting the CSMEP effort.  Staff

such as R, M & E, subbasin assessment, etc., by providing data
completed development and beta testing of the CSMEP Database Web application.  

and maps of existing StreamNet data and technical information
The application is able to complete a Table C1 spreadsheet's lifecycle, from data

management advice or assistance as requested, within available
entry to the grouped display of data.  Focused attention was put toward error- 

time and budget under base level funding.
proofing as much of the application as possible, developing a discussion forum for


users to share comments and discuss data related topics, writing instructions and

creating a tutorial for using the application, providing technical support to data entry staff from all the CSMEP participants, resolving technical glitches that arose during the beta test phase, and adding features as requested and warranted.

The Data Technician finished populating the CSMEP data inventory spreadsheets for the Lower Columbia, and performed quality assurance on previously populated spreadsheets.  All the spreadsheets that have been developed by Oregon StreamNet staff were provided to ODFW’s CSMEP Biologists on August 24th for their review, evaluation, and continuance.

The Project Leader reviewed and revised an 'off the top of the head' listing of Columbia Basin data management (not data collection) projects that was put together by John Piccininni (our BPA COTR), as assigned during the Steering Committee meeting.
 Region
1
At the regional level, support Fish and Wildlife Program activities,
No specific requests for data were received this quarter.

such as R, M & E, subbasin assessment, etc., by providing data

and maps of existing StreamNet data and technical information

management advice or assistance as requested, within available

time and budget under base level funding.
Region
2
Participate in and assist regional Monitoring and Evaluation
The Program Manager continued participation with PNAMP and CSMEP to assist

efforts to provide relevant StreamNet data, and to initiate 
with any data needs identified.

work to obtain new data types necessary for R,M&E.  Since 

no specific requests or funding have been received for this, 

work may be limited to scoping and advising.  Development 

of new data types to serve R,M&E will be initiated only as 

current time and funding permit, or as current work priorities

are reprioritized by regional processes.

WDFW
1
At the agency level, support Fish and Wildlife Program activities,
No data requests or specific requests for assistance were received this quarter.

such as R, M & E, subbasin assessment, etc., by providing data


and maps of existing StreamNet data and technical information

management advice or assistance as requested, within available

time and budget under base level funding.

Objective:
4
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 42 of 56
Objective
4
Services to the Fish and Wildlife Program
Task
2
Participate in Fish and Wildlife Program Development Activities

Participate in planning, development and/or coordination meetings with regional entities to provide assistance in the area of data management, as requested, to support development of Fish and Wildlife Program projects and programs.  Provide input on ways StreamNet can effectively contribute to the programs and general advice about data management.  Participate in advisory groups, task forces, and other groups whose purpose is to enhance the effectiveness of the Fish and Wildlife Program relative to its data development activities.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Participate in groups to develop strategies for ESA recovery
No substantial work on this task was accomplished this quarter.  We continued to

planning efforts to ensure data and technical literature are 
pursue and advocate for this activity through staff participation in several inter-

captured and made regionally accessible. This will be done 
agency groups.  We did identify a substantial amount of "one-of-a-kind" gray

"as possible"' under base level funding.
literature and data in the ODFW John Day field office.  We will explore ways of

capturing these data as time and funding allow.
IDFG
1
At the agency level, work with regional entities to 
Throughout this year, we have provided expertise and time in support of the CSMEP

contribute data management expertise toward development 
project in Idaho.

of activities within the scope of the Fish and Wildlife 

Program.  Serve as a data management resource to the FWP.

MFWP
1
At the agency level, work with regional entities to 
Montana has participated in several conference calls of the NED project and 

contribute data management expertise toward development 
provided information on Montana's involvement in regional data management.

of activities within the scope of the Fish and Wildlife 


Program.  Serve as a data management resource to the FWP.

ODFW
1
At the agency level, work with regional entities to 
Oregon StreamNet staff participated in CSMEP meetings/conference calls on July

contribute data management expertise toward development 
15th, July 29th, August 31st, and September 15th.

of activities within the scope of the Fish and Wildlife 


Program.  Serve as a data management resource to the FWP.
The Oregon StreamNet Project Leader participated in the North-west Environmental

Data-network (formerly CBCIS) regular Project Team meeting via conference

call on June 27th.

Region
1
At the regional level, work with regional entities to 
The Program Manager continued participation with CSMEP to provide advice and 

contribute data management expertise toward development 
support related to data management.  We reiterated our offer of providing two

of activities within the scope of the Fish and Wildlife 
person months of assistance per state to the CSMEP data inventory effort.  That

Program.  Serve as a data management resource to the FWP.
support was built into work plans for FY-05.

Region
2
Continue participation on the Program Team for the 
The Program Manager continued participation in the Northwest Environmental

Council's project to develop a Columbia Basin Cooperative 
Data-network.

Information System to convey recommendations based on 

experience in the development of a regional approach to data


submission.


Objective:
4
Task:
2
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 43 of 56
Region
3
Continue participation in the Federal/State/Tribal Partnership
The Program Manager continued participation in PNAMP, serving on the Steering

for watershed data coordination (now known as the Pacific
Committee and the Data Management Module.  StreamNet offered to provide a

Northwest Aquatic Monitoring Partnership).  Participate
portion of the StreamNet Biologist's time to facilitate development of a project

in other R, M & E groups, including the Action Agencies and
tracking data system.

CBFWA, to provide support and data management expertise.


The Fisheries Biologist participated in two PNAMP Effectiveness Monitoring Module meetings.  PNAMP is beginning discussions about how to share information about habitat restoration projects, or about all projects funded by multiple agencies.  The scope of their effort is being defined, and we are assisting by helping them discuss and clearly define the scope of their effort.

WDFW
1
At the agency level, work with regional entities to 
The Project Leader provided extensive additions and corrections to a list of regional

contribute data management expertise toward development 
monitoring data projects compiled by John Piccininni (BPA) and Bruce Crawford

of activities within the scope of the Fish and Wildlife 
(Washington IAC).  The list, titled "PNW Management Resources", is being used

Program.  Serve as a data management resource to the FWP.
by PNAMP and other activity coordinating groups in the Region to identify potential

overlapping work and responsibilities among the many entities working on salmon

recovery.
Objective
4
Services to the Fish and Wildlife Program
Task
3
Support to Subbasin Planning

At the regional and cooperating agency levels, work with subbasin planners to provide needed information from the StreamNet database and to capture data developed as part of the subbasin planning process.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Participate in subbasin planning efforts, such as serving as 
The Project Leader continued to coordinate and provide technical assistance to

leader of the technical work group for Oregon's Subbasin 
Oregon subbasin planning groups.  Most of the effort this quarter involved archiving

Planning effort.
data from Oregon subbasins.  The Project Leader did participate in planning for

additional subbasin plan development during a "response loop" period.  We 

anticipate receiving an additional contract next quarter to provide additional 

assistance to John Day subbasin planners.

MFWP
1
At the state or local level, and within existing resources, 
Staff reviewed the subbasin plans and determined where they can integrate data and

work with subbasin planners to provide needed information 
how they fit within the Comprehensive Fish and Wildlife Plan.  The only data type

from the StreamNet database and to capture data developed 
new to MFISH would be a disease/pathogen database.

as part of the subbasin planning process.

ODFW
1
At the state or local level, and within existing resources, 
The Oregon StreamNet Project Leader reviewed some of the Oregon Level II Group

work with subbasin planners to provide needed information 
comments on some of Oregon's Subbasin Plans, noting where improved data 

from the StreamNet database and to capture data developed 
management might have addressed some of the concerns.

as part of the subbasin planning process.


Objective:
4
Task:
3
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 44 of 56
Region
1
At the regional level, and within existing resources, work 
The Regional Fisheries Biologist reviewed a draft data layout for subbasin planning/

with subbasin planning groups to provide needed 
TOAST that was developed by CRITFC.  No data have been obtained yet.

information from the StreamNet database and to capture 


data developed as part of the subbasin planning process 

and make it publicly available.

WDFW
1
At the state or local level, and within existing resources, 
Contacts with biologists who manage the Lewis and Kalama watersheds were made

work with subbasin planners to provide needed information 
in order to complete the CSMEP data inventory for those two watersheds.  Several

from the StreamNet database and to capture data developed 
phone conferences were attended to discuss web based data entry for this model.  

as part of the subbasin planning process.
Discussions on progress and needs were covered in these phone conferences.
Objective
4
Services to the Fish and Wildlife Program
Task
4
Archive and deliver independent data sets, as requested

Work with participants to aid in the capture and distribution of data generated through Fish and Wildlife Program activities and to help determine the most appropriate means of storing and disseminating them.  Where data do not fit in existing StreamNet data sets, post data in the archive as independent data sets in their native formats.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
IDFG
1
Work with FWP supported projects in the state to assist 
No independent data sets suitable for posting through StreamNet came to our

them with submission of their data sets to StreamNet for 
attention in Idaho, so none were delivered to PSMFC this year.

archiving and dissemination as part of the formal DEF or as 

Independent Data Sets.

MFWP
1
Work with FWP supported projects in the state to assist 
The subbasin plans were used during the review of northwestern Montana for the

them with submission of their data sets to StreamNet for 
Comprehensive Fish and Wildlife Plan; the appendices are still being reviewed to

archiving and dissemination as part of the formal DEF or as 
insure there are no new data types of value to MFISH and that the data collected

Independent Data Sets.
by the planning process are incorporated in MFISH.

ODFW
1
Work with FWP supported projects in the state to assist 
This task was intended to be performed on an opportunistic basis.  During the year,

them with submission of their data sets to StreamNet for 
no opportunities presented themselves, and therefore no work was performed under

archiving and dissemination as part of the formal DEF or as 
this task.

Independent Data Sets.

Region
2
Coordinate with BPA and BPA contractors and the StreamNet
This new independent data sets capability has not yet been advertised, so any use to

cooperators to capture data sets, reports, and other electronic
date is only from people who have been directed to use it.  During this quarter we 

materials for inclusion in the StreamNet Independent Data
received a water temperature data set from the Nez Perce County (Idaho) Soil and

Sets page.  Finalize metadata needs.  Create a tool to help
Water Conservation District..  They encountered a bit of difficulty installing the tool,

data submitters to easily provide needed information.
but successfully installed and used it, sending their data set to StreamNet.

Objective:
4
Task:
3
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 45 of 56
WDFW
1
Work with FWP supported projects in the state to assist 
Some work was done in this area with Bull Trout data, smolt and adult trap data and

them with submission of their data sets to StreamNet for 
historical index survey data.  Due to the work load with the escapement data, 

archiving and dissemination as part of the formal DEF or as 
hatchery returns data and CSMEP data, no in depth look at a possible DEF for these

Independent Data Sets.
data was explored.  This will be explored more in the next year due to these data 

being more complete and work with the regional biologists to move this data into a

database structure and away from paper or spreadsheet format.  Problems have arisen in the past with data being collected in a year to year format and different data collected in each year to meet management needs for that year.  Standardized data collection has been pursued for year to year collection and the storage and manipulation of historical data stored in various formats and software are being converted to a MS Access database.

Objective
4
Services to the Fish and Wildlife Program
Task
5
Protected Areas

StreamNet will a) maintain and provide access to the Council’s Protected Areas dataset, b) archive the official version as a historic record, c) in consultation with the Council, respond to requests for information concerning Protected Areas, and d) modernize georeferencing and make these data available through online mapping.  If the Council so directs, work with subbasin planners to record any desired changes to the protected status of individual streams.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
Region
1
Maintain the Protected Areas database, and as time allows, 
The Protected Areas data and interactive map pages were maintained during the 

work to resolve the remaining unresolved location issues 
quarter.  No effort to resolve the remaining unresolved location issues from the

that resulted from conversion of the data from the 1:250,000 
transfer of data from 1:250,000 to 1:100,000 were made due to higher priorities for 

scale to the 1:100,000 regional hydrography.
the new GIS Specialist.  This work will be carried forward to next fiscal year.
Objective
5
Project management and coordination

Provide effective leadership that ensures the production of high quality information products targeted at critical applications and the development of these products in a timely, cost-effective manner.
Objective
5
Project management and coordination
Task
1
Manage Project Activities

Administer all aspects of the StreamNet project at the regional and cooperating agency levels, including oversight of budget, personnel 

(including training and staff development), work statement preparation and implementation, coordination among participating agencies, 

active participation in steering committee work, and project reporting.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
Project oversight and guidance.  Participate cooperatively in
The Project Leader attended one steering committee meeting this quarter.  Input on

the StreamNet Steering Committee to guide the direction of 
agenda items was provided via e-mail and discussions at the steering committee 

the project, coordinate within respective agencies, and 
meeting.

resolve policy and technical issues for the project.

Objective:
5
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 46 of 56
CRITFC
2
Supervision.  Supervise project staff at the cooperator level 
Normal staff supervision was provided.

to provide guidance and staff development.

CRITFC
3
Budget.  Manage expenditures to accomplish the jobs in the
We had about a $2,000 over expenditure at the end of the fiscal year.  This was 

Statement of Work within the approved budget.
resolved by reclassifying some expenses to other funding sources.

CRITFC
4
Develop the annual project proposal and budget within 
The draft work statement and budget prepared last quarter was reviewed and revised

submission deadlines.
slightly prior to submission to BPA.

CRITFC
5
Report accomplishment of the work outlined in the annual 
The fourth quarter report was submitted within 30 days of the end of the quarter.

Statement of Work through quarterly progress reports 


submitted to PSMFC within 20 days of the end of each quarter.
CRITFC
6
Submit the draft FY-03 annual progress report for the sub 
Initial scoping of the annual report was done.  Work on producing the report will

project to PSMFC within 60 days of the end of the fiscal year.
occur next quarter.

FWS
1
Project oversight and guidance.  Participate cooperatively in
The Project Leader attended the quarterly Steering Committee meeting, providing  

the StreamNet Steering Committee to guide the direction of 
significant input during discussion of the new Hatchery related DEFs.

the project, coordinate within respective agencies, and 


resolve policy and technical issues for the project.
FWS
3
Budget.  Manage expenditures to accomplish the jobs in the
The remaining funding was allocated to completing the HatcheryReturns,

Statement of Work within the approved budget.
 HatchDisposition, and Age data submission for this fiscal year.

FWS
4
Develop the annual project proposal and budget within 
The preliminary budget for FY 05 was prepared and sent to PSMFC.

submission deadlines.

FWS
5
Report accomplishment of the work outlined in the annual 
The accomplishment report for the previous quarter was completed and submitted to

Statement of Work through quarterly progress reports 
PSMFC.

submitted to PSMFC within 20 days of the end of each quarter

IDFG
1
Project oversight and guidance.  Participate cooperatively in
The IDFG StreamNet project coordinator attended and participated in the 

the StreamNet Steering Committee to guide the direction of 
July Steering Committee meeting in Portland, OR.

the project, coordinate within respective agencies, and 

resolve policy and technical issues for the project.
IDFG
2
Supervision.  Supervise project staff at the cooperator level 
Project coordination and supervision for both StreamNet and non- StreamNet staff

to provide guidance and staff development.
were provided by the IDFG StreamNet project.
IDFG
3
Budget.  Manage expenditures to accomplish the jobs in the
The IDFG StreamNet budget was regularly monitored throughout the quarter.

Statement of Work within the approved budget.


Objective:
5
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 47 of 56
IDFG
5
Report accomplishment of the work outlined in the annual 
The 2004 IDFG StreamNet third quarter report was completed and submitted to the

Statement of Work through quarterly progress reports 
StreamNet project manager at PSMFC.

submitted to PSMFC within 20 days of the end of each quarter.
MFWP
1
Project oversight and guidance.  Participate cooperatively in
We attended the Steering Committee meeting in July in Gladstone.  Following the

the StreamNet Steering Committee to guide the direction of 
meeting, we performed assigned tasks from the meeting, including completing 

the project, coordinate within respective agencies, and 
review of our portions of the budget and the SOW for FY-05.

resolve policy and technical issues for the project.

MFWP
2
Supervision.  Supervise project staff at the cooperator level 
The discussions have continued with respect to Kalispell office staff moving to 

to provide guidance and staff development.
Helena; decisions made included Lydia Bailey will move to Helena as the GIS/Natural Resource Data Manager; Jeff Hutten will continue as the StreamNet western Montana Information Specialist but only at a half-time level; Kim Lindstrom will resign as of January 1 and her position will be rewritten and moved to Helena.  Steve Carson will continue as the Fish and Wildlife Data Manager.  StreamNet duties associated with Jeff and Kim will be reassigned to the remaining staff positions and some duties will be moved to a contract with NRIS.

MFWP
3
Budget.  Manage expenditures to accomplish the jobs in the
Final review of the FY-05 budget occurred and agency work plans were completed 

Statement of Work within the approved budget.
for StreamNet duties.  The Information Management Unit received .24 FTE from the

Fisheries work for fish data/map requests and technical support outside of the

StreamNet Workplan.

MFWP
4
Develop the annual project proposal and budget within 
The Montana FY-05 Statement of Work was approved and incorporated into the

submission deadlines.
StreamNet SOW to BPA and submitted.  Upon receiving the SOW back for the

regional staff, the Montana portion was provided to all FWP staff receiving 

StreamNet funding.

MFWP
5
Report accomplishment of the work outlined in the annual 
The FY-04 3rd quarter report was completed.

Statement of Work through quarterly progress reports 

submitted to PSMFC within 20 days of the end of each quarter.
ODFW
1
Project oversight and guidance.  Participate cooperatively in
A number of Oregon StreamNet staff members attended and participated in the July

the StreamNet Steering Committee to guide the direction of 
19 StreamNet Steering Committee meeting.  A demonstration of the new CSMEP

the project, coordinate within respective agencies, and 
Database Web application was given, and feedback was recorded and addressed.  

resolve policy and technical issues for the project.
The Steering Committee was also updated on Oregon’s pilot effort in the Grande

Ronde basin to test out the development of an enhanced 100k hydrography dataset.
ODFW
2
Supervision.  Supervise project staff at the cooperator level 
Oregon StreamNet’s Project Leader exercised routine supervision of StreamNet 

to provide guidance and staff development.
staff, and in some cases, non StreamNet staff.

Objective:
5
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 48 of 56

The Data Analyst and Data Technician attended a PowerPoint training session at Oregon State University on Thursday, July 22nd.  This was the second portion of the training, as they both felt they had enough experience to skip the first session.

Oregon’s GIS Analyst spent a day assisting Fish Screen and Passage program staff installing a sluice gate on the Clatskanie Falls fishway, and used the opportunity to discuss fishway categorization issues with the fish passage coordinator.

The Database Manager accompanied ODFW Fish Propagation staff to Elk Creek Hatchery to assist with a CWT retention check on two stocks of fall Chinook salmon.  About 1,000 smolts were checked for both coded-wire tags and fin clips.  The information captured, and the forms that were filled out represent what ultimately gets sent through HMIS to the RMIS system to calculate shed tag percentages for stocks of coded-wire tagged fish.  This real world experience aids in understanding the origin of the data we work with, and provides opportunities to consider data management related modifications that benefit the data flow process.

The GIS Analyst participated in a free online training seminar presented by ESRI on Scripting in ArcGIS.

ODFW
3
Budget.  Manage expenditures to accomplish the jobs in the
Routine budget tracking continued during the quarter.  A revised FY-04 budget was

Statement of Work within the approved budget.
submitted to StreamNet to account for the purchase of a new computer for our GIS

Analyst.  Oregon’s proposed FY-05 budget was provided to ODFW management

staff for review and forwarded to Regional StreamNet in mid-July..

ODFW
4
Develop the annual project proposal and budget within 
The draft FY-05 Statement of Work was submitted to Regional StreamNet in mid-

submission deadlines.
July.  At BPA's request, a month-by-month spending plan was developed for our

FY-05 StreamNet contract and submitted it to Regional StreamNet in late August.
ODFW
5
Report accomplishment of the work outlined in the annual 
Oregon's StreamNet 3rd-Quarter Report was completed and delivered to Regional

Statement of Work through quarterly progress reports 
StreamNet in late August.  Oregon StreamNet staff also reviewed and commented

submitted to PSMFC within 20 days of the end of each quarter.
on the corporate third-quarter report, and submitted our comments in late September.
Region
1
Project oversight and guidance.  Participate cooperatively in
The Steering Committee meeting was held in Portland on July 19-20.  Topics

the StreamNet Steering Committee to guide the direction of 
covered included:  CSMEP plans for FY-05, demonstration of the new online data

the project, coordinate within respective agencies, and 
inventory tool, finalizing content of the FY-05 Statement of Work, feedback from

resolve policy and technical issues for the project.  Serve as 
NOAA Fisheries on the critical habitat project, PNAMP, the new CalFish web page,

chair of the Steering Committee.
and a variety of technical issues.

Region
2
Supervision.  Supervise project staff at the regional level to 
Routine supervision of regional personnel continued.  Regional staff also welcomed

provide guidance and staff development.
and provided guidance to Van Hare, the new GIS Specialist.

Region
3
Budget.  Manage expenditures to accomplish the jobs in the
Routine budget expenditure tracking continued during the quarter.

Statement of Work within the approved budget.


Objective:
5
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 49 of 56
Region
4
Develop the annual project proposal and budget within 
The FY-05 Statement of Work and budget were finalized and submitted to BPA.




submission deadlines.
Region
5
Report accomplishment of the work outlined in the annual 
The Third Quarter Report was prepared with input from all of the project 

Statement of Work through quarterly progress reports 
cooperators and submitted to BPA.

submitted to BPA within 30 days of the end of each quarter.

WDFW
1
Project oversight and guidance.  Participate cooperatively in
The WDFW StreamNet Project Manager participated in the July 19-20 Steering

the StreamNet Steering Committee to guide the direction of 
Committee meeting, delivering a round-table summary of recent work and

the project, coordinate within respective agencies, and 
contributing to key discussion topics.  Materials were prepared for contributions to

resolve policy and technical issues for the project.
CSMEP, FY-05 work plan content finalization, a 24K/100K hydro hybrid layer

proposal, and the StreamNet QA/QC White Paper project.  The Committee decided

to continue pursuing the hybrid hydro layer and developing state-centric materials

for the White Paper.

WDFW
2
Supervision.  Supervise project staff at the cooperator level 
We talked with Washington's Department of Personnel to understand why viable

to provide guidance and staff development.
candidates weren't able to get on the hiring register.

Staff debriefed data compiler Gretchen Blatz before she left in order to understand the files she left behind.

To fill our vacant compiler position, we created an MS Access test for applicants and conducted interviews on the last three days of September.

The Project Manager and Region 5 Assistant Database Manager conducted personnel evaluations for the StreamNet staff under their supervision as part of the annual WDFW requirements.

On September 15 & 16, 2004, the Location Data Manager attended a class of ESRI's ArcHydro to further explore how we can integrate ESRI's products into our location data management.  She also made a small start on learning Structured Query Language (SQL).

WDFW
3
Budget.  Manage expenditures to accomplish the jobs in the
The Project Manager worked with the StreamNet Program Manager at PSMFC and 

Statement of Work within the approved budget.
the WDFW Fiscal Office to enact a late-term WDFW StreamNet FY-04 budget

reduction in order to offset some field work done in Spring 2004 for WDFW but

charged to PSMFC. 

The Project Manager managed the WDFW StreamNet budget toward an ending 

balance target of $1,000.


Objective:
5
Task:
1
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 50 of 56
WDFW
4
Develop the annual project proposal and budget within 
The Project Manager worked with his staff to finalize tasks, priorities, and

submission deadlines.
assignments for the WDFW StreamNet FY-05 work plan.  Budget details were 

finalized using the most recent WDFW benefits and overhead figures, and a monthly

spending plan was developed and submitted to the StreamNet Program Manager 

(PSMFC).

WDFW
5
Report accomplishment of the work outlined in the annual 
We submitted the WDFW FY-04 Third Quarter Progress Report to PSMFC on July 

Statement of Work through quarterly progress reports 
16, 2004.

submitted to PSMFC within 20 days of the end of each quarter.

Objective
5
Project management and coordination
Task
2
Coordinate with Related Activities Beyond the FWP

Maintain communications between StreamNet and other applicable regional and state-level fish and wildlife activities and agencies beyond the Council's Fish and Wildlife Program to identify means for collaborative data collection, storage, and dissemination.  Collaborative data activities will include tribal fishery programs within the Columbia Basin, federal land managers’ fishery programs, state fish and wildlife agencies, and, with respect to water use and stream development, state water resource management and environmental quality agencies. Collaboration with coast-wide and private data collection/compilation efforts will be pursued when this supports overall project goals.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
On an opportunistic basis, coordinate with other state, 
The Project Leader is also serves on the Pacific Northwest Aquatic Monitoring

federal, or tribal agencies and various local inter-agency 
Partnership (PNAMP), Northwest Environmental Data Network (NED), and the

planning and management work groups beyond the FWP to 
John Day Analytical Framework Group.  Improved data management and sharing

enhance the collection and management of data related to 
are concerns for all these groups.

management of fish and wildlife resources.

IDFG
1
On an opportunistic basis, coordinate with other state, 
Working with IDFG staff, we completed all but one of the bull trout status review

federal, or tribal agencies and various local inter-agency 
workshops.  Only the Jarbidge-Bruneau workshop remains.  We have prepared and

planning and management work groups beyond the FWP to 
distributed to all IDFG regional biologists draft maps based on those workshops.  

enhance the collection and management of data related to 
Review comments are being input into the database and we are also reviewing the

management of fish and wildlife resources.
entire database for errors and inconsistencies among workshops.
MFWP
1
On an opportunistic basis, coordinate with other state, 
Discussions continue between the Natural Heritage Program (NHP) and FWP 

federal, or tribal agencies and various local inter-agency 
concerning FWP incorporating NHP into the agency.  Options scoping will occur

planning and management work groups beyond the FWP to 
next quarter.  We attended the Fisheries Manager's meeting in September to discuss

enhance the collection and management of data related to 
a data dissemination policy which includes the distribution of MFISH data on a state

management of fish and wildlife resources.
level.  We continued to engage in discussions with NHP in the development of the

process and implementing the process of determining Element Occurrence records.  MFISH data continued to play a key role in the creation of the aquatic matrix for the Montana Comprehensive Fish and Wildlife Plan.


Objective:
5
Task:
2
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 51 of 56
ODFW
1
On an opportunistic basis, coordinate with other state, 
Several coordination activities occurred during this quarter, including:

federal, or tribal agencies and various local inter-agency 


planning and management work groups beyond the FWP to 
-- Meeting with ODFW, OWEB, and OSU Library staff to discuss how we can assist 

enhance the collection and management of data related to 
in making data collected by the North Coast Web Portal Project accessible via the

management of fish and wildlife resources.
web.  They are interested in using our Oregon Plan web application as their initial



data storage vehicle, which the portal would tap for responding to online inquiries.



We also discussed a strategy to avoid duplicating effort when we start collecting data from North Coast watershed councils.  


-- Our data management staff also met with North Coast Web Portal staff regarding the interoperability of their upcoming portal system to the OPSW metadata site.  They also discussed conforming searches of the site to some current bibliography standard, such as Z.3950.  A schema format and field descriptions for the OPSW data site were provided to Portal staff.

-- Meeting with ODFW Wildlife Division staff and staff from the Oregon Bridge Delivery Partners (OBDP) on Monday, Aug. 9th to coordinate GIS data development efforts regarding the in-water timing guidelines.  We agreed upon an initial data development approach and will be working cooperatively to address issues as the process evolves.


-- Staff participated in a conference call on Tuesday, September 7th, then met with Marine Program staff in Newport on Thursday, September 9th to discuss their data management, access, and dissemination needs, and our ability to help.  Several areas for different datasets were identified that we could streamline and make the transition of data to information on the web both easier and less error-prone.

WDFW
1
On an opportunistic basis, coordinate with other state, 
The Project Manager worked with TetraTech consultants to review a Web-based

federal, or tribal agencies and various local inter-agency 
ArcIMS site developed for displaying EDT data of interest to Council members and

planning and management work groups beyond the FWP to 
BPA.  He sent the URL around to StreamNet Steering Committee members and did 

enhance the collection and management of data related to 
a brief demonstration at the July Steering Committee meeting.

management of fish and wildlife resources.


The Project Manager held discussions with WDFW staff from the Habitat Program and others on barriers data compilation and any post-removal monitoring activities that were taking place, as a Steering Committee follow-up activity.  WDFW does not have a coordinated procedure for collecting standardized post-project data, as the staff who work on passage issues currently only do pre-project assessments and the improvement work itself.


Objective:
5
Task:
2
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 52 of 56
Objective
5
Project management and coordination
Task
3
Professional and Public Involvement

As needed, produce public information materials and participate in various meetings and forums (public or professional) to explain the project's capabilities and purpose and to generate support and additional data sources.  Activities may include brochures, issue papers, demonstrations, posters and talks to public, policy or professional groups and organizations.
Project
Job
Planned work elements                                                                                      
Accomplishments, Fourth Quarter 2004
                                                                  
CRITFC
1
As requested, prepare and deliver presentations to public, 
The Project Leader has been invited to participate in a panel discussion on subbasin

scientific and professional meetings to demonstrate project 
planning at the North Pacific/International Chapter of the AFS in November.

capabilities, services and accomplishments and to solicit 


additional data and involvement or coordination with the 

project.

IDFG
1
As requested, prepare and deliver presentations to public, 
No meetings were attended under the StreamNet project this year.

scientific and professional meetings to demonstrate project 

capabilities, services and accomplishments and to solicit 

additional data and involvement or coordination with the 

project.

MFWP
1
As requested, prepare and deliver presentations to public, 
We continued the regional meeting presentations including MFISH and the Fishing

scientific and professional meetings to demonstrate project 
Guide which uses all MFISH data.  We will attend the angler's forum next month

capabilities, services and accomplishments and to solicit 
and give a demo of the Fishing Guide.

additional data and involvement or coordination with the 

project.

Region
1
Publish at least two editions of the StreamNet Newsletter 
Only one newsletter was sent out during the fiscal year, though potential items were

during the fiscal year, providing readers with information 
collected all through the fiscal year.  At the end of the fourth quarter preparations for

about StreamNet activities, available data, data updates, 
the next newsletter began, and we anticipate one being published in the first quarter

new data services, etc.
of fiscal year 2005.


Objective:
5
Task:
2
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 53 of 56
Region
2
Prepare and deliver presentations to scientific and 
The Program Manager and the Regional Fisheries Biologist (under other funding) 

professional meetings to demonstrate project capabilities 
attended the annual meeting of the Organization of Fish and Wildlife Information

and accomplishments, and to solicit additional data and 
Managers (OFWIM) in San Diego, California.  StreamNet's Program Manager

coordination with the project.
became OFWIM's new president and delivered the keynote talk at the meeting,

discussing "Partnerships and the future of fish and wildlife information management."  He also chaired two mini-workshops, one entitled "Incorporation of end-user input into application design" and the other "Strategies for motivating field data collectors to provide metadata -- A brainstorm session."  The Regional Fisheries Biologist gave a presentation on StreamNet's new Independent Data Sets page and data submission tool, soliciting feedback on whether this concept exists in other places and also on how we might improve our current effort.  He also presented the StreamNet poster (updated during this quarter) during the poster session, and attended a USGS-National Biological Information Infrastructure metadata training.  It was hoped that the metadata training would let us produce NBII-compliant metadata for StreamNet's data sets and send these metadata to the NBII system, but the training was hampered by poor software.  Follow-up information was provided and further efforts will occur to meet the NBII metadata standard and send metadata to the NBII metadata clearinghouse.

Region
3
Developed and distribute materials to support the project.  
The StreamNet Fisheries Biologist updated the StreamNet poster in preparation for

Improve public materials such as the StreamNet brochure, 
display at the annual OFWIM meeting.

data inventories, etc. as needed.   Maintain and update 

explanatory materials such as the Query System User Guide 

and documents explaining data categories and structures, as

necessary.

WDFW
1
As requested, prepare and deliver presentations to public, 
This quarter, there were no opportunities to present the StreamNet Project at formal

scientific and professional meetings to demonstrate project 
meetings.

capabilities, services and accomplishments and to solicit 

additional data and involvement or coordination with the 

project.


Objective:
5
Task:
3
StreamNet Fourth Quarter Performance Report, Fiscal Year 
Page 54 of 56
Supplemental Information.  Work accomplished outside the specific work elements in the Statement of Work

Specific accomplishments during the fourth quarter, often on other funding sources, that did not relate specifically to any of the Tasks / Jobs in the annual Statement of Work, but that did relate to StreamNet and served the project mission.  

Project

Accomplishments, fourth  Quarter 2004


CRITFC

Work on the objectives and tasks relating to subbasin planning, regional monitoring and data management groups involved a combination of StreamNet supported staff and CRITFC staff funded by other resources
MFWP

Discussions continue between the Natural Heritage Program (NHP) and FWP concerning FWP incorporated NHP into the agency.  Options scoping will occur next quarter.  Continued to engage in discussions with NHP in the development of the process and implementing the process of determining Element Occurrence records.  MFISH data continued to play a key role in the creation of the aquatic matrix for the Montana Comprehensive Fish and Wildlife Plan.  The FWP Strategic Information Technology Plan has been accepted by the State Information Services Division; issues raised in the Needs Assessment portion of the plan are being reviewed and addressed by the FWP Information Services Steering Committee; issues have included a data dissemination policy, hardware/software purchases; procedures for designing/implementing centralized databases and a new Request Tracker that will be used for all information services requests within the Department.  We attended the annual Organization of Fish and Wildlife Managers meeting in San Diego which provided food for thought with respect to addressing data management issues within FWP and between FWP and other state and federal agencies.

ODFW

Oregon StreamNet's Database Manager continued to support the Oregon Plan Review (Metadata Warehouse) site and provide technical support to numerous users of the site.




Oregon's Statewide Wildlife Conservation Strategy GIS Coordinator fulfilled a request for a map to assist the Wolf Management Task Force.  Oregon StreamNet staff support of Statewide Wildlife Conservation Strategy continued throughout the quarter, mainly focused on providing GIS and analytical support.



Revisions to a Native Non-game Fish Distribution Development Project funding proposal were completed this quarter, and the proposal was submitted to the ODFW Wildlife Division for their review and approval.




ODFW’s Wildlife Division agreed to continue funding our support of the Wildlife Habitat Conservation Management Plan web application.  As a result, we incorporated additional requested changes to the site, and will continue to make modifications as warranted.  Interest was also expressed for us to develop a similar application for the Landowner Incentive Program.




We received approval to continue to pursue information on fishing sites in Oregon to bolster the information provided on the Oregon Fish Finder web site.  Work on this effort will resume in the next quarter.




Staff support of Oregon Subbasin Planning continued at a much lower level throughout the quarter.  The final Subbasin Planning Invoice Certification form was completed and submitted, officially completing our funded Subbasin Planning support.

Supplemental Information
StreamNet Fourth Quarter Performance Report, Fiscal Year 2004
Page 55 of 56



The GIS Technician completed development of Travel Management Area maps for the Dairy Creek, Conroy, Fox Butte, Rager, Devine Ridge, Chesnimnus, Tualatin, Upper Tualatin, Murderer's Creek, Luckiamute, Eagle Creek, Upper Rogue, Starkey, Jackson, and Rickreall areas during the quarter.  Many of the maps were sent to ODFW District Biologists for review, returned, and have been processed for printing.  He also filled a request for hunting access maps for the Heppner, Coombs Canyon, Timbers, Pokagama, and Forsea Ranch areas.




Web use statistics for the various web sites maintained by or related to Oregon StreamNet are provided in Table 3.




Table 3.  Page views recorded in the fourth quarter for the web pages maintained by or related to Oregon StreamNet.

	
	July
	August
	September
	Total

	Oregon Plan Metadata Warehouse
	542
	230
	206
	978

	CSMEP Database Web Application
	3,128
	822
	991
	4,941

	Oregon Fish Finder
	6,191
	5,759
	3,844
	15,794


Region

During this quarter StreamNet was contacted by Gavin F. Hanke, Curator of Vertebrate Zoology at the Royal British Columbia Museum in Victoria, British Columbia.  He pointed out several errors on our existing "Species Database -- Freshwater Fish of the Pacific Northwest" web page in the Public Education section of StreamNet's web site.  Several people over the past few years have pointed out other obvious errors, but we did not feel we had the required knowledge or reference materials to correct this page.  Several recent authoritative publications, along with information supplied by Gavin Hanke, now allowed us to correct this page.  The old version of this page can be seen at http://web.archive.org/web/20040221174131/www.streamnet.org/pub-ed/ff/Species/index.html.   The updated page is available at http://www.streamnet.org/pub-ed/ff/Species/index.html -- the new page also lists the sources of information used to create the page.
WDFW

Dick O'Connor and Brian McTeague participated in the 2004 Annual Meeting of the Organization of Fish and Wildlife Information Managers. O'Connor gave a presentation on data collaboration in the making of WDFW's SalmonScape Web application, and McTeague hosted a poster session on SalmonScape at the "Hacker's Ball".  Participation in the meeting was supported outside of the StreamNet contract.



Martin Hudson, Arleta Agun, O'Connor and McTeague collaborated in developing a model for deriving aboriginal (1880's) distribution of steelhead in Washington state, creating maps of such distribution, and providing assessment of the gains and losses in distribution from that time until the present.  These materials have been incorporated into WDFW's Steelhead White Paper, the scientific foundation for the upcoming statewide Steelhead Management Plan.

Supplemental Information
StreamNet Fourth Quarter Performance Report, Fiscal Year 2004
Page 56 of 56
�EMBED Word.Document.8 \s���








_1098250779.doc
[image: image1.png]






_1098250777.doc
[image: image1.png]






